## Sheet1
Project Name | Department | Annual Report Category | Project Description | IPA Delivery Confidence Assessment | SRO Delivery Confidence Assessment | Departmental Commentary on Delivery Confidence Assessment Rating | Start Date | End Date | Schedule Narrative | Financial Year Baseline (£m) | Financial Year Forecast (£m) | Financial Year Variance (%) | In Year Variance Narrative | Whole Life Cost (£m) | Costs Narrative | TOTAL Baseline Benefits (£m) | Departmental Narrative on Budgeted Benefits | Major Projects ID
Civil Service Pensions 2015 Remedy | CO | Government Transformation and Service Delivery | The 2015 Pensions Remedy Programme was created to end age discrimination within the Civil Service Pension Schemes and is also creating solutions to remediate any affected to historic members of the scheme. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. We are currently on track to implement the next 2 stages of the programme to deliver the functionality to rollback impacted members accounts to a pre-2015 position and offer retired members and immediate choice for benefit payments of the 7 year remedy period (1/4/2015-31/3/2022) and for future retirements a deferred choice. Amber status reflects some concerns around the suppliers resourcing levels. There is an agreed plan in place to mitigate this and we are working closely with the supplier to ensure effective delivery of the project. | 2020-05-20 | 2024-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. No deviation from planned schedule. We are on track to deliver the 'rollback' functionality by 1 Oct 2023 and Immediate/ Deferred choice from 1 Oct 23 onwards. | 7.9 | 4.2 | -47 | The budget variance exceeds 5%. This is primarily due to a significant underspend on behalf of our supplier and compounded in built contingency funds. | 34 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 34m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 34m. This is primarily due to the following factors. Forecast spend in 2022/23 did not materialise within the predicted project timeline and so was moved to 2023/24 forecating, as there remains a need for the work forecast for 22/23 to be completed to ensure timely completion of the programme. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. 2015 Remedy has no benefits associated with it as it is a rectification programme to remove unlawful discrimination | CO_0024_2021-Q2
Commercial Capability Expansion Programme | CO | Government Transformation and Service Delivery | The original Commercial Capability Programme successfully established the Government Commercial Organisation (GCO) - a single central employer of several hundred Commercial Specialists (Grade 6 and above) for central government departments. The Civil Service Board endorsed proposals that commercial capability building interventions should be extended to Grade 7 commercial professionals within central government, Wider Government Bodies (WGBs) and training and accreditation developed and delivered to the Civil Service contract management community. The Commercial Capability Expansion Programme has been established to impact these new target populations deeper within the Civil Service and more broadly across the Public Sector. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Following the IPA Assurance Review in March 2020 we received a programme Delivery Confidence Assessment (DCA) of Amber/Green. The Review Team found the programme had built significant success in building capability across the senior Commercial Function, including to G7s in Central Government Departments. We have followed up the review recommendations including a stakeholder stocktake review to improve delivery with the target contract management population and priority wider government bodies. However the impact of COVID-19 has significantly impacted delivery over the last 2 years and we downgraded our DCA to Amber. | 2017-04-01 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. As a result of COVID-19 impacts (including the transition of face to face service provision to digital) the Civil Service Board endorsed a 12 month programme extension to end March 2023. | 3.7 | 3.1 | -16 | The budget variance exceeds 5%. We are continuing to deliver within our operational constraints and are now forecasting to have a 600k underspend for this financial year (FY2022/23's budget comprises the Accelerator Fund of 3.02m plus 680k for Capability-building for the NHS). This is because only 29k has been spent to date for Capability-building for the NHS due to lower than expected demand throughout the financial year. | 26 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 22m. to 26m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 22m. to 26m. This is primarily due to the following factors. The Whole Life Costs has increased as it includes the FY2022/23's Accelerator Fund budget of 3.7m to bolster delivery. However, we are forecasting an underspend of 600k for this financial year. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agreed monetised benefits at 22/23-Q4. This is an enabling programme and captures qualitative and quantitative benefit realisation data for reporting with programme stakeholders. Whilst we have clear evidence that improved commercial and contract management capability drives commercial benefits and prevents value leakage, the benefits accrue in participating organisations and there are a number of factors at play. | CO_0020_1718-Q4
Falcon IT Platform Refresh and Migration | CO | Government Transformation and Service Delivery | Falcon is a business change programme that will fundamentally underpin the digital transformation of the Cabinet Office.The Transformation will be achieved through two key areas of investment. First we will update the OFFICIAL IT platforms within the Cabinet Office, which will contribute to reducing cyber-security risk, address legacy systems and automate underlying infrastructure. The second work stream the Cabinet Office we will invest in, will enable the implementation of the Central Digital Data Office (CDDO) interoperability policy standards and guidance through the migration of the department to Microsoft Office M365. This will enable better interoperability across government as we move both our people and data from Google Workspace to Microsoft 365. The Cabinet Office is at the heart of Government and a common productivity suite will enable more efficient and effective ways of working. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The DCA of Amber reflects the position of the Falcon Programme in February 2023. The programme has continued to build capacity and capability to ensure it moves forward, it has successfully on-boarded partners and commenced the Discovery phase. Delivery is closely managed by the a Programme Board attended by our Partners to ensure a balance in pace of delivery and quality and ensuring Value for Money. The Programme supports further independent assurance reviews and this are planned alongside the production of a Full Business Case that will be submitted for approval by the Cabinet Office and by HM Treasury for funding to build the new platform and migrate users and their data to Microsoft M365. | 2022-05-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The programme will complete discovery activity in autumn 2023. This will deliver a plan with a high level of confidence for the build of the new platform and the migration to M365. The schedule has a target date of 31st March 2025 with a contingency of one year that will be informed by discovery. The schedule will be monitored by the programme board to ensure value for for money and will will accelerate activity where appropriate. |  |  |  | The programme was challenged to move at pace but was unable to complete the complex procurement activity in the financial year due to extensions in timelines, which were at the request of the market. One of the preferred commercial frameworks was closed (G-CLOUD12), forcing the programme to move to G-CLOUD13 and restart that procurement. These factors were the key drivers behind the budget variance which also impacted the programmes ability to onboard staff resource. Commercial contracts for the 2 supporting partners were signed in Q4 23/24. | 52 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 52m. This is primarily due to the following factors. The Falcon programme has an approved outline business case with forecast costs. The programmes approvals allow it to move into discovery where the phase report will confirm second stage costs. With this data a full business case with final costs will be submitted. The whole life costs will be confirmed at this point. | 60 | The project's departmental-agree monetised benefits at 22/23-Q4 is 60m. The programme will deliver cashable and non- cashable benefits delivering improved collaboration and efficiency in line with the CDDO interoperability policy from the migration of the Department from Google to MS365. The OFFICAL platform refresh will deliver enhanced cybersecurity benefits including mitigating the potential costs of addressing a serious cyber security attack. | CO_0176_2223-Q3
Future Service Programme | CO | Government Transformation and Service Delivery | Future Services Programme is a series of procurement and transformation projects within the Pension directorate of GPG. Key projects within the programme include The Civil Service Pension Scheme (CSPS) and the Royal Mail Statutory Pension Scheme (RMSPS). Ministers have a legal requirement to deliver administration services for the CSPS. MyCSP Ltd currently administers the CSPS under a contract with the Cabinet Office that will expire on 31 December 2023, although transitional protection clauses in the contract means that the current service can continue until December 2025. RMSPS services expires in September 2023 however a year long extension has been although transitional protection clauses in the contract means that the current service can continue for 2 years. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. Awaiting outcome of Gate 3 Review | 2020-10-01 | 2025-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-12-31 to 2025-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-31. This is primarily due to the following factors. Prject schedule has slipped due to extended time required on negotiations for CSPS | 1.6 | 1.7 | 6 | Data already completed on GMPP |  | NA The project did not provide data | 11 | The project's departmental-agree monetised benefits at 22/23-Q4 is 11m. Benefits have been defined as part of the OBC and FBC which will be deleivered during transition. The final business case has been worked on and submitted to COAB for the July board part of which work will be done to revisit benefits identified within the early cost modelling stage to establish whether they are still relevant. | CO_0027_2021-Q4
GOV.UK One Login | CO | ICT | GOV.UK One Login will provide a single account for people to log in, prove (and then reuse) their identity in order to access all central HMG services. The programme, delivered by GDS, will replace the current digital landscape of siloed and duplicative sign-in and identity-proofing methods, providing a front door for services that will continue to be delivered by government departments. In doing so GOV.UK One Login will provide a better user experience, more efficient use of government resources and strengthen the government's ability to counter fraud. The system has been designed with inclusion at its core, so that it will work for everyone. One Login will raise the degree of confidence of identity verifications against internationally recognised GPG 45 standards and improve our ability to spot patterns and more sophisticated types of fraud. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The GOV.UK One Login programme continued to deliver at pace in 2022/23, successfully meeting its major planned milestones. These included the launch of One Login's web- and app-based identity checking routes, integrated with its authentication and account functionality, and the onboarding of its first [8] government services. By year-end, over 1 million users had successfully proved their identity through One Login. The programme deepened its collaboration with departments, agreeing roadmaps that will see the bulk of central government services move to One Login in the current Spending Review period, in line with the programme's business case. This progress also enabled the legacy GOV.UK Verify system to be retired, as planned. The overall AMBER rating reflects the challenging pace of delivery, especially as GOV.UK One Login scales up, and the complexity of both the technical solution and the migration of major government services, all of which the GDS team is actively de-risking. | 2021-01-04 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. We are Amber at the end of 2022/23 due to the pace and complexity of delivery, complicated technical solutions, Cyber and Information security, and stakeholder challenges. We have multiple services and accessibility issues to consider which makes this a very technical and challenging programme within the product development space. Overall confidence is increasing following the upturn in recruitment, careful planning and effective risk management. Onboarding of the first set of services has given further confidence in completion of the programme as scheduled in 2025. | 114 | 114 | 0 | The programme's departmental-agree Whole Life Cost at 22/23-Q4 is 305m. One Login build and running costs have ramped up in 23/24 as the product is developed and services onboarded. | 305 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 22m. to 305m. This is primarily due to the following factors. The programme's departmental-agree Whole Life Cost at 22/23-Q4 is 305m. One Login build and running costs have ramped up in 23/24 as the product is developed and services onboarded. | 1752 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1752m. The programme's departmental-agreed monetised benefits, at 22/23-Q4, is 1751.6m for the 5 year projection. The cashable savings in the business case include reducing identity verification and authentication costs; reducing total cost of online user support whilst reducing total user support; and, reducing public sector fraud. We are in the process of developing KPI targets, and developing a dashboard for benefits realisation. In doing so, we are working closely with HMT and the Evaluation Task Force in the development of this monitoring plan. We are also working with departments as they onboard to update our baseline assumptions, through the administration of a data collection instrument. | CO_0033_2122-Q1
Government Hubs and Whitehall Campus Programme | CO | Government Transformation and Service Delivery | The Government Hubs and Whitehall Campus (WHC) programme is transformative, delivering the Governments priorities: - Providing a smaller, better and greener public estate - Strengthening the UKs economic recovery from Covid-19 - Levelling up economic opportunity, maximising productivity and improving value - Supporting the governments ambition to reach net zero carbon emissions by 2050 - Strengthening the Union of the United Kingdom The programme supports the Places for Growth (PfG) initiative which encourages the movement and creation of jobs outside London and contributes to the levelling up agenda; as well as supporting pursuit of the Governments Industrial Strategy and the transformation of the Civil Service, . | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Programme remains Amber, in line with IPA rating given in April 2022. In the period the Programme has delivered a new Hub in Peterborough alongside interim accommodation in Darlington, Birmingham and Stoke-on-Trent. Since the last IPA Review the Programme has successfully addressed and closed all recommendations including undertaking PMO maturity assessment, mapping and augmenting processes from project initiation to completion stages and provided greater clarity around roles and responsibilities, empowering experts at the right time. Since the current Hubs Programme funding envelope was approved as part of SR21, there has been considerable change, which means that it is now necessary to amend programme plans. The programme is committed to providing an updated Business Case to CO Ministers and HMT which looks to amend scope to reflect construction inflation, cost of borrowing, IFRS16 regulations, smaller Civil Service, utilisation of hybrid working and availability of grade A office space on the market. | 2015-05-01 | 2030-03-31 | The project's end-date at 22/23-Q4 is 2030-03-31. This is primarily due to the following factors. The GPA Government Hubs an Whitehall Campus Programme will support the Governments Strategic requirements to relocate 16,400 Civil Servants out of London and into regional Hubs, and consolidate 37,000 FTE in the Regions by 2030 to promote economic growth |  |  |  | There are projects that are not progressing as initially expected due to a review of strategy between leasehold and freehold. The outcome of that review is still awaited but other non-impacted work is continuing. This has had a significant impact on what could be achieved in year. | 558 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 558m. This is primarily due to the following factors. There are projects that are not progressing as initially expected due to a review of strategy between leasehold and freehold. The outcome of that review is still awaited but other non-impacted work is continuing. A revised Programme has been proposed and is awaiting approval. | 2630 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2630m. The current benefts are calcuated based on cost savings the programme produces over it's lifecycle. Capital Projects are working with GPA Finance to develop a new benefits calculator, and with a cross-GPA Working Group we are exploring how best to measure and report on Social Value. The Social Value Portal company have been contracted to support definition of new social value KPIs | CO_0133_2223-Q1
National Underground Asset Register | CO | Government Transformation and Service Delivery | NUAR will standardise, centralise and make available privately and publicly owned data from hundreds of organisations about the location of underground utilities assets. A phased delivery programme includes a minimal viable product (MVP) for North East England, Wales and London, which launched in Spring 2023 (on schedule). The MVP is a major milestone - delivering core functionality and containing data from 80+ public and private sector organisations, including all major energy and water providers. The platform will be iteratively enhanced and rolled out to the remaining areas of England and to Northern Ireland. Good progress is being made onboarding asset owners outside the MVP regions. Once fully operational across England, Wales and Northern Ireland, NUAR will help improve efficiencies in construction and development, reduce disruption to the public and businesses, improve workers safety and is envisaged to deliver at least 350 million economic growth per year |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The SRO's Delivery Confidence Assessment rating at 22/23-Q4 is Amber, in line with the Gateway 4 Assurance Review conducted by COPO and the IPA in January 2022, due to the challenges of onboarding Asset Owners and the uncertainty around securing necessary legislation. The minimum viable product was delivered on schedule, which included core functionality and data for Wales, North East England and London. We changed the contract to prioritise the highest value Asset Owners (on track), to act as a catalyst for onboarding others, and have engaged with Northern Ireland. We were not allocated a slot for the 4th parliamentary sessions following a bid submission, however we are exploring opportunities for packaging with another bill. | 2021-09-01 | 2024-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. The core functionality of the NUAR service to meet the safe dig use case has now been delivered. Incremental enhancements driven by user feedback will be delivered in the remainder of the programme.82 data sets have been published for the first 3 regions, including all major gas, electricity and water companies. This is envisaged to act as catalyst for all other Asset Owners to be onboarded. We have also fully onboarded 29 out of the remaining 54 high value Asset Owners outside the MVP regions.To date, data has been received from 172 organisations, with 146 DISs agreed and 155 DDAs signed across all regions.We are exploring legislation routes that will underpin the NUAR service offer, mainly through packaging of the NUAR legislation with another bill. The legislation is vital for the programme to deliver its benefits. | 10.95 | 10.1 | -8 | The baseline costs for this year's budget have been amended following the Central Finance Team's supplementals exercise in Cabinet Office. As part of the exercise, the programme exchanged some budgets with the next financial year. The RDEL underspend is due to the Welsh Government grant not being used, less legal support services than originally forecasted and the lack of need to release the management reserve. The overspend in CDEL is due to a late capitalisation of expenditure from last year and higher performance of the suppliers than originally forecasted. | 33 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 35m. to 33m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 35m. to 33m. This is primarily due to the following factors. The programme has delivered an underspend in this and last financial year, due to lack of requirement of the management reserve, the Welsh Government grant not being used, the legal services requirements being less than forecasted, reduced core resourcing resourcing due to personnel leaving and a couple of late payment milestones delivery by the supplier in the last financial year.The baseline allocation of the programme has reduced as a result of Central Finance pressures and reallocation of budget within the unit. | 3474 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3474m. An external firm has been appointed to produce an evaluation and monitoring report, as per the FBC commitment to HMT, which will define the benefits measurement methodology and apply it to establish the baseline against which the benefits will be calculated. The outcome of this work is expected to be available in April 2023. | CO_0014_2122-Q2
Rosa Renewal Project | CO | ICT | The Rosa Renewal Project will ensure HMG continues to have available a pan-departmental secure IT shared service specifically designed for working at SECRET. Project outcomes will deliver much improved service resilience, a modest increase in capacity, new capabilities to meet emerging needs, improvements to usability and effective management of obsolescence . In so doing, it will ensure continued VfM from the original case that underpinned the delivery of Rosa and lay the foundations for future service growth at the point it is needed and affordable. This is the first quarterly report for this project. |  | Green | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Green. This is primarily due to the following factors. The project is currently delivering to time, cost and quality. Risks are well understood and managed. The principal risk concerns ongoing affordability, which is being addressed in two ways: for those making significant contributions, senior engagements continue (and have borne fruit to date); for minor contributors, costs will be added to their annual run cost contributions from Apr 23. With circa 2% of project costs at risk in this way there is no sense of significant risk to overall project delivery. | 2022-04-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. Delivery is on schedule and there are no current indicators that this is likely to change. |  |  |  | The GMPP project did not provide data | 51 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 51m. This is primarily due to the following factors. Project WLC covers the essential investment in the current service, explicitly excluding potential project outcomes that are not currently affordable. Funding is provided by those departments that use the service and is in addition to annual running costs for the service. Those departments are satisfied that the project as funded meets their principal priorities and represents VfM. | 205 | The project's departmental-agree monetised benefits at 22/23-Q4 is 205m. In addition to monetised benefits, this project will enable significant non-monetised benefits that will flow from the levels of cyber security provided to key areas of HMG business. | CO_0210_2223-Q4
Transforming Public Procurement | CO | Government Transformation and Service Delivery | The Cabinet Office has started mobilisation of this programme in 2021/22 which will deliver: Introduction and delivery of a Procurement Reform Bill, delivery of the implementing secondary legislation and a new oversight unit to monitor compliance. A comprehensive training package to embed the new procurement procedures and national priorities for public procurement. New digital systems for commercial data that will bring commercial insight together across the 300bn pa public procurement spend. The Benefits from the programme are: Simpler, faster procurement procedures A more streamline process backed up by relevant training for users Greater transparency surrounding procurement procedures |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. As a result of delays, the programme suffered setbacks in the delivery of key components of the programme along the critical path. This has necessitated the need for a programme re-baseline, which as of May 2023, has been approved and will see the new procurement regime go live in October 2024. . We are confident as a programme team that we can deliver to our policy intent, programme vision and programme benefits to a good standard within this newly allocated time frame. | 2021-01-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. Due to programme wide replanning and authorisation on the re-baseline, the programme end date is now Q1 2026 (where previously it was Q4 2025). Significant work has been undertaken to ensure this milestone is achievable. Regular reporting, including directly to the minister via an overarching level 1 schedule, along with automated planning ensures that any delays can be acted upon accordingly to minimise impact/slippage. | 2.14 | 1.65 | -23 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 35m. At present the programme's baseline wlc remains the same as when we entered the GMPP in the first quarter of 2022/23. As mentioned previously, due to the re-baseline it is likely this may change our wlc figure. We are currently undertaking a review of the cost impact and will reporton this in the next reporting round. | 35 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 35m. This is primarily due to the following factors. The project's departmental-agree Whole Life Cost at 22/23-Q4 is 35m. At present the programme's baseline wlc remains the same as when we entered the GMPP in the first quarter of 2022/23. As mentioned previously, due to the re-baseline it is likely this may increase wlc. We are currently undertaking a review of the cost impact. | 205 | The project's departmental-agree monetised benefits at 22/23-Q4 is 205m. Our benefits figure is 205 million over 10 years as drawn from the published Impact Assessment (see summary on page 4) https://bills.parliament.uk/publications/46429/documents/1767 | CO_0120_2223-Q1
Vetting Transformation Programme | CO | Government Transformation and Service Delivery | The Vetting Transformation Programme is building a workforce with the right skills, fully exploiting technology and implementing a new Vetting standard. The programme has the following aims: faster clearances, processing times will be reduced by implementing a new single joined-up process eliminating duplication, enabling individuals to be recruited into roles quicker. Provide a far better user experience, facilitated by frictionless HR, security data sharing and record management. Clearances will be portable and individuals will move seamlessly between departments. Ongoing assurance of our people through a cross functional approach to managing employee risk throughout the employee lifecycle, to better ensure the integrity of individuals with privileged access. Aligning to these outcomes will provide Government departments with a trusted Vetting service adhering to its customers needs and strengthening our international reputation. | Red |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Red (IPA rating). This is primarily due to the following factors. It was agreed across departments that the cost for Vetting Transformation will continue to be met by Burden Share. The programme secured a further 5.1m funding for 21/22 and has so far delivered to plan. The programme successfully implemented the Airside Accreditation Check by its due date of the 1st January 2022. Further highlights include the achievement that the proportion of decisions made by UKSV has now increased to c.62% | 2019-03-01 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. The Programmes Delivery Confidence Assessment (DCA) is Red, the baseline that VTP is being measured against relates to the Future Vetting System (FVS) project that effectively closed down in 2021. The Programme team is working on restating those plans (scope/time/cost) following a digital discovery which is currently underway. Once complete, the Programme will present an Outline Business Case to the Cabinet Office Approval Board in September 2023 and HMT in October 2023 for spend approval for Levels 2&3. If approved, then the programme will be re-baselined. This will ensure going forward the programme is assessed against the correct metrics. The funding from customers for 23/24 has been approved, but the Programme remains dependent on the spend approval. | 5.8 | 11.06 | 91 | The budget variance exceeds 5%. The programme has exceeded the anticipated budget as it has been unable to meet the initial timescales for delivery. | 14 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 8m. to 14m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 8m. to 14m. This is primarily due to the following factors. The whole life cost of the Vetting Transformation Programme has not been rebaselined since it was established in the programmes approved SOC. The programme has spent to forecast in FY21/22 |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. We do not anticipate any monetised Benefits until April 2024. We anticipate the following benefits - an increased robustness of vetting, productivity improvements and economic benefits from reducing street to seat times and reducing attrition. Increasing the technological capabilities will reduce the time spent by vetting officers accessing disparate data sources. In creating additional capacity through increased efficiency, we will create a continuous improvement fund which will be used to build a deeper quality of capability across vetting. | CO_0028_2021-Q4
Workplace Services Transformation Programme | CO | Government Transformation and Service Delivery | The Workplace Services Transformation Programme seeks to build and run workplace services that can grow to meet demand and flex in response to goverments needs and the growth of the GPA property portfolio. The programme will promote productivity and optimise our use of space - delivering savings. A new workplace services model will achieve customer service excellence delivered through transformed workplace services, optimised for resilience and supported by enhanced commercial and customer service capability and performance. | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (IPA rating). This is primarily due to the following factors. The IPA Gate 0 Review provided the SRO with three recommendations. Significant progress has been delivered on all three of these recommendations. Recommendation 1, To ensure that the Procurement Projects progress smoothly and on time, this has continued to be the key focus of the Project Delivery Teams. However, since the Review, the bolstering of the central Programme Team to include a Delivery Manager and Project Manager has delivered and continues to deliver targeted support across the Programme.Recommendation 2, Continue to work closely with Cabinet Office Officials to ensure smooth approval processes. Since the Review, engagement has been increased through a schedule of monthly meetings with Cabinet Office and HMT approvals teams. Moreover, regular operational level meetings have been established, joint milestone planning is undertaken and there is an agile approach to working through the review periods.Recommendation 3, Utilising GPA Communications Resources to support the development and delivery of messages. | 2020-07-01 | 2024-07-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-07-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-07-01. This is primarily due to the following factors. The Programme remains on schedule, with End Date as per published Baseline End Date. | 89.13 | 80.17 | -10 | The budget variance exceeds 5%. The forecasted Whole Life Costs have reduced to 965m, compared to a 1,059m baseline. Last year's submission was based on the OBC, informed by Should Cost Modelling, and during the last 12 months the bids for the 4 main procurements covering the Performance Partner, Operational Security, Hard and Soft FM have been received and our forecast has been updated accordingly. This has generated an overall saving against the OBC as a result of a competitive market tender process. | 1059 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 1059m. This is primarily due to the following factors. The Whole Life Costs reflect the annual contract values in the preferred bids for the 4 procurements which are either complete or in progress, covering the Performance Partner, Operational Security and Hard and Soft FM. These costs also reflect the anticipated growth in the GPA through the regional hubs programme. The 965m Whole Life Costs represent the 5 year core term of the supply chain contracts, with the remaining 2 optional years and the final year of the programme forecasted at the same run rate, adjusted for inflation and growth as appropriate. | -30.69 | The project's departmental-agree monetised benefits at 22/23-Q4 is -30.69m. Overall the WSTP preferred option was expected to increase costs by 30.7m. However, this results from the investment in GPA staffing which is common to all of the considered options to adequately manage the growing estate and supply chain; and the introduction of the Performance Partner as the critical factor in driving enhanced customer and client benefit. The FM supply chain itself is expected to deliver 22m savings against the existing TFM model. The Baseline used is the OBC preferred option. The latest forecast is a benefit of 65.24m. The current award status is that two of the procurements have completed (PP and Operational Security) at an increased cost to the OBC, but the two FM procurements due to be awarded in Q1, deliver a greater value saving compared to OBC. | CO_0029_2021-Q4
Automotive Transformation Fund | DBT | Infrastructure and Construction | The Automotive Transformation Fund (ATF) is designed to support the creation of an internationally competitive zero emission vehicle supply chain in the UK. The ATF supports late stage R&D and capital investment across strategically important parts of the electric vehicle supply chain: batteries, motors and drives, power electronics, hydrogen fuel cells and storage tanks. Specific objectives relate to the creation and safeguarding of jobs, securing private investment, supporting the UK's role in tackling climate change by reducing global emissions from the sector, and helping to build secure and resilient supply chains and supporting EV manufacturers to meet rules of origin requirements. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Having surrendered some programme budget in the past year, the Automotive Transformation Fund (ATF) team will assess the impact on benefit realisation and continue to closely monitor the benefits delivered by means of annual project reviews. The team continue to assess cases in the ATF pipeline and to hold discussions with original equipment manufacturers (OEMs) regarding potential electric vehicle investments in the UK (which are complementary to the supply chain investments the ATF is designed to support) . The team will continue their engagement with industry and discussions across government to establish a long-term commitment to secure zero-emission vehicle manufacturing in the UK and improve the speed at which government provides support. | 2020-07-31 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. Although the Automotive Transformation Fund is currently only funded to March 2025, the programme team have begun engagement with industry and discussions across government to consider how the government can build on existing interventions to take decisive action to ensure future investment in zero emission vehicle manufacturing. | 191.31 | 7.42 | -96 | The budget variance exceeds 5%. The ATF has surrendered some programme budget in the past year and other forecasted project spend has slipped right, for a number of reasons, into future years. The ATF team will assess the impact on benefit realisation and continue to closely monitor the benefits delivered by means of annual project reviews. The team will continue their engagement with industry and discussions across government to establish a long-term commitment to secure zero-emission vehicle manufacturing in the UK and improve the speed at which government provides support. | 747 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 747m. This is primarily due to the following factors. This was the capital funding awarded to the Automotive Transformation Fund at previous Spending Reviews. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. We updated and submitted our business case along with our bid in the last Spending Review. A complementary business case for submitted but did not get approved. As the two business cases were complementary, our analysts modelled their combined impact on the automotive industry and apportioned the benefits proportionately but as only the ATF secured additional funding analysts are now in the process of reviewing/updating the ATF business case in accordance with the Spending Review outcome and to reflect a reduction in programme budget in the years since. The impact on benefit realisation will be reviewed and the benefits profile in the business case adjusted accordingly. | BEIS_0090_2122-Q4
Export Support Service Programme | DBT | Government Transformation and Service Delivery | Exports are crucial to the UK economy, to growth and improving productivity, and make up 30.5% of total GDP, supporting 6.8m jobs. That is why, in 2021, we published our Export Strategy Made in the UK, Sold to the World: Race to a Trillion, outlining ambitions to achieve 1T pa exports by 2030. The Export Support Service Programme (ESSP) was established to optimise the Department for Business and Trades (DBTs) SME export services. Our aim is to improve services against the strategy, bringing these together into a single coherentecosystem that costs less, works more efficiently, and provides an improved and integrated customer experience. ESSP is complex, requiring assessment, re-design, and refinement of existing services, which are at different lifecycle stages. We have made significant headway to deliver: in-housed the International Trade Advisor (ITA) Service,; established nine overseas hubs; launched the Export Support Service enquiry unit and developed the UK Export Academy covering the UK and maximising reach through a one-to-many model. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Export Support Service Programme(ESSP) was only added to the GMPP during this financial year. Whilst much has already been delivered, we are clear that there is more still to do to fully realise our objectives and deliver the benefits. To date we have completed process mapping of the entire system and developed a target operating model that envisages greater discipline in deploying resources to ensure maximum impact for our customers and the best return on investment. Our plan of further work includes streamlining and improving our export digital services on the website GREAT.GOV to ensure it meets business needs to grow export knowledge and assist UK exporters to develop market insight. We are also planning to develop a digital point of entry that will be fully integrated into the export support service ecosystem structures, and embedding the better use of data to ensure our services are targeted effectively. | 2021-11-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The creation of the Export Support Serviceecosystem necessitates changes to people, processes, and technology. New processes need to be designed and new technology developed, alongside supporting our staff to adopt new ways of working so that the changes are successfully embedded. We are taking a phased approach to delivery that allows sufficient time to design new structures, consolidate processes, and align these across the programme and the Department. We review the timeline on an ongoing basis and use internal oversight to ensure progress. | 47.61 | 44.07 | -7 | The budget variance (savings) is as a result of the programme exceeding expectations and delivering efficiencies across the department 1) the move to digital by default, 2) the renegotiation and reduction in spend of an under-performing overseas contract 3) a reduction in headcount within the EITA project | 124 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 124m. This is primarily due to the following factors. This planning will be set out in the business case to be submitted during FY23/24. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. The work required to identify and monitor the benefits of the programme is underway, including data collection that will underpin our metrics. The next steps are to refine how we measure our current system (baseline) and what we need to do for future evaluation. Our evaluation will be informed by the departments published Analytical Framework which underpins the 2021 Export Strategy (Made in the UK, Sold to the World). As outlined in the Analytical Framework, we intend to use a number of different approaches including the maintenance and development of a range of internal performance metrics, the Export Client Survey, our value for money model, which considers the cost efficiency of our offer and the overall potential return and monitoring business satisfaction. Our approach also includes bespoke research where necessary. This work will be reflected within the appropriate internal government processes to ensure that the programme delivers value for money. | DIT_0098_2122-Q4
Investment Transformation Programme | DBT | Government Transformation and Service Delivery | The Investment Transformation Programmes objective is to make DBT the worlds most capable and respected Investment Promotion Agency (IPA), best placed to deliver high-value inward investment in support of HMGs economic ambitions including science and technology, net zero and Levelling Up. We will transform our: service offer for investors, standard ways of working for DBT Staff and delivery of Strategic priorities for HMG and the Department. The Investment Transformation Programmes scope was confirmed following two years of specialist research, which tested the target operating model in place at the time against an idealised model that reflected views across the investment landscape, and subsequently led to a Spending Review bid. The new target operating model seeks to better join up HMGs offer to investors in a more coordinated way, targeted more strategically, and set against Government priorities. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. During Q4, the Programme underwent a Scope Review to ensure it is set up with the right components and is on track to deliver against the vision and strategic objectives outlined in the Programme Business Case. The SRO recommended baselining all existing workstreams via a mass PID/Star Chambers exercise. New PIDs have been drafted and Star Chambers are underway. Subsequently, two new workstreams have been established and proposals will be tested with User Groups who are also reviewing the Customer Journey Maps. We have made good progress in developing the Programme Blueprint Service Design and a re-baselined Programme Plan is due to be finalised by May 2023. The Programme appeared at DBTs February Performance, Risk and Finance Committee and members agreed the programme was in robust shape. The ITP Business Planning return was submitted in January and provided a fully-costed business plan for the Programmes internal cost centres. | 2021-09-20 | 2024-05-31 | The project's end-date at 22/23-Q4 is 2024-05-31. This is primarily due to the following factors. The ITP Programme Business Case is approved and on track to meet objectives as per the milestones laid out in the business case and the Programme is scheduled to close May 2024. FISS has received HMT approval as at April 2023, an assurance review is due to take place in May 2023 and the Programme plans to come back to HMT in November 2023. | 4.3 | 4.1 | -5 | The GMPP project did not provide data | 73 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 73m. This is primarily due to the following factors. During financial year 2022/23, both the ITP business case and the FISS outline business case were approved by HMT so this is the first time that we are reporting numbers to GMPP. The total costs included in these business cases make up the baseline whole life costs. The FISS full business case has now been approved by HMT. Whole life costs have changed as there were changes in the target operating model between OBC and FBC which caused the cost model to forecast higher total cost. | 781 | The project's departmental-agree monetised benefits at 22/23-Q4 is 781m. The project's departmental-agree monetised benefits at 22/23-Q4 is 781m.The project's departmental-agree monetised benefits at 22/23-Q4 is 781m.The project's departmental-agree monetised benefits at 22/23-Q4 is 781m. We now have a first version of the benefits realisation plan which will be revised as work on benefits progresses. At this stage, we have the foundations of benefits management: we have identified the benefits, we have elements of how we will monitor and evaluate them, and have a credible theory of change. The next stages are to build benefit profiles, understand how inputs significantly contribute to the delivery of those benefits, and agree the longer term monitoring of benefits with the BAU structures. Work continues on presenting benefits calculations in line with the requirements of this return. Please note that the PBC outlined 1.062bn of discounted benefits for full transformation but this has been revised down to 918m following the OBR March 2023 Economic Outlook. Work continues to be progressed on the quantification of the benefits and this will be completed by Frontier Economics. ITP will continue to update the Benefit Management Plan with support from PGA and remain transparent with the benefits management progress at the monthly PCC. | DIT_0097_2122-Q4
4th National Lottery Licence Competition | DCMS | Government Transformation and Service Delivery | The 4th National Lottery Competition Programme is responsible for ensuring the continuation of the National Lottery on the current expiry of the current 3rd Licence at the end of January 2024. This involves designing a new licence fit for the future and selecting an operator via a competitive application process who is able to continue to develop the National Lottery as a public asset in order to maximise the returns to good causes whilst also ensuring the highest standards of propriety and player protection. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The latest Infrastructure and Projects Authority (IPA) Gate 3 review and final report rated the Programme as Amber on its conclusion. All recommendations have been addressed by the Programme. The Programme is currently in conversation with the IPA to plan the Gate 4 review, most likely to be in September 2023. Since last year, the Commission successfully applied to lift the suspension on the Programme and the licence was awarded to Allwyn UK Limited, and transition to the 4th Licence started. However, there continues to be a challenge to the outcome of the competition which the Commission is defending. The Programme's DCA rating remains Amber. | 2018-11-16 | 2024-02-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-02-01. This is primarily due to the following factors. The programme end date of 1st February 2024 reflects the start of the 4th Licence. | 45.31 | 19.64 | -57 | The budget variance exceeds 5%. Due to delays in implementation caused by the legal cases, we are saving money on implementation in 22/23. Litigation costs have been added to the budget and forecast in 22/23 with the underspends in 22/23 added to the forecast in 23/24. Whole life project costs are now 177.47m; this has increased due to the additional litigation budget of 22.6m required for our court cases which was a contingent liability in our business case. The profiling of this is between 22/23 and 23/24. A delay in the court cases to January 2024 has caused variances between budgets and forecasts, however we have approval to carry over unused litigation budget to 23/24, preventing an overspend. | 177 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 155m. to 177m. This is primarily due to the following factors. The budget has increased due to Litigation costs, a budget of 22.6m has been provided. | 22284 | The project's departmental-agree monetised benefits at 22/23-Q4 is 22284m. The project's departmental-agree monetised benefits at 22/23-Q4 is 22284m.The project's departmental-agree monetised benefits at 22/23-Q4 is 22284m.The project's departmental-agree monetised benefits at 22/23-Q4 is 22284m. As set out in the Final Business Case, the programmes benefits realisation approach comprises of 3 broad activities: programme-level evaluation, monitoring and evaluation of individual workstreams during implementation and monitoring and evaluation of the Commissions approach to regulating during the 4th Licence. During the implementation phase, the benefits reporting will focus on development of individual workstreams (as set out in the business case). The overall benefits of the programme (Increased returns to good causes) will be delivered by Allwyn and dependent on the implementation phase delivering. To note, it is the responsibility of the Incoming Licensee to develop its own methodology and forecasting for benefits during the 4th licence period - this will be provided to the Gambling Commission c.6 months prior to the start of the 4th licence and tracked throughout the licence. | DCMS_0013_1819-Q3
Blythe House Programme | DCMS | Infrastructure and Construction | The two main objectives of the Blythe House Programme are to ensure that: 1) Blythe House is put to its most efficient and effective use in order to deliver maximum value for money 2) The Blythe House museums are able to care for their collections in the most efficient and effective way |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. This is primarily due to the impact of COVID-19 and the delay in the V&A's Practical Completion of the V&A East Storehouse. The V&A's facility is expected to be completed by the end of May 2023 and the decant schedule has been reprofiled to meet agreed deadlines. Both facilities for the British Museum and the Science Museum Group have been completed and the decant of all three museums' collections is well underway. DCMS remains confident that the programmes aims of protecting the museum collections and maximising the sale value of Blythe House will still be met. | 2015-04-01 | 2024-06-28 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-03-31 to 2024-06-28. This is primarily due to the following factors. The change in end date to 28/6/24 is due to the delay in the V&A vacating Blythe House. | 30.66 | 37.73 | 23 | The budget variance exceeds 5%. The in-year variance reflects the management of grant in aid drawdown from year to year. The in-year forecast spend represents anticipated expenditure on the Blythe House project, while the baseline represents what is being drawn down in grant in aid funding. There is an arrangement whereby the museums can draw down the grant in aid funding for non-Blythe House project expenditure, and 'repay' it to the project in future years. | 240 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 217m. to 240m. This is primarily due to the following factors. Additional funding was secured at the 2020 and 2021 Spending Reviews due to the significant impacts on the programme caused by the Covid pandemic. The grant-based sponsorship model used for delivery of the programme retained with no central contingency, consequently. This uplift reflects the wider approach to supporting museums during the pandemic | 915 | The project's departmental-agree monetised benefits at 22/23-Q4 is 915m. The project's departmental-agree monetised benefits at 22/23-Q4 is 915m.The project's departmental-agree monetised benefits at 22/23-Q4 is 915m.The project's departmental-agree monetised benefits at 22/23-Q4 is 915m. The benefits are indicative estimates from the museums' benefits profiles and are calculated until 2066/67 | DCMS_0008_1516-Q4
Natural History Museum Unlocked | DCMS | Infrastructure and Construction | NHM Unlocked is an ambitious programme to secure the future of our irreplaceable collection, accelerate scientific research and innovation, and enhance our public offer. Underpinned by a 201 million government investment, we are looking to: build a sustainable new centre at Thames Valley Science Park, equipped with purpose-built collections storage, laboratories and 160 Museum scientists; relocate 38 million natural history specimens, of which 28 million will be housed in the new centre; and capture digital specimen data for use by partners around the world. The programme will not only enhance the UKs leading role in tackling urgent global challenges, but also unlock the redevelopment of our historic South Kensington site transforming our public offer and mission to create advocates for the planet. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Rating decreased to red during this year due to delay in agreeing the site lease and having to swiftly enact a mitigation plan which led to deviation from the schedule previously presented in the Strategic Outline Case. Subsequent further changes to the timeline were as a result of a need for an additional assurance review to follow completion of Royal Institute of British Architects stage 2 and precede Outline Business Case resubmission, plus need to revisit RIBA 2 post OBC approval to incorporate area savings on labs and collections areas to meet revised budget and avoid delaying TAP further. Following successful approval of our preferred OBC option the programme considers that there are no major outstanding issues currently threatening successful delivery. | 2019-05-15 | 2031-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2026-12-30 to 2031-09-30. This is primarily due to the following factors. Delay in agreeing the site lease and having to swiftly enact a mitigation plan led to deviation from the schedule previously presented in the SOC+. Subsequent further changes to the timeline were as a result of a need for an additional assurance review to follow completion of RIBA 2 and precede OBC resubmission, plus need to revisit RIBA 2 post TAP to incorporate area savings on labs and collections areas to meet revised budget and avoid delaying TAP further. The programme also now includes a longer time period for the physical move of collections to the new site as more detailed planning than had taken place at SOC stage identified that additional time would be required to complete one of the largest ever moves of natural history collections. | 6.35 | 6.38 | 0 | The GMPP project did not provide data | 229 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 182m. to 229m. This is primarily due to the following factors. Forecast/actual costs have been rephased to reflect more realistic timelines matching the approved Outline Business Case timeline. Figures reflect recent approved budget allocation following OBC. Actuals and Forecast have all been reclassified as Capital as per ESA 10 directive for R&D. Previously they were split between Resource and Capital, also they now reflect the approved option 4 HMT allocation. | 1985 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1985m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1985m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1985m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1985m. Monetised benefits presented are from the SOC, updated annualised figures will be presented in the next return. The bulk of the benefits associated with creating a new NHM centre will be felt by UK society, rather than the NHM. Not all the potential benefits are quantifiable. Where benefits have been quantified, the approach to quantification has been deliberately conservative. Benefits primarily arise from improvements to growth potential from creating new scientific infrastructure through an enhanced innovation ecosystem and undertaking scientific research and development. The benefit to cost ratio of the approved delivery option is over 7:1. | DCMS_0018_2021-Q3
Youth Investment Fund | DCMS | Infrastructure and Construction | The Youth Investment Funds (YIF) objective is to create, expand and improve local youth facilities and their services, in order to drive positive outcomes for young people, including improved mental and physical wellbeing, and skills for life and work. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The programme has developed a pipeline for assessing bids and allocating funding. This will inform in year controls and help track the construction and budgets. | 2022-04-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The programme is on track to deliver objectives by March 2025 | 22.03 | 18.87 | -14 | The Youth Investment Fund saw substantial demand for capital funding, however, a significant number of applications were at too early a stage of development to be considered for the programme.The created an underspend for this financial year, and in order to balance the funds spending profile with the emerging pipeline of capital works, that has been reprofiled into 24/25. At Supplementary Estimates 2022-23 DCMSs supply estimate that was approved contained a Budget Exchange and a surrenderoffundingfor the YouthInvestmentFund, in order to ensure the spending profile reflected the latest delivery assessment at the time. | 341 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 341m. This is primarily due to the following factors. The 368m will provide youth facilities and services, including smallcommunity youth spaces, youth centres and activity centres in the most underprivilegedareas across the country.This investment will: Build/preserve youth facilities that are fit for purpose in areas of need Develop environmentally sustainable youth facilities Drive improvements in youth sector capability Improve access, participation and short-term wellbeing of young people Improve the evidence base for the youth sector | 5318 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5318m. The project's departmental-agree monetised benefits at 22/23-Q4 is 5318m.The project's departmental-agree monetised benefits at 22/23-Q4 is 5318m.The project's departmental-agree monetised benefits at 22/23-Q4 is 5318m. There are a number of monetised and non-monetised benefits. Monetised include: Attending youth services is associated with higher wellbeing for beneficiaries in the short-runActivities lead to intermediary outcomes (e.g. leadership, communication, aspiration) and therefore future life outcomes (e.g. education, employability, health)Intermediary outcomes also lead to impacts on wider society (e.g. reduced crime, lower public spending, higher tax revenue).Developing land or renovating existing physical infrastructure will lead to a higher land value. Non-monetised include - Increasing community infrastructure has links with increases in social capital and subsequent economic outcomes for communities. Renovating buildings lowers ongoing costs, and prevents further expenditure on repairs in the long run. Additional income will be generated in order to continue running the services. | DCMS_0118_2223-Q1
Bridgwater Barrier | DEFRA | Infrastructure and Construction | The Environment Agency are working in partnership with Sedgemoor District Council to deliver this project located on the Parrett Estuary at Bridgwater, Somerset. The project will provide protection from tidal flooding to the town of Bridgwater and villages downstream. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. March 2022 the Secretary of State signed the Bridgwater Tidal Barrier Transport & Works Act Order (TWAO). The TWAO sets out the statutory powers to deliver the construction of the Bridgwater Tidal Barrier Scheme. Detailed design is on programme and cost estimates and the full business case will be be submitted for assurance in the next quarter. The construction industry is subject to very high inflation due to fuel prices and under-supply in key areas such as availability of heavy plant. We are updating the project estimate to take account of inflation that has occurred and the predicted level anticipated in future years. The Environment Agency is reviewing the impact that inflation is having on partnership funding arrangements. | 2014-03-01 | 2030-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. March 2022 the Secretary of State signed the Bridgwater Tidal Barrier Transport & Works Act Order (TWAO). The TWAO sets out the statutory powers to deliver the construction of the Bridgwater Tidal Barrier Scheme. Detailed design is on programme and cost estimates and the full business case will be be submitted for assurance in the next quarter. The construction industry is subject to very high inflation due to fuel prices and under-supply in key areas such as availability of heavy plant. We are updating the project estimate to take account of inflation that has occurred and the predicted level anticipated in future years. The Environment Agency is reviewing the impact that inflation is having on partnership funding arrangements. | 2.48 | 2.48 | 0 | The GMPP project did not provide data | 225 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 225m. This is primarily due to the following factors. The Whole Life cash cost over the 100 year assessment period is 225m |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. Benefits calculated in accordance with FCRM Appraisal Guidance 1,522m. Outcome Measure 1 Economic Benefit. 11,300 homes and 1,500 businesses with reduced tidal flood risk. | DEFRA_0009_2021-Q3
Collection and Packaging Reforms | DEFRA | Government Transformation and Service Delivery | The three projects included within the Collection and Packaging reforms programme Extended Producer Responsibility for packaging (pEPR), Deposit Return Scheme for drinks containers (DRS) and Consistency in Recycling Collections (Consistency) - will deliver significant changes to the waste collection and recycling sector including bringing benefits such as the creation of green jobs and significant carbon savings, contributing to Net Zero and outcomes in Defra's 25 Year Environment Plan | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q3 is RED. DEFRA agrees with this rating. Delivery confidence is low due to the challenging timescales in which DEFRA needs to implement the reforms. Work to support this implementation is ongoing with a particular focus on strengthening our plans, programme control and benefits management. | 2018-04-02 | 2027-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-03-31. This is primarily due to the following factors. Collection & Packaging Reforms Programme has been delayed repeatedly. Two of three key Government responses to consultation now published: Extended Producer Responsibility - March 22; Deposit Return Scheme - January 23; Consistency - outstanding. Detailed delivery has been reprogrammed such that target end date is still feasible, but there is limited contingency available. | 29.16 | 30.77 | 6 | The budget variance exceeds 5%. This is primarily due to the following factors: 1) The baseline that was approved by Investment Committee in the SOBC was prior to business planning for 2022/23 and was subject to change. 2) Delay in progressing work during 2021/22. | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | 11611 | The project's departmental-agree monetised benefits at 22/23-Q4 is 11611m. The project's departmental-agree monetised benefits at 22/23-Q4 is 11611m.The project's departmental-agree monetised benefits at 22/23-Q4 is 11611m.The project's departmental-agree monetised benefits at 22/23-Q4 is 11611m. 1) this estimate is based only on the economic transfer of packaging recycling and waste management costs from Local Authorities to producers - making obligated producers responsible for the disposal cost of their packaging is a key outcome of the programme 2) qualitatively, we understand there are significant additional benefits and the modelled values of these are currently undergoing review; we will be in a position to update on these by 31/12/2023. | DEFRA_0040_2122-Q3
Defra Biosecurity, Borders and Trade Programme (BBTP) | DEFRA | Government Transformation and Service Delivery | The Defra Biosecurity, Borders and Trade Programme (BBTP) vision is to deliver world-class biosecurity capability which protects health, encourages prosperity and enables security for a global UK. The programme is delivering the key infrastructure, systems, services, operations, capabilities, and legislative changes required to enable the introduction of new controls for goods to and from the EU. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Final Rating is AMBER from March 2023 review. Several recommendations have emerged including focus on development of a critical path to identify key interdependencies, data quality and assurance and a detailed roadmap beyond 2025. The Programme Management Office will be working with project teams across the Programme to address and close these actions over the coming months. | 2021-01-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Ministers decided to delay the planned implementation of import controls for EU Sanitary and Phytosanitary Goods (SPS) goods in 2022 and commissioned further work on a new border operating model to better balance biosecurity and trade objectives. A new model has been developed and was approved by the Domestic & Economic Affairs Committee (DEA) In February 2023. Domestic & Economic Affairs Committee (DEA) also approved a new delivery schedule, with implementation in tranches commencing from October 2023. | 158.14 | 118.24 | -25 | The budget variance exceeds 5%. There is a significant variance on this programme which is due to the pausing of many programme activities whilst the Target Operating Model was worked through. There has also been a significant reduction in the site operator monthly charges as well as an assumption the operating costs will be recovered from FY 24/25 - the previous assumption was that this would not be possible however that assumption has changed, and is confirmed as being legally possible. Capital costs for further site development are also better understood and are lower, as have been some of the capital costs invested in physical infrastructure and Digital Delivery in Financial Year 22/23. | 902 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 910m. to 902m. This is primarily due to the following factors. The baseline remains unchanged as the programme has not yet been formally rebaselined due to ongoing work to further finalise the impacts of the Target Operating Model. The comparison between the current baseline and the current expectation of the whole life costs demonstrates that the programme has a better understanding of the costs and has refined them, that the programme is looking for efficiencies and savings wherever possible, and that the programme is obtaining better value for money from tax payer funding. The whole life costs will be formally baselined once the target operating model consultation is complete and the impacts have been properly analysed. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. The Biosecurity, Borders and Trade Programme (BBTP) End Benefits have been revised in accordance with updates to the Target Operating Model. These were approved by the internal Programme Board in March 2023 and work is ongoing to finalise Profiles and Realisation Plans. Analyst resource has been assigned to begin the costing and monetising of Benefits for future reporting. | DEFRA_0016_2122-Q1
Farming and Countryside Programme | DEFRA | Government Transformation and Service Delivery | By 2028, the Farming and Countryside Programme aims to deliver: 1) A renewed agricultural sector, producing healthy food for consumption at home and abroad, where farms can be profitable and economically sustainable without subsidy 2) Farming and the countryside contributing significantly to environmental goals including addressing climate change | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Programme remains deliverable with majority of critical outcomes on track and expected challenges being managed.Weve: * Launched the Lump Sum Exit Scheme * Tree Health Pilot went live * Successful launch of Sustainable Farming Incentive early rollout phase 1 followed by opening for applications and then allowing those in existing stewardship agreements to apply directly online* Soft launch of Farming Investment Fund Adding Value, online eligibility checker and applications.* Countryside Stewardship 2024 policy proposal and Countryside Stewardship 2022 facilitation fund approved by Minister and payments rates for Countryside Stewardship 2024 agreed in principle* First Vet Visit took place in September, private beta launched in OctoberIPA Review resulted in a very positive report (Amber rating), noting good progress in the last year and supporting the direction of travel towards embedding the one-team way of working in the Sustainable Farming Incentive delivery space to enable efficiency in decision-making and join-up with delivery partners | 2017-05-01 | 2028-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-12-31. This is primarily due to the following factors. The department continues to deliver the planned reforms and although some changes to plans have been made as part of our test and learn approach, delivery is on track for the critical path milestones, costs and benefits. | 2638.03 | 2535.45 | -4 | The budget variance is inferior or equal to 5%. | 24875 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 24864m. to 24875m. This is primarily due to the following factors. The costs are split into two main sections, payments to beneficiaries (scheme costs) and the costs of delivering those schemes together with policy and programme support (administrative costs).The value of the scheme costs will be linked to the definition of the manifesto commitment to guarantee the current annual budget to farmers in every year of this Parliament. | 58865 | The project's departmental-agree monetised benefits at 22/23-Q4 is 58865m. The project's departmental-agree monetised benefits at 22/23-Q4 is 58865m.The project's departmental-agree monetised benefits at 22/23-Q4 is 58865m.The project's departmental-agree monetised benefits at 22/23-Q4 is 58865m. The total project Baseline Monetised Benefits are 58.86bn. These benefits are from the approved Phase 2 Business Case from September 2021 these figures do not reflect changes in the programme since then, however, updated figures will be provided going forwards. The benefits presented here have been calculated bottom-up by scheme and totalled across the programme. This is a cautious estimate as not all schemes have monetised benefits and, for some schemes, benefits have been calculated from the year of spend but do not necessarily materialise in that year of spend. | DEFRA_0008_2021-Q1
Leeds Phase 2 Flood Scheme | DEFRA | Infrastructure and Construction | LFAS2 will reduce the risk of flood across Leeds using a catchment wide approach. The aim of the scheme is to deliver a 1 in 200 year level of protection (plus climate change allowance) through the use of linear flood defences, a large flood storage area and a programme of natural flood management measures. The scheme will help stimulate economic growth and regeneration with the city as well as helping to address the current climate emergency. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project remains rated as amber, this is on the basis that the project is progressing well overall, although unforeseen delays have been experienced when finding a temporary works solution for a listed structure and whilst mitigation measures have been implemented, the project completion date has changed by 15 weeks. The overall design and construction works are approximately 85% through the programme. | 2016-09-01 | 2024-10-18 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-10-18. This is primarily due to the following factors. Unforeseen delays have been experienced when finding a temporary works solution for a listed structure and whilst mitigation measures have been implemented, the project completion date has changed by 15 weeks. The overall design and construction works are approximately 85% through the programme. | 33.27 | 46.96 | 41 | The budget variance exceeds 5%. The forecast spend for this financial year has changed due to the impact of inflationary pressures on project materials, people and equipment. | 146 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 146m. This is primarily due to the following factors. Inflationary pressures and additional funding has been sourced to assist with challenges being experienced in supply chain material price increases. | 1428 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1428m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1428m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1428m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1428m. | DEFRA_0010_2021-Q3
Nature for Climate Fund | DEFRA | Infrastructure and Construction | The Nature for Climate Fund Programme has been established to significantly increase tree planting, woodland creation and management, and peatland restoration in England to support the delivery of Net Zero and 25-Year Environment Plan commitments. The programme is also designed to deliver wider social, economic and environmental benefits. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. We have implemented many of the recommendations made by the IPA in 2022, and continue to welcome their support and assurance to improve delivery confidence. We have continued programme activity at pace, having sought greater clarity over the future of woodland creation and recalibrated planned activity through the programme's annual review process. | 2020-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The NCF Programme is now well into its delivery phase, witha range of initiatives scheduled to deliver tree planting and peatland restoration. The programme's trajectories are showing an upward trend through the remaining years of the programme, but there are several key enablers required to match the planned delivery trajectory, which steepens over that period, and these are not certain. These key enablers include landowner demand for the schemes put forward through the NCF and the ability of the wider sector to respond to that demand. There has been a significant effort to implement these enablers and improve delivery confidence for years 4-5, and for woodland creation and peatland restoration beyond NCF. | 219.26 | 219.26 | 0 | The budget variance is inferior or equal to 5%. | 928 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 763m. to 928m. This is primarily due to the following factors. The increase in Whole Life Cost is due to an increase in the overall Programme budget and scope which was approved through an updated business case in 2022. | 54302 | The project's departmental-agree monetised benefits at 22/23-Q4 is 54302m. The project's departmental-agree monetised benefits at 22/23-Q4 is 54302m.The project's departmental-agree monetised benefits at 22/23-Q4 is 54302m.The project's departmental-agree monetised benefits at 22/23-Q4 is 54302m. The total monetized benefits figure is based on the cumulative benefits arising from tree planting and peatland restoration over the course of the NCF programme. Measured over a 50-year appraisal period, these benefits include: carbon sequestration, biodiversity, recreation, flood regulation, air quality and landscape. | DEFRA_0013_2021-Q4
NO2 Programme | DEFRA | Infrastructure and Construction | The NO2 reduction programme is a joint programme with the Department for Transport to deliver the 2017 UK Plan for Tackling Roadside Nitrogen Dioxide Concentrations. The Plan outlines how councils with NO2 levels exceeding legal limits must develop and implement local plans to deliver legal levels of NO2 in the shortest time possible. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Good progress has made against all previous IPA recommendations. The most recent IPA review of the programme was in March 2023 and actions against each recommendation from this review are being taken forward. Overall the NO2 Programme continues to deliver mitigations alongside Local Authorities and remains at Amber. | 2016-01-01 | 2027-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-12-31. This is primarily due to the following factors. The NO2 programme is legally mandated to deliver compliance with NO2 legal limits in the shortest time possible. The programme team works with local authorities across England who have exceedances to develop and implement local NO2 reduction plans through a variety of interventions. In 2022/23 four further Clean Air Zones were successfully launched in Bradford, Bristol, Tyneside and Sheffield to help reduce NO2 levels in the cities. In February 2022, Ministers granted permission for Greater Manchester to pause implementation of their Clean Air Zone and submit revised plans. The programme team continues to work with Greater Manchester to continue engagement and meet legal obligations. Comprehensive monitoring and evaluation arrangements are in place to assess whether local authorities are on track to reduce NO2 levels in the timeframe expected and consider appropriate remedial action if they are not. The programme team also continues to work closely with National Highways to address NO2 exceedances on the Strategic Road Network. | 189.3 | 43.4 | -77 | The budget variance exceeds 5%. The NO2 programme is supporting local authorities to develop and implement measures to address NO2 roadside exceedances. Funding has been provided to local authorities to deliver the necessary reductions to tackle NO2 over the lifetime of the programme. There have continued to be delays in agreeing local authority plans resulting in an underspend this year. The 22/23 baseline was updated in year, to reflect underspends as agreed with HMT and these figures were allowed for in SR21 budgets for the NO2 programme. | 883 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 885m. to 883m. This is primarily due to the following factors. 80 (m) to 883.00 (m). This is due to rounding rather than a decrease in costs. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. The primary benefit of the NO2 programme is reduced NO2 levels leading to a positive impact on public health. There is comprehensive monitoring and evaluation in place to track and manage the realisation of benefits from the programme. | DEFRA_0014_2021-Q4
Northern Ireland Programme | DEFRA | Government Transformation and Service Delivery | The Defra Northern Ireland Programme was formed in January 2021 and is led by the NI Directorate. It aims to ensure an enduring, operable NI/GB boundary for all Defra stakeholders, and the ongoing integrity and efficacy of Defras regulatory regimes in the context of the Windsor Framework, working collaboratively with the devolved administrations. The high-level strategic objectives of the programme are to: Ensure compliance with the Windsor Framework Mitigate the impacts of the WF implementation for businesses trading into and out of Northern Ireland Minimise the impact of WF implementation on consumers | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | DEFRA_0015_2122-Q1
Oxford Flood Alleviation Scheme | DEFRA | Infrastructure and Construction | We are working with 9 partners on a major new flood scheme for Oxford, which will reduce flood risk to homes, businesses and major transport routes into the city. Our scheme will provide a long term reduction to flood risk in Oxford, helping better protect the city as flood risk increases with climate change. The scheme will run through the existing floodplain west of Oxford. It will be formed of a new stream surrounded by a gently sloping floodplain of new wetland habitat and grazing meadow to create more space for water away from built-up areas. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project has submitted its additional information to support the planning application. After public consultation by the Local Planning Authority we expect a planning decision Summer 2023. Further to this the project team are progressing the Compulsory Purchase Order, we expect this to go to Public Inquiry in early 2024. Subject to the consents and authorisations being secured construction is expected to commence in 2025. We have undertaken a re-costing exercise in light of the macro-economic inflationary conditions. This has shown that the project is still progressing the economically preferred option and that it remains affordable. Given the inherent uncertainty with timescales and outcomes of consenting processes the project, whilst making good progress, remains at Amber. | 2014-04-02 | 2030-01-09 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-01-09. This is primarily due to the following factors. The project remains on schedule to complete as per the overall programme. Whilst the consents and authorisations are taking longer to secure than originally anticipated risk allowance within the programme and current construction sequencing enables completion to the stated dates. The Oxford Flood Alleviation Scheme delivery schedule remains dependent on Oxfordshire County Council's A423 bridge replacement progressing as we are delivering a joint asset in this part of the scheme area. | 1.81 | 1.84 | 2 | n/a - forecast for the year is inline with the baseline | 205 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 205m. This is primarily due to the following factors. The Whole Life Costs of the project remain within affordable range having taken into account wider inflationary pressures being experienced across the construction sector and economy as a whole. | 1537 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1537m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1537m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1537m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1537m. The benefits figure reflects the national flood damages avoided as per existing economic guidance. There are local quantifiable benefits and additional local economic growth factors not incorporated within this figure. | DEFRA_0011_2021-Q3
Pevensey and Eastbourne Coastal Management Scheme | DEFRA | Infrastructure and Construction | The aim of this project is to deliver a scheme to manage flood and erosion risk to a large number of properties, infrastructure, cultural heritage and environmental designated sites as well as deliver wider benefits. The area for this scheme is Pevensey Bay to Eastbourne on the southeast coast of England. This is a partnership project between the Environment Agency and Eastbourne Borough Council. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Pevensey Bay to Eastbourne Coastal Management scheme completed its modelling this financial year. This is a big milestone achieved for the project as it works through different scenarios and gives us an idea how many properties are at risk and provide the economic baseline for our appraisal. Looking ahead to the coming financial year the main milestones for this project are to go through the optioneering; from long-list to short-list to preferred option working with our partner Eastbourne Borough Council. | 2020-06-29 | 2030-03-29 | The project's end-date at 22/23-Q4 is 2030-03-29. This is primarily due to the following factors. The project remains on schedule to complete as per the stated programme. There will be an annual baselining exercise in the next financial year. | 1.13 | 0.97 | -14 | The budget variance exceeds 5%. There is a reduction in total in year spend this quarter against the baseline forecast because of the adaptation pathways approach meant there was less consultancy spend than previously forecasted. We also paused our Early Supplier Engaged Contractor due to the adaptation pathways which we did to seek efficiencies in our delivery approach. | 142 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 142m. This is primarily due to the following factors. The project Baseline Whole Life Cost has not changed. The whole life cost for the Pevensey Bay to Eastbourne Coastal Management Scheme considers all the work needed before, during and after scheme construction. This includes the cost of the work needed to design the scheme; gain the necessary licenses and consents and obtain business case approvals. It also considers the cost of materials and labour to construct the scheme, allowing for inflation and contingency for any risks which could occur and impact the delivery programme or cost. It further includes the estimated cost of works needed to maintain the scheme over a 100-year period and ensure benefit delivery. | 1661 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1661m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1661m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1661m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1661m. Scheme manages and reduces flood risk to homes, businesses and infrastructure such as the A259, hospitals, schools and water treatment works. The project also improves key protected habitats and increases biodiversity. Benefits are monetised as costs avoided once the reduced flood risk has been achieved. The whole life benefits of the scheme are calculated using established flood damage calculations (based on Multi-coloured manual) | DEFRA_0086_2122-Q4
River Thames Scheme | DEFRA | Infrastructure and Construction | The River Thames Scheme has 3 main goals: - Protecting our communities - we will create more resilient places and infrastructure for our communities by reducing the risk of flooding - Enhancing our Thames - we will increase the natural capital of the River Thames - Securing our economy - we will maximise social value of the scheme to promote green and sustainable growth How we'll achieve this: - People - we value people and champion an inclusive culture - Sustainability - create a greener future by tackling causes of climate change and becoming carbon neutral - Value for money - maximise opportunities to innovate to deliver valuable outcomes |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The collaboration agreement with Surrey County Council has been signed and the supply partners for the consents and authorisations phase of the project leading to the Full Business Case has been onboarded. Favourable weather conditions have also allowed us to bring forward ground investigation surveys into this financial year. Reviews of the consenting programme and construction programme have resulted in increased forecast durations of these activities which is reflected in later start on site and readiness for service dates. The project is continuing work on it's cost update to reflect the wider macro-economic inflation factors. This will lead to an increase in the overall forecast cost which could lead to economic and financial pressures that the team will be managing to ensure the scheme remains deliverable and affordable. | 2017-04-12 | 2030-04-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-04-01. This is primarily due to the following factors. The project forecast dates are expected to exceed the baseline dates as the Development Consent Order is expected to take longer than originally anticipated and the construction programme is likely to require an additional year to complete an operational scheme. | 16.68 | 17.89 | 7 | The budget variance exceeds 5%. In year spend has exceeded the original baseline figures. This is due to having favourable weather conditions that allowed for ground investigations scheduled for next financial year to be brought forward to this financial year and having higher resourcing costs than when originally baselined. | 501 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 501m. This is primarily due to the following factors. The current whole life cost figure remains as per the Outline Business Case forecast. A cost review process is ongoing to provide a re-baselined figure that takes into account wider macro-economic inflation factors. When completed scheme cost is expected to increase to reflect the wider increases across the construction sector.. | 2763 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2763m. The project's departmental-agree monetised benefits at 22/23-Q4 is 2763m.The project's departmental-agree monetised benefits at 22/23-Q4 is 2763m.The project's departmental-agree monetised benefits at 22/23-Q4 is 2763m. The benefits figure reflects the national flood damages avoided as per existing economic guidance. There are local quantifiable benefits and additional local economic growth factors not incorporated within this figure. | DEFRA_0012_2021-Q3
Science Capability in Animal Health Programme | DEFRA | Infrastructure and Construction | The SCAH Programme sets out the Department for Environment, Food and Rural Affairs' (Defra) plans for long-term investment in the Government's main animal health science facility. The re-development of the site infrastructure and associated transformation programme will secure and safeguard the critical animal health science capability, protecting the nation from the impacts of animal diseases in a cost effective way. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Good progress is being made towards clearing the site for construction and to inform the main investment decision point in Q3 2024 which will settle scope. This includes work on requirements and specialist technical services to support maturing the design for the scheme, which will underpin the business case. The programme remains amber due to current uncertainty of scope and funding, which will be addressed at the next Business case in 2024. | 2021-04-01 | 2036-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2036-09-30. This is primarily due to the following factors. The forecast completion date for the Programme remains September '36 pending further development of the Programme Master Schedule to reflect the changes approved following the first Tranche of activity (T1a). | 29.72 | 27.54 | -7 | Forecast spend for 22/23 is c. 2.2M (7%) below the budget allocated primarily as a result of the Programme not spending c.1.5M of optimism bias that was built into the allocated budget as SRO-owned contingency for the Programme. | 2820 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 2820m. This is primarily due to the following factors. The Whole Life Cost estimate has reduced as a result of a reforecast of costs following an assessment of the changes identified through Tranche 1a of the Programme. These revised costs also reflect the updated Master Schedule. | 208 | The project's departmental-agree monetised benefits at 22/23-Q4 is 208m. The project's departmental-agree monetised benefits at 22/23-Q4 is 208m.The project's departmental-agree monetised benefits at 22/23-Q4 is 208m.The project's departmental-agree monetised benefits at 22/23-Q4 is 208m. Work continues to identify and refine benefits for inclusion within Programme Business Case V2.0. | DEFRA_0007_2021-Q1
Terrestrial Natural Capital Ecosystem Assessment | DEFRA | Government Transformation and Service Delivery | The TNCEA programme establishes the first comprehensive understanding of the condition of natural capital assets across England drawn upon measurements data captured in the field. It puts in place sustainable capabilities to maintain and refresh the data baseline to keep it current in informing and supporting delivery of the 25YEP and related initiatives. The programme takes Defra's progress further towards becoming a data-driven, evidence-based organisation. The programme also incorporates development of systems modelling approaches in order to gain greater understanding of the complex relationships within the captured data, enabling it to be exploited for greater utility by customers for the data. The data generated will be used by a wide-range of stakeholder communities, including; core Defra and its Arms Length Bodies (ALBs), other Government departments, local government, national parks and authorities, utility providers and regulators, NGOs (local and national), private sector companies and academia. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Delivery confidence is currently Amber as we have set up almost all the governance infrastructure within the Programme and we have Programme Business Case approval from Investment Committee. Our Future Delivery Confidence is at Green/Amber as we are in the process of standing up all outstanding Governance Structures, completing the Benefits Plan and are currently filling critical FTE within the Programme. | 2021-04-01 | 2025-04-01 | The project's end-date at 22/23-Q4 is 2025-04-01. This is primarily due to the following factors. The Project end date is 31/3/25 and is based on the funding approved through the 2021 Spending Review, following a successful pilot funded through the 2020 Spending Review. The current programme will deliver national and some regional scale estimates of ecosystem and natural capital asset extent, location, and condition. To obtain the finer granularity that customers seek for their decisions and evaluations, additional capital funding will be required to extend the programme for 3 years. Stopping at the end of the FY 24/25 would leave additional benefits unrealised. Hence, we are working with partners and stakeholders to identify potential sources of funding for this. | 23.28 | 26.2 | 13 | The programme was unable to spend its full allocation of funding for 22/23 as it took time longer than expected to staff the programme and to procure the services required. This was due in part due to recruitment restrictions introduced in 2022 and difficulties in getting projects through the commercial process in time. We have now recruited four commercial staff to focus on NCEA procurement and filled many of the vacant posts. | 125 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 125m. This is primarily due to the following factors. The programme has a range of controls and implementable measures to ensure expenditure does not exceed available funds, currently standing at 40.1m for FY 23/24 and 51.6m for FY24/25. Programme funding and costs for future years will be assessed on an annual basis. Where necessary, costs will be submitted as committed liabilities for future Spending Review assessments; for example, where costs are for the maintenance or infrastructure, or where they related to headcount cost. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. N/a - no monetised benefits | DEFRA_0190_2223-Q3
UK Seafood Fund | DEFRA | Government Transformation and Service Delivery | The UK Seafood Fund aims to deliver the 100 million of funding to support the fishing sector, by ensuring better utilisation of our larger share of quota and supporting the industry to become more self-sustaining through increased product value and access to new markets. The fund supports the government priorities of levelling up coastal communities, strengthening the Union and increasing sustainability. The fund is divided into three key elements: Science and Innovation, Infrastructure and Skills and Training. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. This is primarily due to the following factor: Some funding rounds have been completed but there are some delivery milestones yet to achieve. A follow up assurance review is scheduled for June 2023. | 2021-02-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-03-31 to 2025-03-31. This is primarily due to the following factors. An extension to the end date of the scheme and subsequent reprofile of funding as recommended by the IPA Assurance review in March 2022. | 13.1 | 9.3 | -29 | The UK Seafood Fund remains on track to spend the 100 million provided. The variance reflects the changes in spending as a result of the extension of the scheme and will be addressed at the Supplementary Estimates. | 100 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 99m. to 100m. This is primarily due to the following factors. Creation of a new baseline budget and forecast cost following the revised Supplementary Estimate agreed by HMT. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. The benefits for the UK Seafood Fund, as stated in the programme Business Case, have been estimated based on an economic analysis of similar case studies. A significant majority of this will be unquantifiable and unmonetised due to the nature of the projects, therefore it is not possible to predict a profile defining exactly what monetised benefits will be realised and when. | DEFRA_0017_2122-Q1
Workplace and Facilities Management | DEFRA | Government Transformation and Service Delivery | Workplace and Facilities Management services make it possible for Defra Group to operate its property portfolio (over 300 properties and the Weybridge Science Community) for 26,000 colleagues. These essential services include asset maintenance in line with Health and Safety requirements and bio-security regulations. Without these services, the estate (including offices, science laboratories, flood depots etc) would be unsafe and unable to operate, with severe consequences for the UK economy and environment given the frontline nature of much of Defra Groups activity. The project will transform workplace and facilities management services through unifying two separate operating models - utilising an integrated delivery model. This will enhance the working relationship between Defra and its delivery partners, improving the contractual risk apportionment and ensure the control of critical services sits within Defra. As a key enabler, the new services form an integral element of the wider Corporate Services Transformation Programme. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project remains on target to deliver to its Spring 2024 go live schedule. The Amber delivery confidence rating reflects ongoing delivery, stakeholder engagement and resource risks. The Full Business case has received internal approval in principle and will require HMT and Cabinet Office final sign-off before contract award. Mobilisation will start once the contract has been awarded and the Preferred Supplier is in place . The project continues to focus on developing its Target Operating Model, on stakeholder engagement initiatives and on preparing for bringing the preferred supplier on board ahead of mobilisation of the contract. | 2021-06-01 | 2024-10-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2024-12-31 to 2024-10-31. This is primarily due to the following factors. The Project remains on track to go live with the new Contract in 2024. This date is subject to the approval of the Full Business Case in Spring 2023 and subsequent Contract Award. Once the contract has been awarded, and following implementation of the mobilisation plan, the project is scheduled to go live by Spring 2024 | 74.43 | 74.43 | 0 | The GMPP project did not provide data | 866 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 866m. This is primarily due to the following factors. The baseline whole life costs figure is as reported in the Outline Business Case, setting out a position of 865.9. Updated costings information reflecting the Full Business Case (FBC), which sets out Preferred Supplier costs, is being developed and will be reported when the business case has been signed off. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. The Project's Outline Business Case was approved in March 2022, we have subsequently refined benefits details and will be able to provide updated figures following Full Business Case sign-off in early 2023 . The project expects to deliver benefits which include: Legal and health and safety requirements including minimising estate-related incidents and health and safety regulatory compliance; Direct monetary savings (cash releasing benefits), such as the avoidance of unexpected repair and breakdown costs; Indirect monetary savings (non-cash releasing benefits), such as improvements in colleague productivity and reductions in colleague turnover; and Public value benefits, such as social returns on public investment in science; and a wide range of benefits that are unlocked by activities undertaken by the Defra Group colleagues such as animal disease prevention and control; emergency flood response; environmental regulation and the impacts on greenhouse gas emissions. | DEFRA_0012_2122-Q2
CCUS | DESNZ | Infrastructure and Construction | CCUS is essential in meeting net zero targets and we have committed to supporting the deployment of CCUS in two industrial clusters by the mid-2020s and a further two clusters by 2030, as announced in the Prime Minister's Ten Point Plan. As set out in the Net Zero Strategy we have an ambition to capture 20-30 million tonnes of CO2 per annum and, as per the Energy Security Strategy, will enable 10 GW of low carbon hydrogen capacity by 2030 with at least half from electrolytic hydrogen, subject to affordability and value for money. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 2020-04-01 | 2030-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. N/A | BEIS_0018_2122-Q1
Energy Bills Support Scheme | DESNZ | Government Transformation and Service Delivery | The Energy Bills Support Scheme (EBSS) will provide a one-off 400 reduction to domestic energy bills for the significant majority of households in Great Britain and Northern Ireland. The programme is made up of three schemes: Great Britain (GB - c11.7bn), Northern Ireland (NI - c340m) and the Alternative Fund (AF - c380m). EBSS GB is being delivered through six separate payments to applicants between October 2022-March 2023. EBSS NI will be delivered through a single payment to customers from January 2023 (combined with the 200 Alternative Fuel Payment NI scheme). The AF (GB and NI) scheme was launched in Febuary 2023 to deliver a single payment to applicants up til 31 May 2023. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The EBSS GB and NI projects have now been delivered and attention is firmly on increasing voucher redemption rates, compliance and enforcement activities. Their intitial 'high risk' overall risk potential assessment ratings has nowhave reduced to 'low' and 'very low' respectively. The current Delivery Confidence Assessments for these two projects are RAG-ed as Green.The EBSS AF project is currently in delivery with challenges being experienced with the digital application process and a significant number of applicant complaints. Consequently, the RAG rating for this project remains at Amber. | 2022-02-21 | 2023-10-31 | The project's end-date at 22/23-Q4 is 2023-10-31. This is primarily due to the following factors. The EBSS GB and NI projects have now been delivered with outstanding work only remaining in the assurance and benefits space. These projects are on schedule to be closed by end-November 2023.The EBSS AF project is currently in delivery with challenges being experienced with the digital application process and a significant number of applicant complaints. | 12445 | 11988.15 | -4 | Narrative not required as budget variance is inferior or equal to 5%. | 12455 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 12455m. This is primarily due to the following factors. The above 12.5bn baseline is based on costings using the regulator meter points and estimated edge case that should be provided with 400 EBSS support. Updated meter point data provided by suppliers has, however, been marginally lower for the EBSS GB scheme, where an average of 28,753,579 GB customers received 400 over the period, leading to a reduction in forecast spend to 12.2bn. | 12415 | The project's departmental-agree monetised benefits at 22/23-Q4 is 12415m. The programme departmental-agreed benefits at 22/23 Q4 is 12,415m. This figure is an estimate only, representing the total value of the energy grant expected to be delivered through the EBSS GB, NI and AF schemes. This figure should only be considered as a partial analysis of the schemes impact and there will be instances where it is not possible to deliver grant funds.Work is ongoing within the department to quantify impacts which are crucial to the benefits of the schemes, including the avoidance of heating underconsumption and fuel poverty, and they are not accounted for in the baseline benefits figure provided above. Further data on benefits arising from the EBSS schemes is expected to be published in 2024. | BEIS_0102_2122-Q4
Geological Disposal Facility Programme (GDF) | DESNZ | Infrastructure and Construction | The primary objective of the programme is to site and construct a permanent geological disposal facility (GDF) as the safe, secure and environmentally responsible solution to the long term management of higher activity radioactive waste in the UK excluding Scotland. A GDF is the internationally agreed and only viable permanent answer to the UK's existing legacy of Highly radioactive waste. As a nationally significant infrastructure programme a GDF will also provide an opportunity to sustainability boost the economy of the host region and local community to transform itself for many generations. The programme also supports the delivery of the UK's nuclear new build programme as the Government needs to be satisfied that effective arrangements exist or will exist to manage and dispose of the wastes they will produce before development consents for new nuclear power stations are granted. | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (IPA rating). This is primarily due to the following factors. Departmental narrative on schedule | 2008-06-30 | 2050-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2040-12-31 to 2050-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2040-12-31 to 2050-03-31. This is primarily due to the following factors. The indicative project end date is that given for the first emplacement of legacy radioactive waste in the facility, aligned to the Tranche 3 sub programme business case; this includes updated timescales in the securing of willing communities, a better understanding of the full scope of work to characterise the sites through the drilling of deep boreholes and associated consents and permissions and a level of schedule risk and uncertainty.It should be noted that the programme continues to face large uncertainties at this stage due to the site selection process; confidence will increase as the potential site locations are down selected and fully characterised. The schedule remains on target for the first key decision point - site down selection in 2026. | 52.12 | 66.1 | 27 | The budget variance exceeds 5%. The budget variance exceeds 5%. This is primarily due to the following factors resulting in additional spend in year: 1) A case was made to bring forward the seismic survey for Copeland in order to support the site evaluation and characterisation which was completed during the financial year, in addition the opportunity has been taken to procure existing information to further inform site evaluation and characterisation at other sites. 2) Ongoing progress of community partnerships and the utilisation of the Community Investment Funding, recovering some of the activities that were constrained due COVID impacts in prior years. | 20300 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 20300m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 20300m. This is primarily due to the following factors. The whole life costs align with those approved in the Programme Level Business Case. The WLC costs presented in the GMPP report cover both the HMG and non-HMG costs to the programme and are the lower bound estimate within the business case. The lower bound 20.3bn covers the lower technical complexity of the GDF site construction and includes legacy waste, waste from new nuclear and other potential materials. The upper bound of the business case 53.3bn includes for a higher technical complexity GDF construction site, contingency, optimism bias and uncertainty. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. As a nationally significant infrastructure project which will span decades, a GDF will also provide a unique opportunity to sustainably boost the economy of the host region and local community to transform itself for many generations. The benefits of a GDF are wide-ranging and will span many future generations, they fall into four main categories: 1. It is an essential environmental protection project - finally disposing of legacy radioactive waste and providing a safe, permanent solution.2. Enabling the completion of the NDA decommissioning mission across the NDA Group and in particular Sellafield - avoiding the very significant costs and risks of keeping the waste safe and secure in storage facilities above ground for many thousands of years.3. A key enabler for nuclear new build contributing to the British Energy Security Strategy and net-zero 2050 .4. Significant host community benefits - a transformational opportunity by creating thousands of jobs, a highly skilled local workforce, and business opportunities for more than 100 years as presented in the GDF Creating Jobs & Skills report as well infrastructure investment and community support. | DECC_0005_1112-Q1
Green Heat Network Fund | DESNZ | Infrastructure and Construction | The Green Heat Network Fund (GHNF) is a 288 million capital grant fund that supports the following: (i) Commercialisation and construction of new low and zero-carbon heat networks (including the supply of cooling). (ii) The retrofitting and expansion of existing heat networks to make them low carbon. (iii) The development and growth of the heat network market, addressing some of the challenges of decarbonising the UK's heat sector. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Since the GHNF was launched in March last year, three funding rounds have been completed, with the fourth recently closing for applications. To date, we have publicly announced more than 117 million of GHNF awards to 9 projects which use a range of low-carbon technologies including heat pumps, recovered heat, deep geothermal and energy from waste. This includes an announcement on 12 May of nearly 91.5 million in grant funding to 7 projects in Yorkshire, Cornwall, Reading and London. We believe this is the biggest ever announcement of capital funding for heat network projects in this country in terms of the cumulative amount. The UK Infrastructure Bank also announced on 20 December last year that they will offer councils streamlined access to their 4 billion local authority lending product as part of the GHNF application process. In Powering Up Britain and the Energy Security Plan, published on 30 March, the Government announced that capital support will be extended to 2028 to facilitate the continued growth of low carbon heat networks, including 220m additional capital support over 2025/6 and 2026/7 for the Heat Network Transformation Programme, of which the GHNF is a part. Following this, on 30 May, we announced that additional funding will be available for the GHNF and that projects can now apply for funding that can be drawn down in the financial years through to 2026-27. Further details will be announced in due course.Amendments to the scheme rules have also been included in the latest iteration of the guidance for applicants, which will apply from Round 6. These concern changes to the scheme eligibility with respect to networks supplying new build properties. | 2022-03-07 | 2025-03-30 | The project's end-date at 22/23-Q4 is 2025-03-30. This is primarily due to the following factors. The project's end-date at 22/23-Q4 is 2025-03-30. This is due to: Currently, the project end-date remains unchanged but the award of 220m to the Heat Network Transformation Programme for FY2025/26 and FY2026/27 means that continued capital support will be available for longer. | 101.5 | 10.14 | -90 | Year 1 CDEL spent was substantially lower than Year 1 budget. This underspend was expected at the point of business case approval and unspent funds were offered for reallocation in a timely manner. | 298 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 298m. This is primarily due to the following factors. The project's departmental-agree Whole Life Cost at 22/23-Q4 is 298m. This is due to: The scheme is on track to be delivered to budget, with recorded CDEL underspend in year 1. | 2267 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2267m. GHNF's departmental-agreed total monetised benefits is expected to be an estimated 2267.05m over its lifetime (baseline). This estimate remains the same at 22/23. Specifically, the GHNF project is tracking the following benefits:1. An increased volume of thermal energy supplied through low-carbon sources2. Decreased carbon intensity of heat delivered by GHNF supported heat networks3. Monetised carbon savings and air quality improvements4. Increased use of recovered heat in heat networks funded via GHNF5. Increased investment in the UK heat network market | BEIS_0115_2223-Q1
Green Homes Grant: Local Authority Delivery (LAD) | DESNZ | Government Transformation and Service Delivery | BEIS has administered 500m funding to Local Authorities in England to support energy improvements to the worst quality homes by installing energy efficiency measures and low carbon heating. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The delivery confidence status is Amber for the Local Authority Delivery (LAD) project due to the outturn of measures and households delivered against the business case. Over 38,000 houses were completed with 49,000 measures. Local Authorities experienced procurement delay and problems with the supply chain, impacting their capacity to deliver against the full 500m allocation. | 2020-03-01 | 2023-04-28 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-04-28. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-04-28. This is primarily due to the following factors. The delivery of LAD projects by LAs was largely completed by September 2022 with minimal exceptions beyond this date. Post delivery, there were registrations, lodgements and transfers of funds to be actioned before projects could be concluded. | 2.78 | 2.04 | -27 | The budget variance exceeds 5%. LAD 1 &2 evaluation and assurance activity and associated cost will take place in 23/24 due to the timing of the Gate 5 review, reducing the anticipated spend in 22/23. | 509 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 506m. to 509m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 506m. to 509m. This is primarily due to the following factors. The increased baseline WLC reflects an increase in CDEL to fulfil a higher value bids/funding allocations received. This error was corrected in the Q2 GMPP report for 22/23. Against the WLC baseline of 509m LAs spent 340m (66% of the budget) but completed 70% of the business case target for number of homes treated. | 2202 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2202m. The project's departmental-agree monetised benefits at 22/23-Q4 is 2202m. Benefits are predominantly from the energy savings and carbon emission reductions of installing new energy efficiency measures in homes. Wide societal impacts such as improved air quality and improved wellbeing and health outcomes have also been incorporated into this figure. These are estimated in line with HMT Green Book. | BEIS_0011_2021-Q4
Home Upgrade Grant (HUG) Phase 1 | DESNZ | Government Transformation and Service Delivery | The Home Upgrade (HUG) Phase 1 is a 219.6m scheme providing energy efficiency upgrades and low-carbon heating to low-income household living off-gas grid in England to tackle fuel poverty and meet net zero commitments. Forecast expenditure is 195.3m further to midpoint review exercise. Delivery of the scheme started in January 2022 and is now scheduled to finish in September 2023 further to the addition of a Managed Closure period approved by Ministers in February. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The delivery confidence status of Amber reflects delivery risks associated with the project, including those associated with the capacity within the supply chain to support the delivery of measures into homes. Work is ongoing to manage and mitigate these risks, including the recommendation and approval of a Managed Closure period to support further delivery and revisions to policy and scheme design for HUG2 to ensure future projects are better placed to realise outcomes and benefits. | 2020-03-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-07-31 to 2024-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-07-31 to 2024-03-31. This is primarily due to the following factors. Further to agreement by ministers to a Managed Closure period, LAs have the opportunity to extend scheme delivery through to 30th September 2023, with all LAs required to close the month before their commencement of HUG2 if they are continuing into this scheme. This will be followed by a project closure. | 67.85 | 44.49 | -34 | The budget variance exceeds 5%. Capital grants have been recovered from LAs that have not fulfilled their forecast delivery expectations. | 222 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 223m. to 222m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 223m. to 222m. This is primarily due to the following factors. CDEL baseline decreased following the voluntary withdrawal of two approved Local Authority grant applications. | 604 | The project's departmental-agree monetised benefits at 22/23-Q4 is 604m. The project's departmental-agree monetised benefits at 22/23-Q4 is 604.22m. The project's Whole Life benefits have been re-baselined and reforecast (currently equal to the new baseline) following a midpoint review exercise which demonstrated a significant reduction in FBC benefits. The new benefits baseline was presented via a note to PIC. Associated tolerances have been set. An exercise to reforecast benefits, post the current Managed Closure Recovery process will be carried out in Q1. The reduction in primary (annual household bill savings) and secondary benefits (carbon savings) is a result of challenges faced by Local Authorities in identifying sufficient off-gas grid eligible homes, accessing sufficient supply chain capacity and delivering an appropriate measure mix within the scheme's cost caps. While HUG1 will underspend and under deliver on benefit, up to 5,000 homes will be moved to HUG2 for delivery. | BEIS_0012_2021-Q4
Homes Upgrade Grant (HUG) Phase 2 | DESNZ | Government Transformation and Service Delivery | The Home Upgrade Grant Phase 2 (HUG 2) is a 630m government-funded grant scheme that provides energy efficiency upgrades and low carbon heating to low-income households living in the worst quality, off-gas grid homes in England. To tackle fuel poverty and meet net zero commitments. The Delivery of the scheme will start in April 2023 and is scheduled to finish in March 2025. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Funding has been allocated to Local Authorities following the announcement in March 2023 they are now mobilising to begin delivery. | 2020-03-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The project's end-date at 22/23-Q4 is 2025-03-31. HUG 2 scheme delivery milestones are on schedule. There is no current or planned deviation from planned schedule. | 6.55 | 6.37 | -3 | variance not more than 5% | 676 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 676m. This is primarily due to the following factors. The whole life cost of the project is to deliver Grant Funding to local authorities from Feburary 2023 to March 2025. | 1839 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1839m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1838.6m. HUG 2 anticipated benefits will progress towards fuel poverty bill savings, less carbon, levelling up supply chain improvement, better health and quality of life and strenthen the energy security of the UK. | BEIS_0198_2223-Q4
Industrial Decarbonisation & Hydrogen Revenue Support | DESNZ | Infrastructure and Construction | While CCUS and hydrogen production are technically proven and have been deployed successfully internationally, they have not been deployed at scale in the UK and remain pre-commercial. ICC and hydrogen are currently too expensive for industry to deliver alone. Carbon pricing may drive deployment in the longer term, but there is currently no market incentive for investors to take on additional cost and risk. Deployment is needed now to meet the UKs Carbon Budgets, and to capture market opportunities. For a market to grow, we need to put in place the right commercial frameworks and supportive policies to bring through private sector investment. Capital support is provided through the CCUS Infrastructure Fund (CIF) and Net Zero Hydrogen Fund (NZHF). IDHRS will cover lifetime costs for Industrial Carbon Capture (ICC) and hydrogen business models. The ICC Business Model will be government-funded. Funding for hydrogen projects will initially be provided by the government, before transitioning to levy funding. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Carbon Capture Usage & Storage (CCUS) Programme Delivery: The Chancellor confirmed in the Spring Budget 2023 that the government will provide up to 20 billion funding for early deployment of Carbon Capture, Usage and Storage, In the meantime the Track-1 Projects Negotiation List has been published at the end of the quarter, taking forward 8 projects, with clearance to proceed to the negotiations phase. The Track-2 Expressions of interest period has also commenced.Electrolytic Hydrogen (EH2) Delivery: The EH2 allocation round application window closed on 12th October 2022 with 41 submissions. We have assessed applications against the eligibility and evaluation criteria set out in the guidance. In accordance with the shortlisting process set out, we have selected 20 electrolytic hydrogen projects which are invited to proceed to the first step of the Agreeing an Offer stage, consisting of due diligence and value for money assessments in Q2-23 calendar year. | 2021-01-01 | 2050-12-30 | The project's end-date at 22/23-Q4 is 2050-12-30. This is primarily due to the following factors. Last approved end date at Outline Business Case stage is 2050. This is due to the IDHRS being delivered through 15 year Business model contracts and the end date is aligned with the expected deployment costs profile to deliver the "CCUS Phase 2 ambition" from the cluster sequencing project and the first two allocation rounds for electrolytic hydrogen. This end date is subject to review following the CCUS programme rebaseline and will be updated in the respective Full Business Cases for the CCUS and Electrolytic Hydrogen programmes. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | BEIS_0004_2122-Q2
Local Authority Delivery (LAD) Phase 3 | DESNZ | Government Transformation and Service Delivery | The Local Authorities Delivery (LAD) Phase 3 is a 286.8m scheme that has been rescoped to a 239.8m scheme that will continue to provide energy efficiency upgrades and low-carbon heating to low-income households living on-gas grid in England to tackle fuel poverty and meet net zero commitments. Delivery of the scheme started in January 2022 is now scheduled to finish in September 2023 following approval by ministers in February for a Managed Closure period. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. The IPA delivery confidence status is green for LAD Phase 3. LAD Phase 3 was allocated 200m of funding in March 2021, with a further 86.8m allocated to the scheme from the Green Home Grants vouchers underspend as part of the closure of the voucher scheme. Delivery confidence is green because the project is forecast to meet approx 98% of no. homes and within 95% of measures against revised forecast targets agreed in Feb 23 by the Project Investment Committee, with the managed closure supporting delivering for as many of low income households as possible. | 2020-03-01 | 2024-03-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-07-31 to 2024-03-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-07-31 to 2024-03-01. This is primarily due to the following factors. Delivery of LAD 3 commenced in January 2022 and is now scheduled to finish in September 2023, further to agreement by ministers to a Managed Closure period. This will be followed by project closure. | 1.43 | 1.19 | -17 | Evaluation and assurance activities that were forecast for FY 22/23 will now take place in FY 23/24 due to the managed closure as delivery will finish in September | 290 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 290m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 290m. | 736 | The project's departmental-agree monetised benefits at 22/23-Q4 is 736m. The project's whole life benefits have been re-baselined and forecast (currently equal to the new baseline) following a comprehensive mid-point review exercise which demonstrated a significant reduction in FBC benefits and a breach of tolerances. The new benefits baseline was presented via a note to PIC. Associated tolerances have been set. An exercise of reforecast benefits, post the current Managed Closure Recovery process will be carried out in Q1. The reduction in primary (annual household bill savings) and secondary benefits (carbon savings) is a result of challenges faced by Local Authorities in identifying sufficient eligible homes, accessing sufficient supply chain capacity and delivering an appropriate measure mix within the scheme's cost caps. | BEIS_0068_2122-Q3
Low Cost Nuclear Programme (Rolls Royce SMRs Challenge) | DESNZ | Infrastructure and Construction | The Low Cost Nuclear Programme Phase 2 is a 468m (210m grant + 258 match industry funding) Research and Development (R&D) and innovation project aiming to further develop the UK small modular reactor power station concept, to enable the design to successfully pass the key regulatory milestone of Generic Assessment Design (GDA) Step 2 completion by 31/03/2025. The grant recipient, and lead on the project is Rolls Royce SMR Ltd. DESNZ is responsible for the project, and have contracted UKRI to act as delivery partner, providing programme management and assurance of the grant |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Following a slow start to the project the primary supplier has sought to re-baseline the major workstreams over the last year. A revised project plan was agreed in October 2022 and delivery against this has shown improvement over the last quarter. The project remains at Amber until further evidence is available of long term delivery against the new project plan. GDA Step 1 completed as expected and we continue to believe that overall delivery of GDA continues to be achievable within the time frame of the project to March 2025. | 2021-05-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The overall timelines are driven by the desired outcome, of completion of Step 2 of GDA, by 31/03/2025. Progression from Step 1 of GDA to Step 2 of GDA undertaken in Q4. | 186 | 92.3 | -50 | The budget variance exceeds 5% due to the in-year rebaselining of the project plan and its requisite payment forecasts. | 468 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 468m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 468m. This is primarily due to the following factors. The project is currently on track to deliver the desired outcome within the timeframe, with costs driven by the key innovations and work to complete Step 2 of GDA. | 280 | The project's departmental-agree monetised benefits at 22/23-Q4 is 280m. As this is an R&D innovation project the majority of benefits are non-monetised. Direct monetised benefits will be realised through co-investment in this phase of R&D provided by RR SMR Ltd. The wider NPV of the programme, should the design progress beyond the current scope of Phase 2 to deployment will be between 1.3bn and 8.2bn (dependent on the range of SMR capacity employed) | BEIS_0001_2122-Q2
NZHF | DESNZ | Infrastructure and Construction | The Net Zero Hydrogen Fund is a 240 m fund that will be delivered between 2022 to 2025 via 4 strands. The aim of the NZHF is to support the commercial deployment of new low carbon hydrogen production projects during the 2020s, ensuring the UK has a diverse and secure decarbonised energy system fit for meeting our ambition of 10GW low carbon hydrogen production by 2030, and commitment to reach net zero by 2050 |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Strands 1 and 2 of the NZHF were launched in April 2022 and delivered (15 successful projects announced on 30 March 2022 and issued grant offer letters totalling 37.9m). Other funds will be dispersed through the Hydrogen Allocation Round 1 (HAR1) which is a joint Electrolytic Allocation Round with the Hydrogen Business Model (HBM) and NZHF Strand 3. This has made good progress: on 30 March, DESNZ announced 20 shortlisted projects which now move into the Value for money assessments and due diligence. A second window for Strand 1 & 2 is due to Launch in April 2023 with a second Allocation round, HAR2 due to Launch in Q3 2023. Progress is good, but we are reporting as Amber to reflect the large amount of funding which will be delivered through Strand 3 (reflecting the inter-dependencies with the Hydrogen Production Business Model (HPBM) allocation). | 2020-11-18 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The project delivered the first window of Strands 1 & 2 on the 30th of March with 15 successful projects announced and issued grant offer letters totalling 37.9m. The Hydrogen Allocation Round 1 (HAR1) which is a joint Electrolytic Allocation Round with the Hydrogen Business Model (HBM) and Strand 3, Announced 20 shortlisted projects on the 30th of March who now move into the Value for money assessments and due diligence stage. A second window for Strand 1 & 2 is due to Launch in April 2023 with a second Allocation round, HAR2 due to Launch in Q3 2023. | 87.37 | 87.37 | 0 | The budget variance is less or equal to 5%. | 242 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 242m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 242m. This is primarily due to the following factors. The NZHF is worth 240m of CDEL. This spend is forecast within the current SR period and into the next SR. The CDEL estimate reflects the expected spend on grants to support the deployment of UK Low Carbon Hydrogen. These have been forecast using the expected production costs within the BEIS 2021 Hydrogen Production Costs Report. The RDEL estimates reflect the forecasted delivery costs of the fund. | 4390 | The project's departmental-agree monetised benefits at 22/23-Q4 is 4390m. The benefits data has been obtained from the FBC Economic Case. Therefore, we have not broken it down by year to year.. The monetised benefits figures has been obtained from the Economic Case OBC w/ the Displacement of high carbon fuels valued at 1400 m, Carbon savings valued at 2820m and Air quality benefits valued at 170m | BEIS_0002_2122-Q2
Public Sector Decarbonisation Scheme (PSDS) | DESNZ | Infrastructure and Construction | A capital funding programme for heat decarbonisation and energy efficiency improvements in public sector organisations. The PSDS has received funding for three phases. Phase 1 consisted of 1bn of funding which was delivered over 2020/21 and 2021/22. Phase 2 consisted of 75m of funding which was delivered over the 2021/22 financial year. Phase 3 consists of 1.425 billion funding to be delivered over three years between 2022/23 and 2024/25. Funding for further phases of the Scheme will be determined through the Spending Review process. Funding for Phases 1 and 2 of the Scheme ended on 31 March 2022. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. SRO DCA remains Amber. Although the key milestones for year 1 of PSDS Phase 3 has been successfully delivered, the outcome for year 1 in terms of spend and technology deployed remains uncertain. We know that projects are experiencing headwinds from higher than expected costs and tight supply chains linked to wider market responses to the ongoing energy situation. | 2020-07-08 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The project is due to conclude on 31/03/2025 in line with available funding secured as part of the Autumn budget and 2021 spending review. The project end date may shift as funding for further phases of the scheme are determined through the next spending review process. | 504.23 | 504.23 | 0 | The budget variance is inferior or equal to 5%. The forecast budget variance is less than or equal to 5% though underspend arising from late project abandonment and scope changes tends to emerge very late in the year so risks remain that this will increase once full year data is available | 2598 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 2570m. to 2598m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 2570m. to 2598m. This is primarily due to the following factors. The Whole Life Costs increased due to the addition of resource departmental expenditure limit figures for FY 2022/23 following confirmation of budget allocation. | 5324 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5324m. The scheme benefits are monetised as far as possible. The monetised benefits are i) reductions in carbon emissions as a result of changes to fuel consumption, ii) air quality improvements through decreased burning of fossil fuels, and iii) changes to energy consumption. The benefits are monetised using the most recent available Green Book Assumptions.The benefits associated with the scheme continue beyond delivery as projects delivered under the PSDS result in continued carbon emission reductions. | BEIS_0013_2021-Q4
Replacement Analytical Project | DESNZ | Infrastructure and Construction | The Replacement Analytical Project is a key component of the Analytical Services Programme, which provides essential services to operations on the Sellafield Site supporting multiple Programmes & Operational Facilities. The existing facility is 60 years old and cannot provide long-term capability so new analytical facilities need to be established. The Replacement Analytical Project has therefore been initiated to deliver future analytical capability to the Sellafield site, through a major modification of the National Nuclear Laboratory Central Laboratory. Key modifications are provision of standalone Highly Active (HA), Medium Active (MA) and Special Nuclear Material (SNM) analytical capability. A key part of the scope is the delivery of 135 Analytical Instruments which will perform the ongoing analysis required by facilities at Sellafield. Analytical Services remains essential to the delivery of high hazard reduction and remediation until the completion of the Sellafield Ltd mission. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. The red IPA RAG rating was based upon the inability of the project to fall within the OBC cost and schedule range, and that the current range is assessed at a most likely outturn of 1,100-1,300m when compared to the OBC P50 of 680m. The Project will return to the DESNZ Projects and Investment Committee in FY2023/24-Q1 to agree a way ahead. | 2016-09-26 | 2028-07-10 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-07-10. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-07-10. This is primarily due to the following factors. The baseline end date remains at 10th July 2028. However, the current reported forecast of 9th Nov 2028 for completion of project support to active commissioning reflects a 4 month slippage from the Outline Business Case and baseline date, with the significant factor being the impact of COVID. Given the early maturity of the project in the detailed design phase and typically for projects at this stage, the lifetime schedule for future phases is not underpinned and is likely to change as the project matures. Latest level 3 schedule output states completion dates of September 2031 for Special Nuclear Materials (SNM) and October 2032 for Medium Active / Highly Active (MA/HA), these dates will be reflected in the forecast for the quarter 1 submission. | 85.93 | 54.78 | -36 | The in year baseline of 85.93m represents the planned scope to be delivered against the plan put in place in 2019. Actual scope being delivered this financial year is 16.07m, at a cost of 54.78m. The project has delivered less scope than originally planned due to delays in completing design and progressing enabling works (COVID-19 / resourcing issues / supply chain contract delays). The actual scope that has been delivered has cost more than planned due to the requirement of additional design hours and increased management and overhead costs. | 712 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 648m. to 712m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 648m. to 712m. This is primarily due to the following factors. Compared to 21/22-Q4, the RAP budgeted cost (baseline) has increased by 63.93m, this is due to escalation in line with the agreed indices. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. There are no monetised benefits defined within the Replacement Analytical Project (RAP) OBC. The project will provide improved accuracy, reliability and throughput in support of the Sellafield mission for accelerated high hazard risk reduction. Additionally, RAP will enable the removal of analysis from the existing facility, itself a high hazard facility demanding increasingly costly facility and asset care to maintain its safe operational status. In addition to the primary Sellafield mission requirements, RAP will also provide the National Nuclear Laboratory with the research and development capabilities to support the HMG New Nuclear agenda. | BEIS_0007_2021-Q3
Sellafield Product and Residue Store Retreatment Plant | DESNZ | Infrastructure and Construction | To provide a facility that will receive special nuclear material from existing stores on the Sellafield site and process into a form suitable for safe and secure storage until 2120. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. This is a complex, first of a kind nuclear project, and as such has a high degree of delivery risk. The SRP project is being delivered by the Programme and Project Partnership (PPP). The IPA afforded this project a RAG rating of GREEN. | 2012-03-01 | 2029-10-09 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2029-08-20 to 2029-10-09. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2029-08-20 to 2029-10-09. This is primarily due to the following factors. Following the approval of an adjustment event associated with covid impact (from June 2021 to the end of March 22), there was a update to the baseline to reflect the schedule adjustment. | 210.08 | 171.46 | -18 | The variance between the 22/23 baseline and actual is due to several factors: The project has made a number of true savings against the FBC on the scope delivered to date, there has been positive management action taken to secure supply chain contracts for less than the budget. In addition, the project was able to deliver 19.5m of the working plan last financial year in order to de-risk the forward schedule. | 1380 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1278m. to 1380m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1278m. to 1380m. This is primarily due to the following factors. Compared to 21/22-Q4, the SRP budgeted cost (baseline) has increased by 102.5m. 97.5m is due to escalation in line with the agreed indices. In addition, an approved adjustment event for covid impact was implemented increasing the baseline by a further 5m. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. There are no monetised benefits defined within the Sellafield Product & Residue Store Retreatment Plant (SRP) FBC. SRP will provide key capabilities which will enable the delivery of benefits to the Special Nuclear Materials (SNM) Future State Programme at Sellafield. The retreatment and repackaging capability provided will reduce the risk associated with current plutonium storage conditions at Sellafield. The UK has the largest inventory of separated civil plutonium in the world, most of which is stored at Sellafield, safe and secure management of this material is a priority. SNM has identified three long term benefits that will be fully realised once all plutonium packages have been retreated or repackaged and consolidated within modern storage facilities. Enhanced nuclear Safety & Security. Improved high security resilience and a reduction in the number of Category-1 facilities. Value for money by reducing the size of the delivery organisation required for managing future plutonium stocks. | BEIS_0008_2021-Q3
SIXEP Continuity Plant | DESNZ | Infrastructure and Construction | SIXEP Continuity Plant (SCP) is required to deliver a continued site effluent capability in support of high hazard reduction projects and the overall NDA mission. It is a key enabler for the safe and reliable retrieval and treatment of legacy waste at Sellafield, in support of government and Nuclear Decommissioning Authority strategic objectives. | Green |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. This is a complex nuclear project on an operational nuclear site. The Project is in the execution stage with manufacturing and construction activities ongoing. The SCP project is being delivered by the Programme and Project Partnership (PPP). The IPA afforded this project a RAG rating of GREEN. | 2013-05-25 | 2031-01-23 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2031-01-23. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2031-01-23. This is primarily due to the following factors. The Project remains on schedule and there is no change to the date of 23 January 2031. | 198.82 | 114.02 | -43 | The in year spend is less than the budget for 2022/23 due to realignment to PPP Multi Project Procurements and the Category Management approach. This shows that the project is not spending money ahead of demand, does not affect the overall spend position for the project and better aligns key procurements to the current construction delivery strategy. The decision maintains the equipment required on site dates and minimises interim storage costs for plant and equipment. | 1034 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 960m. to 1034m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 960m. to 1034m. This is primarily due to the following factors. Compared to 21/22-Q4, the SCP budgeted cost (baseline) has increased by 74.25m, this is due to escalation in line with the agreed indices. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. There are no monetised benefits within the SCP project however, it will provide key capabilities which in enables the following benefits: Allows the Site Licence owner to meet its requirements in the regulatory permit. Provides effluent abatement to 2060 in support of site missions. Provides an opportunity to deploy an Alternative Ion Exchange (IX) media that improves abatement performance, following the consideration of best available technique (BAT). Maintaining unconstrained Site Ion Exchange Effluent Plant (SIXEP) waste material storage capacity. | BEIS_0009_2021-Q3
Sizewell C | DESNZ | Infrastructure and Construction | The Sizewell C (SZC) project team will lead on negotiations with SZC and EDF (joint shareholder in the project with Government) and will have responsibility for designing a viable funding/financing model that delivers the Government objectives of value for money, fiscal responsibility, and decarbonisation. The Sizewell C project in Suffolk is considered the most advanced new nuclear project in the UK and is likely to be the only project capable of delivering the Energy White Paper objective for at least one large scale nuclear project to reach Final Investment Decision (FID) this Parliament. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 2021-01-01 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | BEIS_0019_2122-Q1
Smart Metering Implementation Programme | DESNZ | Infrastructure and Construction | The Programme aims to replace existing traditional gas and electricity meters across Great Britain with smart gas and electricity meters resulting in a cleaner, cheaper and more reliable energy system. Smart meters are a key enabler of technologies such as electric vehicles, smart tariffs and microgeneration to be efficiently integrated with renewable energy sources, underpinning the cost-effective delivery of Government's net zero commitment. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. - There were 32.4 million smart and advanced meters operating across Great Britain as of end March 2023.- A new 4-year regulatory framework was implemented on 1st January 2022 with minimum installation targets set for energy suppliers for 2022 and 2023.- Work is underway on the Mid-Point review of the Targets Framework. A consultation on minimum installation targets for years 3 and 4 of the Framework (2024 and 2025) closed on 21 March and responses are now being reviewed.- Customer smart meter technical eligibility moved to 99% in January 2023 with the controlled commencement of Alternative Home Area Network solution installations. Deployment is due to enter the mass rollout phase later in 2023. - DESNZ/SMIP continues to work with energy suppliers to improve consumer engagement and operational fulfilment activities to strengthen and increase consumer uptake and to continue to support installations at scale. | 2009-12-02 | 2025-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-12-31. This is primarily due to the following factors. The new four-year installation Targets Framework commenced on 1 January 2022 and will end on 31 December 2025. |  |  |  | The budget variance is inferior or equal to 5%. | 20177 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 20147m. to 20177m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 20147m. to 20177m. This is primarily due to the following factors. The whole life cost figure now reflecting the baseline budgets that were confirmed as part of the Spending Review 2021. | 34130 | The project's departmental-agree monetised benefits at 22/23-Q4 is 34130m. Benefits arise to a number of different groups - to energy consumers in the form of bill savings through reduced consumption and time savings through reduced need to interact with the metering system, to energy suppliers in the form of operational efficiencies (e.g. no more site visits for meter reads, fewer calls to complain about inaccurate / estimated bills), to distribution network operators (e.g. in the form of more targeted investment decisions) and to society as a whole (e.g. in the form of reduced carbon emissions). Benefits break down into around 39% directly to consumers, around 50% to the energy industry (which we expect will be passed through to consumers in the form of lower energy prices) and around 10% in societal benefits to the UK. | DECC_0010_1112-Q1
Social Housing Decarbonisation Fund | DESNZ | Infrastructure and Construction | The 2019 Conservative Manifesto committed to a 3.8bn Social Housing Decarbonisation Fund over a 10-year period. SHDF will support the ambition set out in the Clean Growth Strategy, that as many homes as possible are improved to Energy Performance Certificate (EPC) band C by 2035, and for all fuel-poor homes to reach this target by 2030. SHDF will play a critical role in meeting legally binding fuel poverty targets as set out in the Fuel Poverty Strategy. Owing to the proposed length of the scheme, and the uncertainty in the decarbonisation environment (e.g., electrification/hydrogen decision ), SHDF will be delivered in four waves. SHDF Wave 1 commitments will build on the findings of the SHDF Demonstrator project, scaling up supply chain capacity and knowledge as in advance of the larger, longer-term Wave 2 which has recently concluded its first and major competition phase, with successful bids under Wave 2.1 announced in March 2023. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. There has been considerable progress on the SHDF Programme over 22/23. The Programme is well placed to deliver whilst recognising risks on mobilisation, cost and quality on Wave 1 and Wave 2. The Demonstrator in the last quarter of 22/23 achieved a green at Gateway 5 confirming the benefits/learning it provided to the longer-term direction of the SHDF Programme. Wave 1 issued 187.5 million in grant funding prior to the start of 22/23 with delivery continuing throughout this year. In Q4, Wave1 re-baselined following HMT approval for the grant spend window to extend to the end of June 2023.On Wave 2, a competition launched in Autumn 2022, the outcome of which was the award of 778m of grant funding to 107 projects, with a further 1.1bn committed as match funding. A Delivery Agent (Salix Finance) is in place to support delivery, alongside a Delivery Partner which has been procured with contract award expected to be in late April 23. | 2020-09-09 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. The SHDF programme continues to deliver and, subject to funding being allocated at a future fiscal event, it is expected to continue to deliver to the Programme end date in 2030. The Demonstrator is formally closing as a project, Wave 1 delivery continues as planned with delivery expected to be completed in 2023 and Wave 2 delivery commences at the start of financial year 23/24 for delivery through to 2025. | 251.22 | 13.32 | -95 | The budget variance exceeds 5%. The annual total budget variance exceeds 5%. This is primarily due to the initial agreed CDEL baseline in this report for FY22 /23 being 236m, where the budget allocated was actually 80m. The CDEL and RDEL budgets were underspent due to Wave 2 competition outcomes being known too late to enable maximum delivery in the financial year 22/23. | 4721 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 4721m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 4721m. This is primarily due to the following factors. Whole Life Costs remain unchanged for the programme from FY 21/22. | 10326 | The project's departmental-agree monetised benefits at 22/23-Q4 is 10326m. The Demonstrator project learnings have been shared across the wider SHDF programme, resulting in the active consideration and application of lessons learned with a focus on deriving greater benefits in the delivery of future Waves of the SHDF programme. | BEIS_0014_2021-Q4
Spherical Tokamak for Energy Production | DESNZ | Infrastructure and Construction | Spherical Tokamak for Energy Production (STEP) is a staged programme to design and build, by 2040, a prototype fusion energy plant capable of delivering net-energy to the grid. STEP will demonstrate the technical and commercial viability of fusion, through a design that would be cheaper than other approaches to fusion and through developing a supply chain for this embryonic technology. This will extend the existing UK lead in this field, and place the UK in pole position to design, manufacture and export the first fleet of low-carbon fusion energy plants into an international clean energy market potentially worth Tns p.a. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. IPA gate 0/2 review completed 24/03. Delivery Confidence Assessment - Amber with 12 recommendations.Action plan put in place to support Outline Business Case with second IPA review to be conducted in June ahead of Business case Review in July.The scale of ambition, and risk for Tranche 2 is large. Key areas to address to support this level of ambition were identified by IPA as:-Increase fidelity of reporting to understand progress to plan and risk impacts.-Implementation of Review, Check, Assure to enable agile response to emerging information.-Increase in capability commensurate with the increasing scale of the programme going into Tranche 2.-Increased clarity on cross government sponsorship responsibilities. | 2018-07-16 | 2024-03-31 | The project's end-date at 22/23-Q4 is 2024-03-31. This is primarily due to the following factors. STEP Tranche 1 completes 31/03/2024, in line with original business case and following completion of deliverables identified in original business case. Business Case process is in train to authorise STEP Tranche 2a activity developing the programme out to 2028. | 66.19 | 70.94 | 7 | Underspend in previous financial years was reallocated in last spending review. Variance is against original business case spend profile. Current forecast including this variance is within the overall envelop of the original business case. | 218 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 218m. This is primarily due to the following factors. This is the first Annual Reporting for the Programme. The STEP concept design business case allocated 217.6m for this concept phase. The programme is currently forecasting 217.6m against the scope of the original business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. | BEIS_0153_2223-Q2
Evolve | DFE | Government Transformation and Service Delivery | The Evolve portfolio of change is an enterprise wide transformation which enables SLC's corporate strategy. The strategy has 5 key objectives: An Outstanding Customer Experience; An Enabler of Opportunity; Leaner, Better, Doing more for less; A Great place to work; Trusted delivery partner. The portfolio contains a number of programmes that are designed to further enable and enhance how the SLC delivers its services. These programmes include; Customer Engagement Management, Apps and Portals, Data, Policy Commissioning, Accelerated Service Improvement, People, and Working Practices Transformation. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. Evolve has materially delivered against the strategic objectives set out in the Full Business Case and will complete delivery in FY23-24. Despite numerous delivery challenges, benefits have been protected where possible and a stronger than FBC lifecycle forecast remains. The NPV at the time of writing the Full Business Case was 209.9m and is currently 293.2m.The Full Business Case approved spend was 148m, now forecasting 156m, due to increased costs to deliver CEM.There are currently no programme risks being reported.The position has improved since Q3 as a result of the risks being fully mitigated or not materialising and the APRA position being settled, clearly defining the FY23-24 available budget to support delivery. | 2019-10-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The end date as per the FBC is FY 24-25 | 17.58 | 24.8 | 41 | The budget variance exceeds the 5% threshold against the business case due to the increase in costs to deliver Core Customer Engagement Management (CEM) subsequently creating in year Annual Performance and Resource Agreement (APRA) pressure resulting in other project timelines pushing to the right | 148 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 148m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 148m. This is primarily due to the following factors. Lifecycle costs are within the original budget tolerances as set out in the FBC | 377 | The project's departmental-agree monetised benefits at 22/23-Q4 is 377m. The FY22/23 forecast is 80.7m, an increase of 20.5m from the FBC position. The current lifecycle forecast position of 457.5m is 80.2m higher than that reported in the FBC. | DFE_0013_1920-Q3
FE Capital Transformation | DFE | Infrastructure and Construction | The FE capital transformation will fund investment in FE colleges through: grants, 16 centrally delivered projects, and bidding rounds over five years. The programme will deliver on the government's manifesto commitment to upgrade and transform the FE college estate. This will support the FE sector to deliver on its reform agenda and to support the levelling up of learner and labour market needs across the country, with greater emphasis on technical education and vocational training. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Delivery Confidence Assessment is Amber as rated by the external assurance review in January 2023. All three phases of the programme delivery are launched and are being progressed in tandem. Phase 1 is complete. Phase 2 and Phase 3 round 1 are slightly delayed but are now progressing well. Phase 3 round 2 allocations were announced on 28 March and grants are due to be made in May. Delays will affect the profile of outturn spend; HMT approved a subsequent revised baseline spend profile in February 2023. | 2020-04-01 | 2025-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-06-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-06-30. This is primarily due to the following factors. All three phases of the programme are launched and being progressed in tandem. The first phase of the fund saw an initial 200 million allocated to all colleges so they could carry out urgent remedial work to refurbish their buildings. Following this, in April 2021 an announcement was made to work in partnership with sixteen colleges with some of the poorest condition sites in the country to upgrade their sites and ensure they are excellent places to learn. Construction is nearly complete at Stafford College and other schemes will soon follow. Through Phase 3 60 FE colleges across the country are to benefit from building and campus upgrades and transformation, helping to level up opportunities for more people. Around 76 projects will be supported to allow colleges to create great buildings and facilities for high-quality training so more people progress into rewarding jobs, and plugging plug skills gaps in local economies. A final allocation of 286million will be made to colleges for them to continue to rebuild and upgrade their facilities. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | DFE_0015_2021-Q3
Higher Technical Education | DFE | Government Transformation and Service Delivery | The higher technical education reforms aim to raise the quality and uptake of level 4/5 technical courses, with Higher Technical Qualifications (HTQs) as a flagship offer and credible alternative to traditional 3-year degrees. The reforms are underpinned by the findings of the Independent Sainsbury Review and form part of a wider suite of technical education reforms, including T levels and apprenticeships. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Overall delivery confidence is at Amber. There has been significant progress across the programme this quarter and we continue to see strong Ministerial support. However, this is a long-term endeavour to reform the level 4/5 market and change entrenched perceptions and behaviours over the course of roughly 10 years. | 2019-10-01 | 2027-09-01 | The project's end-date at 22/23-Q4 is 2027-09-01. This is primarily due to the following factors. The programme schedule remains achievable | 58.4 | 18.1 | -69 | The budget variance exceeds 5%. The budget variance is mainly due to reprofiling of the HTE Skills Injection Fund, and clawback from the HTE Growth Fund. | 176 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 176m. This is primarily due to the following factors. Total Baseline Whole Life Costs reflect initial budgets for each year to deliver the HTE Reforms, from 2020-21, up to 2024-25 in line with the current spending review period. 2023-24 and 2024-25 are subject to annual business planning. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. As our reforms go through the early stages of delivery, with the first teaching of HTQs this academic year, we have updated our monitoring & evaluation and benefits realisation strategies. The benefit of HTE reforms is greater uptake of high-quality HTE generally and HTQs specifically. | DFE_0173_2223-Q2
Initial Teacher Training Market Review (ITT) | DFE | Government Transformation and Service Delivery | The government commissioned an Expert Advisory Group to review the Initial Teacher Training (ITT) market to address issues around quality and inconsistency. The reviews recommendations, which the government has accepted, aim to increase the quality and consistency of ITT in a more effective market. The ITT Reform programme has been set up to implement the recommendations. The programme will ensure that ITT providers adopt a series of new 'Quality Requirements', which were assessed during a market-wide re-accreditation process starting in February 2022. This was followed by improvement support and readiness checks beginning in November 2022, with the aim of ensuring the market delivers reformed ITT to trainees from September 2024. The reform is also designed to complement ongoing reforms to improve teaching quality, including the new Core Content Framework, Early Career Framework and National Professional Qualifications. The programme is on track to deliver the reformed ITT from September 2024. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The ITT Reform programme is on track to deliver reformed ITT for trainees from September 2024. The Stage 1 accreditation process is now complete with 179 providers accredited to deliver ITT from September 2024. This is significantly higher than expected and, combined with ongoing work for providers to expand their provision, will mitigate sufficiency risks. Work is now ongoing as part of Stage 2, to check the readiness of providers to deliver and provide any required improvement/readiness support. Following initial checks by ITT Associates, 75% of providers have already been flagged as ready to deliver (RAG rated Green), with targeted support now being provided to the remaining providers. Remaining checks, and related support, are expected to conclude in Spring 2024 ahead of the start of reformed ITT courses in September 2024 The curriculum check will conclude September 2023, at which point we will have assurance on the quality of the provision and the programme is expected to move to Green.The programme has remained Amber while partnership agreements are finalised to expand the provision of accredited providers, following which the programme is expected to move to Green. | 2021-11-10 | 2024-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. The Full Business Case has been approved and the programme end-date remains scheduled to finish on 30 SEP 2024 . This is primarily due to the following factors:- The recommendations of the Expert Advisory Group has been published and agreed with the Department (July 2021)- Stage 1 of the process has been completed with 179 provider accredited (Sep 2022)- Stage 2 has commenced (Nov 2022) and is on track to finish within schedule | 5.06 | 3.44 | -32 | Key factors for variance are: the budget has an element of demand led costs through grants. Capital spending has been delayed until FY 24/25 and the budget for FY22/23 and 23/24 surrendered; Programme staffing pressures for FY22/23 and 23/24 released due to reorganisation and costs absorbed by central budgets. | 56 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 55m. to 56m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 55m. to 56m. This is primarily due to the following factors. Programme costs are made up of a combination of projected grant costs, capital costs and programme funded staff. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. No monetised benefits will be realised by this project | DFE_0051_2122-Q3
Institutes of Technology (IoT) 2 | DFE | Government Transformation and Service Delivery | The Institutes of Technology programme is a manifesto Commitment to establish the second wave of high quality Institutes of Technology (IoTs). the first 12 IoTs were selected through a government led competition and commenced Live delivery from September 2019, wave 1 has successfully deliver 12 IoTs across the country, Wave 2 utilised the same model as Wave 1 successfully delivering a further 9 IoTs, and are collaborations between further Education (FE) providers, universities and employers. IoTs specialise in delivering higher technical education (at levels 4and 5) with a focus on STEM (Science, technology, engineering and Mathematics) subjects |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. 8 of the 9 wave 2 IoTs have now signed their Capital Funding Agreement and Licence, with the last due to be signed by end of May 2023. We expect 7 of these to commence delivery from September 2023, with the remaining commencing from September 2024. Some capital works will continue during this period. No actions required on RAG rating. | 2020-01-01 | 2026-01-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-01-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-01-01. This is primarily due to the following factors. No deviation from planned schedule at present, more information will become available from final agreements with contractors. | 4.3 | 4.3 | 0 | The budget variance is inferior or equal to 5%. Not applicable, budget variance does not exceed 5% | 6 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 3m. to 6m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 3m. to 6m. This is primarily due to the following factors. Whole life costs are still being agreed with wave 2 contractors and will be available once all wave 2 IoTs have agreed CFAs, Licences and agreements with contractors |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Not applicable, no monetised benefits will be realised from this programme | DFE_0016_2021-Q3
Lifelong Loan Entitlement | DFE | Government Transformation and Service Delivery |  | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | DFE_0109_2223-Q1
National Tutoring programme | DFE | Government Transformation and Service Delivery | The NTP makes available subsidised tutoring to boost progress and support for those children most in need to catch up on education lost because of Covid-19. The programme offers three routes to subsidised tuition: Academic Mentors: employed to work as full-time, in-house staff members to provide intensive support to pupils who need it. Tuition Partners: external tutoring organisations, quality assured by DfE. School-Led Tutoring: offering flexibility for schools to use their own staff to provide tutoring, which may involve personnel they currently employ, or staff newly engaged for this purpose (which could include retired teachers, supply teachers, support staff or others) For academic year 2022/23, we are allocating all funding directly to schools. This has made the process simpler for schools and given them the flexibility to arrange tutoring to exactly meet the needs of their pupils. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Infrastructure Project Authority's Delivery Confidence Assessment rating at end of 22/23 Q4 is Amber. Gate 0 review scheduled for July 2023. We continue to address recommendations from the IPAs previous Gate review, and have begun to engage with the IPA to plan for the next Gate 0 review which is scheduled for July 2023. We will be preparing documentation for IPA according to the areas of focus for the review, and will prepare stakeholders to be interviewed by the review team. | 2020-07-01 | 2024-07-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-07-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-07-31. This is primarily due to the following factors. The National Tutoring Programme is on schedule and there has been no deviation from the planned schedule to deliver subsidised, high-quality tuition to those disadvantaged pupils most impacted by the pandemic. | 419.5 | 241.13 | -43 | The budget variance exceeds 5%. AY 21/22 figures have now settled and the Department have clawed back unused funding from schools. This was forecast at Q3. Variance between baseline and forecast is due to lower delivery than forecast. Funding for AY 22/23 is provided in advance. However, all schools have until the end of each Academic Year to spend NTP funding. This will be returned to the Department if not spent. As a result, we will see a credit on our grant lines in FY23-24. A robust forecast figure will be provided at Q1. | 1125 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1121m. to 1125m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1121m. to 1125m. This is primarily due to the following factors. The Department has increased capital funding for this programme by 4m to fund the Find a Tuition Partner digital service. This spend is profiled over three financial years. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Not applicable, no monetised benefits realised by this programme | DFE_0020_2021-Q4
School Rebuilding Programme | DFE | Infrastructure and Construction | The School Rebuilding Programme (SRP) is undertaking major rebuilding and refurbishment projects targeted at school and sixth form college buildings in the worst condition across England. The programme was announced by the PM in June 2020. The number of projects in the programme was confirmed publicly in HMT SR 2020 documentation, with a commitment to announcing 50 new school rebuilding projects a year for ten years. An initial programme budget was agreed with HMT in May 2021 (HMT confirmation letter received in July 2021) as part of the programmes clearance through the Treasury Approval Process (TAP). The first 161 projects from Rounds 1-3 are in delivery and we achieved a significant programme milestone with the first SRP project handed over in February 2023. Additionally, 24 projects have now entered contract as of March 2023, 15 in the 22/23 financial year. We announced a further 239 schools into the programme in December 2022, from nominations received in 2022. These schools will enter into delivery at approximately 50 projects per year over the next 5 years. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The first 161 projects from Rounds 1-3 are in delivery and we achieved a significant programme milestone with the first SRP project handed over in February 2023. Additionally, 24 projects have now entered contract as of March 2023, 15 in the 22/23 financial year.We announced a further 239 schools into the programme in December 2022, from nominations received in 2022. These schools will enter into delivery at approximately 50 projects per year over the next 5 years. | 2020-11-01 | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | The programme scheduled end date remains changed. | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | DFE_0018_2021-Q3
Schools Commercial | DFE | Government Transformation and Service Delivery | The Schools Buying Programme is designed to support schools in achieving value for money and directly contributes to delivery of both the efficiency and sustainability portfolios. Our Strategy is designed to support schools to achieve value for money on their non-staff spend, be more sustainable and change the behaviours of buyers in schools to ultimately achieve value for money and enable more spend to be focused on improving educational outcomes. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. Programme delivery confidence (DC) is currently Amber. Whilst we are on track to deliver forecast benefits over the next 10 years, we have experienced challenges with recruitment and retention in the last year that has delayed delivery and mobilisation of some projects. Funding is secured and we have now reached agreement on headcount for the remainder of this SR that will enable delivery to plan once recruitment into priority roles has completed. Programme scope has expanded to prioritise resilience and sustainability projects to ensure financial efficiency in the long term and delivery of the new Get Help Buying for Schools Service is now live nationally and supporting schools through the current cost of living crisis. Overall, the programme is effectively set up, funded and soon to be resourced for effective delivery. | 2020-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Programme schedule remains on track and is reviewed monthly at Programme Board meetings chaired by the SRO. An independent IPA led assurance review of the programme was conducted in March 2022 and assessed delivery confidence as green. The green rating has been assigned on the basis that successful delivery to time, cost and quality appears highly likely and there are no major outstanding issues that appear to threaten delivery. | 24.45 | 25.11 | 3 | The budget variance is inferior or equal to 5%. | 145 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 181m. to 145m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 181m. to 145m. This is primarily due to the following factors. In 2021/22, the Schools Buying Programme expanded its scope to include efficiency projects, aimed at supporting schools in increasing their energy and water efficiency. Whole Life Cost (WLC) encompass the live and anticipated projects being undertaken in the programme. It should be noted that, due to the test and learn nature of the programme, this may lead to amendments to the forecast WLC. While the programme is scheduled for 5 years, the WLC and benefits span 10 years to reflect the transition from project to BAU. The figures provided have been rounded to the nearest 1,000,000 and VAT (20%) has been included on all non-staff costs. All admin staff costs are inclusive of Travel and Subsistence. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Not applicable, no monetised benefits realised by this programme | DFE_0019_2021-Q3
Skills Bootcamps and Free Courses for Jobs | DFE | Government Transformation and Service Delivery | The National Skills Fund (NSF) helps people retrain and upskill into better, more productive jobs through developing higher and intermediate skills, and aligned with Further Education. The project is comprised of two offers, Skills Bootcamps and Free Courses for Jobs. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The National Skills Fund programme remains broadly on schedule, with delivery of Free Courses for Jobs meeting agreed milestones and exceeding delivery trajectories. Skills Bootcamps dynamic purchasing system has delivered to agreed milestones although risks remain around the expansion of starts numbers in 2023/24 and whether this will be fully achieved by planned procurement. | 2020-04-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-03-31. This is primarily due to the following factors. The project end-date is 31 March 2024. This is primarily due to the following factors: The programme end date reflects the financial commitment to fund the National Skills Fund until the end of this parliament. By this point the programme will have delivered on various interventions to fill the gaps in adult skills in key sectors and assist learners in achieving better jobs, including the Free Courses for Jobs Offer and Skill Bootcamps. The timeline is driven by the need to deliver these interventions in a way that allows initial delivery to inform future design, accommodate the consultation on adult skills and align with the wider adult skills reform work. | 150 | 107.2 | -29 | The budget variance exceeds 5%. The delivery profile for the programme moved later in the financial year moving some delivery and associated expenditure into 2023/24. | 696 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1149m. to 696m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1149m. to 696m. This is primarily due to the following factors. The whole life cost reported last year being based on initial estimates which have now been revised in the latest business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Not applicable, no monetised benefits realised by this programme | DFE_0017_2021-Q3
T Level Programme | DFE | Government Transformation and Service Delivery | To increase the economic value of skills being supplied by the post 16 system, increasing take-up of high quality qualifications to improve skills, increasing productivity and social mobility. To enable the sustainable delivery of new high quality T Levels for 16-19 year olds. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. The current IPA Delivery Confidence Assessment for T Level programme is red, following the Gate 0 review in February 2023. To address challenges to delivery, the February IPA review recommended that the programme's objectives be reviewed and refined and the programme re-baselined to refocus delivery on sustainable growth. The current viability of the programme is not in question and this reset is taking place alongside continued delivery for summer 2023. A review of the progress against the recommendations took place in June, and the programme has subsequently received an Amber rating at the Assurance of Action Plan. The review team noted "The SRO and programme team are commended for the significant amount of work that has been undertaken by the programme team in a short space of time to address the (letter and the spirit of the) previous recommendations." | 2016-10-25 | 2023-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-09-30. This is primarily due to the following factors. The change in date from 30 September 2023 to 30 September 2025 is a result of the updated Business Case, drafted in September 2021, reflecting changes to business as usual and a revised project end date of 30 September 2025. | 232.2 | 248.2 | 7 | The budget variance exceeds 5%. The budget variance is mainly due to additional CDEL spend for T Levels Specialist Equipment Allocation (SEA) as agreed with HMT. This is partially offset by underspend on RDEL which mainly relates to - changes to Industry Placements Employer Support arrangements - revised forecasts from IfATE due to structural changes - refined delivery plans for Phase Two of T Level Professional Development (TLPD) | 1754 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 919m. to 1754m. This is primarily due to the following factors. At 2122-Q4 the projects total Baseline Whole Life Cost were only until 2022-23. Total Baseline Whole Life Costs have been updated to reflect up to 2024-25 in line with the latest approved Programme Business Case, and current spending review period. Our current budgeted whole life costs reflect:- actual spend from pre-2019 to 2021-22,- 2022-23 actual costs at P11 plus remaining forecast for FY,- 2023-24 to 2024-25 forecasted costs based on the latest Programme Business Case, subject to annual business planning. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Not applicable, no monetised benefits realised by this programme | DFE_0010_1819-Q1
Teacher Development Reform Programme | DFE | Government Transformation and Service Delivery | The Teacher Development Reform (TDR) Programme is part of the wider reforms to Teacher Continual Professional Development (CPD) and the DfE Teacher Recruitment and Retention Strategy, referenced in the DfE White Paper published in March 2022, 'Opportunity for all: strong schools with great teachers for your child'. The TDR Programme includes, the Early Career Framework (ECF), National Professional Qualifications (NPQ) and National Institute of Teaching (IoT) projects. These exciting innovations are part of the investment in our teachers and leaders which include; a new two year induction for Early Career Teachers (ECT), with mentors trained and provided to support those new teachers and; new Specialist NPQs and reforms to our existing Leadership NPQs. Alongside this, the NIoT has launched and will be showcasing exemplary delivery of ITT, the ECF and NPQs, delivering evidence-based approaches to teacher training, leadership training and continued professional development, building on existing high-quality provision. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Teacher Development Reform Programme delivery confidence assessment is rated Amber. This reflects all TDR sub-programmes and projects: ECF, NPQs and the National Institute of Teaching. This delivery confidence is based on approved business cases, structured delivery plans and planned risk mitigations monitored in line with a clear TDR risk management strategy. Significant progress has been made across the programme, with the successful launch of the ECF and new suite of NPQs in Autumn 2021 and the NIoT in Autumn 2022. The Amber rating is a reflection of the key programme risks that relate to meeting take up targets for NPQs. We recognise that this is a key challenge and have implemented a number of key actions to mitigate the risk. | 2018-11-01 | 2026-02-12 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-02-12. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-02-12. This is primarily due to the following factors. Project schedule remains on track for delivery in line with the current plan. | 194.62 | 112.92 | -42 | The budget variance exceeds 5%. The programme is recording a -42% variance primarily due to an end of year accrual not meeting tightened assurance requirements, which resulted in a c.52m underspend. The remaining level of underspend is due to reduced uptake of NPQ participants and reduced numbers of ECTs coming through the ITT pipeline. | 761 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 761m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 761m. This is primarily due to the following factors. At 22/23 Q4 the programme expects whole life costs to be c.617.85m. This is a variance of -19% compared to the baseline whole life costs. This is primarily due to the demand led nature of the programme and an end of year accrual not meeting tightened assurance requirements that resulted in a significant programme underspend in FY22/23. | 8 | The project's departmental-agree monetised benefits at 22/23-Q4 is 8m. The Teaching School Hub business case set out that the cost of continuing with the previous teaching school system would require approximately 27-29m in programme funding per year for infrastructure functions, compared to the new system requiring approximately 18.9m per year, creating a saving of 8.1m-10.1m per year in steady state. In the financial year 2022-23 the Department for Education made a greater than forecasted saving of 9.16m-11.16m, with 17.84m spent in total. | DFE_0014_2021-Q2
2nd Generation UK Search and Rescue Aviation | DFT | Government Transformation and Service Delivery | The UK Search and Rescue Second Generation (UKSAR2G) programmes is the UK's replacement aviation Search and Rescue (SAR) and Aerial Surveillance and Verification (ASV) services that will continue to save lives, protect the UK's economic interests and maintain aeronautical compliance with International Conventions beyond 2024. |  | Green | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Green. This is primarily due to the following factors. The tender assessment was completed and the contract awarded to Bristow Helicopters Ltd. The programme is mobilising and regular meetings have been established between the MCA and BHL. Internal workstreams are being established to manage the transition between the old and the new contracts.The Gateway Review found that the Programme is well-established and constructed and seeks to deliver a vital emergency service without loss of continuity. | 2019-12-16 | 2026-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-12-31. This is primarily due to the following factors. The contract has been awarded and the FBC approved. The contracted schedule maintains the projected end date. |  |  |  | The GMPP project did not provide data | 1959 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 2607m. to 1959m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 2607m. to 1959m. This is primarily due to the following factors. The cost of the accepted bid was lower than anticipated and this has been reflected in the Full Business Case which has been approved by DfT and HMT. Milestone payments will be made as each base transitions to service. | 24475 | The project's departmental-agree monetised benefits at 22/23-Q4 is 24475m. The project departmental-agree Benefits at 22/23-Q4 is 24.5b. The project is in its mobilisation phase. The Search and Recue bases will transition to the new service between October 2024 and January 2027, during which, the benefits will start to be realised as the assets respond to incidents. The actual benefits annual benefits will progressively increase as each base transitions to this new contract. The majority of the benefit value is derived from the lives saved by the service. | DFT_0048_2021-Q3
A12 Chelmsford to A120 Widening | DFT | Infrastructure and Construction | As announced in the Roads Investment Strategy 2, the scope includes: Widening the A12 to three lanes between junction 19 (north of Chelmsford ) and junction 25 (A120 interchange) |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The IPA review in September 2021 identified 6 specific actions which have been addressed including updates to the project benefits register to highlight local economic benefits and the improvement of risk software to track and manage known project issues as part of the risk management process. | 2015-04-01 | 2028-07-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-07-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-07-31. This is primarily due to the following factors. The project schedule has an approved baseline position of July 2028 for the project end date and a current forecasted project end date of October 2028. This milestone is not the same as the forecasted date for the road to be open to traffic following the improvements which is December 2027. This is the point at which the post-construction benefits will begin to be realised. Within the year, there was slippage to an interim milestone as the DCO application was completed in August 2022 however this allowed for a more robust submission. | 50.89 | 60.19 | 18 | Variance due to the adjustment for the NR VAT re-calculation. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | DFT_0034_1920-Q2
A303 Amesbury to Berwick Down | DFT | Infrastructure and Construction | This is a road upgrade scheme to construct a free-flowing dual carriageway replacing the current single lane on the A303 between Amesbury and Berwick Down including a twin bore tunnel under the majority of the World Heritage Site and a by-pass and viaduct to the north of Winterbourne Stoke. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project still awaits the Development Consent Order (DCO) re-determination decision. Until such time as this is received the project has paused site preparation works. | 2014-12-01 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 7.53 | 13.82 | 84 | The GMPP project did not provide data | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | The above shows the provisional baseline that was presented to the Chief Secretary of Treasury in 2022. It incorporates the expected delay due to the Judicial Review impact and will be reviewed once the DCO re-determination delay is known. | 1486 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1486m. DCO redetermination could impact the benefits | DFT_0024_1516-Q4
A417 Air Balloon | DFT | Infrastructure and Construction | As announced in the Roads Investment Strategy 2, the scope includes: A417 Air Balloon - connecting the two dual carriageway sections of the A417 near Birdlip in Gloucestershire, taking account of both the environmental sensitivity of the site and the importance of the route to the local economy. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. An Independent Assurance Review (IAR) 3B was undertaken in October 2022 with a Green outcome. Project received 5 recommendations of which 2 were recommendations and 3 were essential. An action plan was put in place and all recommendations have been completed | 2015-04-01 | 2027-08-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2027-04-30 to 2027-08-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2027-04-30 to 2027-08-31. This is primarily due to the following factors. Start of Works (SoW) was achieved on 17 February 2023, one month ahead of the DfT approved forecasted date, and seven months ahead of National Highways Delivery Plan commitment date. Project is still on target to achieve commitment dates | 33.4 | 30.5 | -9 | The baseline for 22/23 was set in the 21/22 FY, prior to appointment of the Delivery Integrated Partner at a point where the preliminary design was still being improved. As the project mobilised the Regional Delivery Partnership contract, we acquired more certainty over work packages through the year. National Highways also changed the supplier for its project controls function (the contract) and the contractual rates differed from the assumptions made when the baseline was set. | 482 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 482m. This is primarily due to the following factors. The project is forecasting within the approved budget | 424 | The project's departmental-agree monetised benefits at 22/23-Q4 is 424m. The benefits have been reprofiled in line with the latest economic appraisal (Business Case). The benefits have dropped by 92m (Present Value Benefits) since updated Outline Business Case (Approved in 2021) due to changes in transport appraisal guidance and methodology updates. There has been no material change to the project scope. | DFT_0044_2021-Q2
A428 Black Cat to Caxton Gibbet | DFT | Infrastructure and Construction | The scheme provides a new off-line two lane dual carriageway between Black Cat roundabout on the A1 in Bedfordshire and Caxton Gibbet roundabout on the A428 in Cambridgeshire. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The A428 Black Cat to Caxton Gibbet Project is currently in the development phase. The Development Consent Order (DCO) process has concluded with Secretary of States (SoS) granting consent for the scheme August 2022. There have been delays to the schemes delivery plan milestones due to a Judicial Review challenge. The impact of delays associated with the legal process has significantly impacted the projects programme and cost. The project will be returning through governance beginning in Q2 2023/2024 for approval of an updated Full Business Case and re-baseline. | 2015-04-01 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | There have been delays to the schemes delivery plan milestones due to a Judicial Review challenge. The impact of delays associated with the legal process has significantly impacted the projects programme. The project will be returning through governance with a full impact analysis of delay and re-baseline, ahead of Start of Works. | 60 | 34.4 | -43 | There have been delays to the schemes delivery plan milestones due to a Judicial Review challenge. The impact of delays associated with the legal process has significantly impacted the projects programme and cost. The scheme missed the planned Start of Works milestone for December 2022, which has decreased the in year costs reflecting the reduced activity necessitated by the legal challenge. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | DFT_0031_1819-Q1
A66 Northern Trans-Pennine | DFT | Infrastructure and Construction | Dualling of the remaining single-carriageway sections on the A66 between M6 J40 Penrith and A1M Scotch Corner, creating a continuous dual carriageway across the Pennines. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. An Action Plan has been put in place to address the five actions from the last Assurance Review, and progress is monitored on a monthly basis. The next the IPA Assurance Review (scheduled for July 2023) will formally review progress against the Action Plan. | 2017-07-05 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. The committed milestones of Start of Work in Q4 23/24 and Open for Traffic in Road Investment Period 3 are still on track. Over the course of Financial Year 22/23, the project has achieved a number of important milestones, including Development Consent Order Submission (June 2022), National Highways Project Controls Framework Stage 3 completion (June 2022), contract award with the Delivery Integration Partners (October 2022), and the commencement of the Development Consent Order Examination in November 2022. | 68.8 | 66.76 | -3 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 692 | The project's departmental-agree monetised benefits at 22/23-Q4 is 692m. The baseline monetised benefits reflect the June 2022 DfT Investment Committee (IPDC) approved position. A value for money remediation plan is being implemented. This information will be presented in the Full Business Case. | DFT_0047_2021-Q3
Crossrail Programme | DFT | Infrastructure and Construction | A new high-frequency rail service which will increase rail-based capacity in London by up to 10% and cut journey times across London and the South East. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. Since opening on 24 May 2022, the Elizabeth line has had high levels of reliability and usage having been used by more than 120 million passengers.The final stage of opening which will deliver full end to end services, as well as bringing the Elizabeth line up to the end state frequency level of 24tph in the peak, is due to be delivered on 21 May 2023 as part of the national timetable change. There are still concerns over the performance of Network Rails western route, with Great Western performance issues affecting all services in and out of Paddington, including Elizabeth line services in the western section. However, improvement plans are now in place, and are being monitored, and there is a strong focus from Network Rail and TfL on performance improvement in the western route and making sure the timetable change goes as well as possible. | 2008-07-22 | 2023-05-14 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-05-14. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-05-14. This is primarily due to the following factors. The Elizabeth line opened to passengers within the central section on 24 May 2022. 6 November saw the successful start of through-running services connecting Reading and Heathrow in the west and Shenfield in the east to the central section tunnel. This also saw the introduction of Sunday services and an increase in service levels through central London from 12 to 22 trains per hour (tph) in the peak (16 tph off peak).As Bond Street station opened on 24 October 2022, all Elizabeth line stations are now open for revenue service.The final stage of opening which will deliver full end to end services, as well as bringing the Elizabeth line up to end state frequency level of 24tph in the peak, is forecast to be delivered on 21 May 2023 as part of the national timetable change. | 197 | 295.1 | 50 | The budget variance exceeds 5%. Yearly budget/forecast variance is due to higher actuals for 2022/23 than the baseline costs which were projected in 2020/2021. However, 60m of contingency was released therefore reducing the overall Anticipated Final Crossrail Direct Costs. On Network Works saw a re-profile of costs into 2023/24 for residual works and commercial closeout. | 18815 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 18814m. to 18815m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 18814m. to 18815m. This is primarily due to the following factors. The Anticipated Final Crossrail Direct Costs decreased this year by 60m to 15,903m, reflecting contract completions and the close out of risks as the project approaches final completion. The overall project costs include Network Rail costs for the On Network Works but excludes costs for rolling stock and depots. A long-term funding settlement was agreed with TfL in August 2022 which included the funding to complete Crossrail. | 19800 | The project's departmental-agree monetised benefits at 22/23-Q4 is 19800m. A post-opening evaluation study, jointly funded by DfT and Transport for London, is expected to be completed in Summer 2024. This will report on the impacts of the Elizabeth line/Crossrail since opening in May 2022. At the time of writing this report, nearly 140m journeys have been completed on the Elizabeth line. | DFT_0001_1112-Q1
East Coast Digital Programme | DFT | Infrastructure and Construction | The East Coast Digital Programme will introduce European Train Control System signalling technology to the East Coast Mainline southern section between Kings Cross & Stoke Tunnel just south of Grantham. This will involve the removal of conventional line-side traffic light signals and their replacement with digital signalling which will display safety information in the drivers cab. This is the first implementation of this technology on a UK mainline route, and will provide drivers with more information through the continuous communication between the train and track, allowing for greater safety and reliability. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The programme received an AMBER RAG rating at its annual Gateway 0 review held in September 2022. The review team recognised the unique and challenging nature of the programme and highlighted several key risks to delivery broadly focused on freight fitment, risk management and industrial relations. To support the successful delivery of the programme the review team provided 13 recommendations for ECDP to implement ahead of the next planned review in September 2023. Since the review 8 of the 13 recommendations have been implemented on the programme with a clear plan for the delivery of the remaining 5 ahead of the next review. Outstanding actions include the signature of freight business change agreements, launch of a programme intranet and marketing campaign, the holding of the annual QCRA risk review, publication of a refreshed programme mandate and an update to the programme benefits strategy. All 5 of these actions have an assigned owner and are tracked and reported on with an escalation route to the SRO. | 2017-05-01 | 2030-10-14 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-10-14. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-10-14. This is primarily due to the following factors. The programme remains on schedule at the end of this reporting period. Since the last annual report a number of Tier 1 milestones have been achieved by the programme. This includes the commissioning into service of the interlocking system at Moorgate on the Northern City Line as well as the successful system proving of the ETCS system on the same branch line. However, delays continue on agreeing the signature of several major contracts which is putting significant pressure on programme schedule as we move into the next reporting period. In addition, the programme faces a major challenge in securing requisite additional engineering access over the coming year to make up for lost access over the last reporting period due to industrial action outside of the programmes control. Both of these factors bring a risk that over the next year programme schedule may move to reflect the delay to agreeing these contracts. | 222 | 232 | 5 | The GMPP project did not provide data | 3477 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 3477m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 3477m. This is primarily due to the following factors. At the end of the reporting period, programme who life costs have remained stable over the last year. Despite inflation remaining a key risk to the programme this has not yet materialised into higher whole life costs. However, as the programme moves into the next reporting period there remains a risk that cost will increase due to the challenge of securing sufficient engineering access to make up for delays caused by industrial action over the last year. Mitigations are being prepared by the programme, but the risk remains that this will cause significant additional cost to the programme. | 826 | The project's departmental-agree monetised benefits at 22/23-Q4 is 826m. The programmes benefits profile has remained static compared to last reporting period. As the benefits of digital signalling start to materialise on the Northern City Line, the first area to transition to ETCS, the programme will begin monitoring there accrual in earnest over the coming year. To note, the monetised benefits figure is the discounted Net Present Benefit as set out in the FBC, and therefore not comparable to the Nominal whole life costs. This will be updated in the Q2 submission to IPA. | DFT_0038_1920-Q4
East Coast Mainline Programme | DFT | Infrastructure and Construction | The East Coast Main Line Enhancement Programme is a collection of track and power upgrade schemes between London King's Cross and Edinburgh to increase capacity and reduce journey times. The Programme has enabled the East Coast franchise to introduce a new fleet of Intercity Express trains. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Although the majority of the necessary infrastructure upgrades have now been completed, the Programme's Amber rating reflects the challenging schedule for finalising the content of the new East Coast Main Line timetable, led by the Department's Passenger Services team, and securing the necessary approvals ahead of its introduction, which will not be before June 2024 . | 2014-04-01 | 2024-12-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-01. This is primarily due to the following factors. The power supply upgrades remain forecast to be completed by December 2024 but, with mitigations in place, the rail industry could introduce a new East Coast Main Line timetable from June 2024 to increase the number of passenger services and reduce journey times. The introduction of the new timetable is dependent upon agreement of the train service specification and funding for the operation of those services. | 15.1 | 79.49 | 426 | Programme costs in 2022/23 were significantly higher than the baseline because delays to the power supply upgrades led to costs moving from earlier years; total costs have not changed. The delays were principally due to the redesign work needed to satisfy a change in interface requirements from the electricity Distribution Network Operators and archaeological discoveries at a worksite near Berwick. | 1040 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1040m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1040m. This is primarily due to the following factors. The baseline whole life cost for the project has not changed and forecast costs remain within the funding range agreed with HM Treasury for the delivery of the Programme. | 2953 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2953m. The benefits baseline assumed that the new East Coast Main Line timetable would be introduced in May 2021 but, due to the impact of the pandemic on the rail industry's finances, its implementation has been deferred until June 2024 at the earliest. When the content of the new timetable and its date of introduction have been agreed, the passenger benefits achieved by the Programme will need to be reappraised. | DFT_0033_1819-Q1
East West Rail Configuration State 1 | DFT | Infrastructure and Construction | The East West Rail (EWR) scheme will create a rail link from Oxford to Cambridge, and is a key part of the governments ambition for the Oxford to Cambridge Arc. EWR is being delivered as a single integrated programme, structured around the phased introduction of services (Connection Stages). East West Rail Connection Stage 1 (CS1) delivers services between Oxford and Bletchley/Milton Keynes. CS1 will re-construct and upgrade a partly disused railway between Bicester and Bletchley. This will allow for the introduction of new passenger services, improving connectivity and journey times along the corridor to support transport and economic growth needs. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project is progressing well and is largely on budget and schedule to deliver services by 2025. The project has made good headway, mitigating certain delivery risks. Improved delivery integration with HS2 Ltd has enhanced the management of ongoing challenges for handover in the Calvert Integration area. Operational readiness for EWR CS1 remains a priority focus. In April 2023 the Department issued a Prior Information Notice that, subject to the outcome of negotiations, Chiltern will operate EWR CS1 Services. | 2011-11-30 | 2025-09-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-09-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-09-01. This is primarily due to the following factors. Overall, the schedule remains ambitious but achievable. Good progress has been made against important infrastructure milestones, including the completion of all earthworks and significant progress on track laying. The biggest risk to schedule remains the successful handover of the Calvert integration area from HS2 to EWR later this year. Important progress is being made to ensure operational readiness and the department is progressing negotiations with Chiltern at pace to formally appoint an operator for CS1 services. | 241.45 | 190.37 | -21 | The budget variance exceeds 5%. Updated planning assumptions have changed the forecast of spend, with some construction activity due to take place in later financial years than was assumed at FBC in December 2020. Whilst spend has been reforecast in this way the project continues to perform well against it's overall Anticipated Final Cost position | 1353 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1353m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1353m. This is primarily due to the following factors. The whole life costs for the project have align with the approved business case. These figures represent scheme delivery costs, rather than whole life costs. Project spend largely represents the capital expenditure to deliver infrastructure, through the East West Rail Alliance. Current forecasts show the Anticipated Final Costs to be lower than the Baseline Whole Life Cost and the programme is therefore looking to rebaseline appropriately. | 2649 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2649m. The programme has developed the appropriate benefits management documentation and processes. However, the final benefits realisation position is uncertain and dependent on post-Covid travel patterns, housing and job creation; as well as the realisation of later connection stages extending services to Bedford and Cambridge. Please note the 2,654m is a nominal value and has been uplifted for each year across the appraisal period. The 574m/740m are appraisal values in 2010 prices | DFT_0046_2021-Q2
East West Rail Connection Stage 2 & 3 | DFT | Infrastructure and Construction | The East West Rail (EWR) scheme will create a rail link from Oxford to Cambridge. The project is structured around the phased introduction of services (Connection Stages). East West Rail Connection Stage 2 (CS2) predominantly upgrade existing infrastructure (between Bletchley and Bedford) to allow services between Oxford and Bedford. East West Rail CS3 involves building a new line, between Bedford and Cambridge, to extend the railway and facilitate services from Oxford to Cambridge. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. Following a review of the programme, Government recommitted to East West Rail with the March 2023 Budget noting a public announcement on the route would be made in May 2023. Cross-government discussions are taking place how to support local authorities bringing forward plans for strategic economic development around stations on the route (c15m of funding was announced at Budget for this) to ensure benefits will be realised. The delivery programme is now being re-baselined with the aim for a Development Consent Order submission in 2025 with increased confidence in benefits delivery. | 2014-08-01 | 2030-10-09 | The project's end-date at 22/23-Q4 is 2030-10-09. This is primarily due to the following factors. This project is still in the concept and design stage. There remains a degree of uncertainty around the overall project schedule, until further work has been completed to refine delivery options and the projects scope and a funding profile agreed with HMT. More detailed information will be provided in subsequent iterations of the IPAs annual report and via project led public engagement in due course. | 162.26 | 49.72 | -69 | The budget variance exceeds 5%. Variance of anticipated spend is primarily due to a review of the schemes priority leading to slower progress than originally anticipated. | 3970 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 3970m. This is primarily due to the following factors. This project is still in the concept and design stage with important scope decisions yet to be made. The cost range is estimated at 4-7bn. More detailed information will be provided in subsequent iterations of the IPAs annual report, and the funding required will be determined via business case processes. | 10961 | The project's departmental-agree monetised benefits at 22/23-Q4 is 10961m. No annual return benefits narrative provided. EWR can unlock wider benefits (economic growth, jobs, housing). Final benefits realization remains uncertain. | DFT_0052_2122-Q1
Further Electrification of Midland Main Line (MML3) | DFT | Infrastructure and Construction | Electrification of the Midland Mainline from Wigston to Sheffield and Nottingham. The programme will enable the removal of diesel traction from the route (contributing to net carbon zero and air quality targets), and facilitates HS2 trains to serve the East Midlands and South Yorkshire | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (IPA rating). This is primarily due to the following factors. The development and design work is continuing well, and it is planned to seek implementation authority in 2024, lessons learned from the successful implementation of electrification on the route will ae being incorporated into the delivery plans. Uncertainty around the funding profile are importing cost and programme risk into the delivery plans. | 2022-01-21 | 2030-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. The delays to confirming the available funding profile have imported delays into the delivery programme. Network Rail are preparing a new project baseline at is expected that the completion date will be later than the current date of end December 2030 | 67 | 14 | -79 | Variance is as a result of the costs associated with the delivery of the route section between Market Harborough and Wigston being included in the MML KO1a project rather than MML3. | 1468 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1468m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1468m. This is primarily due to the following factors. Network Rail are revising the baseline for the project, cost pressure are expected relating to inflations and base costs, this will be updated during the next quarter reporting | 2591 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2591m. The project benefits are being reviewed, however there is not expected to be any significant change to the quantified benefits, however the profile of delivery may change commensurate with any revisions to the delivery programme | DFT_0039_2122-Q3
HS2 Phase 1 | DFT | Infrastructure and Construction | A new railway connecting the countrys biggest cities and economic regions enabling rebalancing and regional growth in the Midlands Engine and Northern Powerhouse - through a high capacity, high speed and low carbon transport solution. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. The Spring Budget required HS2 to rephase parts of Phase 1 to reduce expenditure over the next two years to help manage overall government expenditure whilst protecting the Old Oak Common to Birmingham Curzon Street section. HS2 Ltd has reported further cost pressures across Phase 1 which are currently being reviewed by HS2 Ltd's Board. Phase 1's delivery targets for cost and schedule will need to be amended to address these changes and to address excess inflation given costs continue to be measured in 2019 values. | 2009-01-14 | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Old Oak Common to Birmingham Curzon Street remains on track to deliver initial services between 2029 and 2033. Works continue to be progressed north of Birmingham but may need to be slowed if necessary to protect initial services. Work south of Old Oak Common including Euston has been paused and a revised schedule depends on when funding is reinstated. |  |  |  | The current forecast is within 5 per cent of budget. | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | WLC does not reflect the true up-front cost for HS2 so is not reported by DfT. The Target Cost for Phase One is 40.3bn, and the overall budget including Euston is 44.6bn. The HS2 budget is in 2019 terms and needs to be rebased to adjust for inflation. HS2 is experiencing high inflation, and HS2L has reported cost pressures, with its estimate at completion under review.On 9 March DfT committed to the delivery of HS2 between Old Oak Common and Birmingham Curzon Street but delayed other parts of Phase 1. DfT and HS2 Ltd are rescheduling delivery and reprofiling costs to protect vfm, but prolongation and delay costs have not been assessed, and will depend on when funding is available.DfT is committed to delivering services to Euston, and is working with HS2L on affordability to protect vfm, this includes investing in more mature designs and cost-effective delivery approaches. | 32850 | The project's departmental-agree monetised benefits at 22/23-Q4 is 32850m. The HS2 Programme tracks progress against its benefits baseline through quarterly reporting. This reporting is not monetised but uses natural measures to reflect whether the outcomes are being achieved. It continues to RAG rate Green overall in terms of the benefits being reported during design and construction. The work to reschedule delivery and reprofile costs will be reflected in revised benefits baselines. It is anticipated that benefits will be delayed rather than forfeited. | DFT_0040_2021-Q1
HS2 Phase 2a | DFT | Infrastructure and Construction | A new railway connecting the countrys biggest cities and economic regions enabling rebalancing and regional growth in the Midlands Engine and Northern Powerhouse - through a high capacity, high speed and low carbon transport solution. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Red. This is primarily due to the following factors. The Spring Budget confirmed that the Government is committed to delivering HS2 Phase 2a between Birmingham and Crewe. However, due to significant inflationary pressures and increased project costs, this section will be rephased by two years, with an aim to deliver high-speed services to Crewe and the North West as soon as possible after accounting for the delay in construction. The Department is continuing to work through the cost and programme implications of this rephasing decision with HS2 Ltd, and further details, including a new delivery-into-service date range for HS2 Phase 2a, will be confirmed in due course. | 2014-03-17 | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | The project's end-date at 22/23-Q4 is awaiting reforecasting. Following the Written Ministerial Statement on 9 March and the Budget Statement on 15 March the department is resetting the Phase 2a programme. The schedule range of 2030-2034 was formally approved in June 2021, and an updated Delivery into Service range reflecting the 2-year rephasing of Phase 2a construction will be confirmed in due course. | 339.62 | 339.62 | 0 | The current forecast is within 5 per cent of budget. | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | The Department does not report on WLC as it does not reflect the true up-front cost for building HS2. The total capital forecast is 5.2-7.2bn (2019 prices). The current WLC cost status for Phase 2a is displayed as 'zero'.Along with the wider UK economy, HS2 is experiencing high levels of inflation. Its budget remains in 2019 terms and needs to be rebased to adjust for observed inflation.The Ministerial Statement on 9 March by the Secretary of State for Transport committed to delivering HS2 Phase 2a between Birmingham and Crewe. In light of inflationary pressure and increased cost, we are re-phasing construction by two years with an aim to deliver high-speed services to Crewe and the North West as soon as possible. DfT is working with HS2 Ltd to reschedule delivery and reprofile costs for Phase 2a in a way that protects value for money so far as is possible. This wil nevertheless introduce additional prolongation and remobilisation costs. | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | DFT_0041_2021-Q1
HS2 Phase 2b Western Leg | DFT | Infrastructure and Construction | A new railway connecting the countrys biggest cities and economic regions enabling rebalancing and regional growth in the Midlands Engine and Northern Powerhouse - through a high capacity, high speed and low carbon transport solution. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Spring Budget confirmed that the Government will continue to take the High Speed Rail (Crewe Manchester) Bill through Parliament, and the Crewe-to-Manchester section will also form the foundations for improved rail services in the North through Northern Powerhouse Rail. | 2016-11-27 | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained scheduled to finish in the range of 2035-2041. This remains subject to reduce funding for preparatory work including Ground Investigation over the next two years and will be reassessed on Royal Assent, subject to the will of Parliament. | 207.3 | 207.3 | 0 | The current forecast is within 5 per cent of budget. | Exempt under Section 22 of the Freedom of Information Act 2000 (Information intended for future publication) | The Department does not report on WLC as it does not reflect the true up-front cost for building HS2. Following the removal of the Golborne link, the total estimated cost range for Phase 2b Western Leg (Crewe-Manchester) is 13bn - 19bn (2019 prices).Along with the wider UK economy, HS2 is experiencing high levels of inflation. Its budget remains in 2019 terms and needs to be rebased to adjust for observed inflation. | 7535 | The project's departmental-agree monetised benefits at 22/23-Q4 is 7535m. The HS2 Programme tracks progress against its benefits baseline through quarterly reporting. This reporting is not monetised but uses natural measures to reflect whether the outcomes are being achieved. It continues to RAG rate Green overall in terms of the benefits being reported during design and construction. The work to reschedule delivery and reprofile costs will be reflected in revised benefits baselines. It is anticipated that benefits will be delayed rather than forfeited. | DFT_0042_2021-Q1
Lower Thames Crossing | DFT | Infrastructure and Construction | The Lower Thames Crossing (LTC) is a proposed new expressway connecting Kent, Thurrock and Essex through twin-bored tunnels under the Thames. It will almost double the road capacity across the River Thames east of London and is the largest single road investment project in the UK since the M25 was completed more than 30 years ago. As a vital part of the UKs transport infrastructure, it will act as a catalyst for national and local economic growth. Building a reliable, modern new road that is fit for the future will help connect the nations busiest ports to the distribution hubs in the North, Midlands and beyond. It will improve network resilience and the performance of the existing crossings at Dartford, transforming the regional and national road network. LTC will open up new markets for businesses and create tens of thousands of new jobs and hundreds of apprenticeships during its construction. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The key strategic risks remain mainly around the consenting process and loss of momentum. The current risk profile of the programme is being reviewed to understand the implications of the Ministerial Statement issued on the 9 March 2023 confirming government commitment to the Programme and that construction would be rephased by two years, against the current approved baseline given the wider fiscal pressures on capital investment from inflation.Compared to financial year 21/22-Q4, the programmes DCA remains at Amber due to the Ministerial Statement, pressures on capital investment from inflation, and the Development Consent Order | 2014-05-30 | 2032-03-10 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2029-05-31 to 2032-03-10. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2029-05-31 to 2032-03-10. This is primarily due to the following factors. The date is within the original range we expected. The written ministerial statement has increased the range to the upper end which has been included in the forecast. The Ministerial Statement issued on the 9 March 2023 confirmed government commitment to the Programme and that construction would be rephased by two years, against the current approved baseline given the wider fiscal pressures on capital investment from inflation. The project will continue to work through what the announcement means for the schedule and the project end date. | 129.3 | 169.3 | 31 | The budget variance is due to advancing the acquisition of Southern Valley Golf Course, Port of Tilbury Land and Pilgrims Lane lease. | 8309 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 6752m. to 8309m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 6752m. to 8309m. This is primarily due to the following factors. The cost increases are primarily linked to the Freeport changes, DCO delay, inflation and prolongation costs. This figure is is the Most Likely capex cost in outturn prices. | 4313 | The project's departmental-agree monetised benefits at 22/23-Q4 is 4313m. Work is ongoing to update the benefits following submission of the DCO to inform Government's final investment decision and following the Written Ministerial Statement on 9 March 2023, which confirmed that the construction of LTC would be re-phased by two years due to wider pressure on the RIS, driven by high inflation. Benefits are expressed in 2010 prices and values. | DFT_0022_1415-Q4
Midland Main Line Programme | DFT | Infrastructure and Construction | The Midland Main Line (MML) Programme was a package of works to provide new track and electrification between Bedford, Kettering and Corby, along with journey time improvements across the MML. This package was completed for the May 2021 timetable. Further work to extend new electrification from Kettering to Wigston, enhance the existing electrification from London to Bedford and provide additional power supply to allow new hybrid trains to run electrically from London to Wigston inclusive is underway. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Green (SRO rating). This is primarily due to the following factors. Key Output 1 of the project is now complete and is going through a formal close out process. Key Output 1a will not be reported as a GMPP project, and so the rating is Green as a complete project. | 2011-01-01 | 2024-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-31. This is primarily due to the following factors. The project is complete, with formal close out currently underway. Key Output 1a will be reported separately as a Tier 2 project. | 4.12 | 2.78 | -33 | The project remains within budget, with a small amount remaining for final close out activities. | 1421 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1671m. to 1421m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1671m. to 1421m. This is primarily due to the following factors. Key Output 1 of the project reflects the c1.4bn cost, and has been completed within budget. The reduction from the higher number reflects the removal of Key Output 1a from the report as this has gained new authority and scope with approvals in 2022, and will be reported separately as a Tier 2 project. | 1299 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1299m. Benefits have been realised in full | DFT_0027_1617-Q1
Midlands Rail Hub | DFT | Infrastructure and Construction | The Outline Business Case for Midlands Rail Hubs West and Central scope was received in November 2022, and it is progressing through assurance and governance to support a Decision to Design. Following the IPAs review in February 2023, we are working with Network Rail and Midlands Connect to ensure full separability of the programmes scope. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Midlands Rail Hub was subject to an IPA Gate 0 review in February 2023, and received an Amber rating. The review recommended clarifying the Departments objectives for investment, scope separability, resources, and governance. The project team is addressing the recommendations, and we intend to present the Decision to Design to the Investment Portfolio and Delivery Committee in June. | 2017-04-01 | 2033-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2033-06-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2033-06-30. This is primarily due to the following factors. The November 2022 OBC forecasts entry into service of Midlands Rail Hub in December 2030. While this may change during further development of the scheme, there is no reason at present why this cant be achieved. | 7.31 | 3.35 | -54 | The project is currently well within budget and there is no obvious reason why this will be exceeded. | 1563 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1563m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1563m. This is primarily due to the following factors. | 1817 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1817m. | DFT_0043_2021-Q2
Northern Powerhouse Rail (NPR) | DFT | Infrastructure and Construction | Northern Powerhouse Rail (NPR) is the Government's vision to transform rail connectivity by providing faster and more frequent services between the Norths key economic centres. NPR is aligned to the government's Integrated Rail Plan and, subject to ministerial agreement, will see route developments and upgrades between Liverpool to Manchester, Leeds, York, and Newcastle. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Strategic Outline Business Case (SOBC) continues to be revised to align to the Integrated Rail Plan (IRP) including updating the economic analysis underpinning the NPR Business Case. Due to the assurance of the economic analysis outputs taking longer than anticipated, the scheduled date for ministerial approval (Q4 FY 2022/23) has been impacted.A revised plan has been developed, which, subject to necessary approvals being received at each stage, will see the SOBC submitted to government for approval in Q2 FY 2023/24. Despite the delay to the original plan, ultimate delivery of the scheme as planned remains feasible, with additional uncertainty over actual target dates until the post-Autumn Statement re-baselining of the whole IRP portfolio is complete. | 2016-06-01 | 2045-01-01 | The project's end-date at 22/23-Q4 is 2045-01-01. This is primarily due to the following factors. End date aligns with recently published Integrated Rail Plan (IRP) report. Northern Powerhouse Rail Strategic Outline Business Case (SOBC) is being updated to align with the Integrated Rail Plan (IRP). | 39.1 | 30.5 | -22 | The budget variance exceeds 5%. Majority of underspend sits with Network Rail due to funding and remit being confirmed in Q1 of Financial Year 2022/23 which impacted Network Rail ability to mobilise and commence activity at the start of the Financial Year (22/23). | 17265 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 17265m. This is primarily due to the following factors. The figure provided is the capital cost (2019 prices) of building the NPR Core network in line with the Strategic Outline Business Case being prepared. This figure will be reviewed in Q1 2023/24 as it currently does not include operating costs, renewal costs, or the impact of the real cost of inflation. | 19453 | The project's departmental-agree monetised benefits at 22/23-Q4 is 19453m. The figure shown is based on early planning and is being updated as part of finalisation of the Strategic Outline Business Case. A revised figure will be provided in Q1 2023/24. | DFT_0141_2223-Q1
Rail Passenger Services | DFT | Government Transformation and Service Delivery | To secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended). The focus of this GMPP is the Passenger Services programme overall, centring on the transition to National Rail Contracts (NRCs). The NRCs are the precursor to the Passenger Services Contracts (PSCs), which will implement the vision in the Williams-Shapps rail reforms for the future relationship between the public and private sector. The GMPP return will also include relevant information on the PSC projects as these are set up. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the Infrastructure Project Authority's (IPA) Delivery Confidence Assessment rating at 22/23-Q4 imporoved from Red to Amber. This aligns with the recent IPA Gate 0 Assurance review with the same result. Some improvements have been made with the development of an interim commercial approach and the transition of TOCs to NRCs is largely complete, which has stabilised the operating market. Ministerial ambitions for the Rail Transformation Programme have been confirmed. While ongoing industrial action continues to impact rail services and disputes with trade unions remain, progress has been made with a pay deal secured with Network Rail RMT members and consequent calling off of March/April strike dates. However significant challenges such as the budgetary and resourcing position, as well as the complexities in delineating the Passenger Services Contract (PSC) schedule remain the key challenges faced by the programme. | 2020-03-23 | 2024-04-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-10-16 to 2024-04-01. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-10-16 to 2024-04-01. This is primarily due to the following factors. Rail Passenger Services National Rail Contract (NRC) programme is close to completion. NRC projects completed this financial year were Thameslink, Southern and Great Northern started in April 22, Great Western started in June 22 and East Midlands in October 22. The final NRC in Tranche 3, West Coast Partnership Direct Award (DA), has been retimed and is due to be completed in October 2023 having been agreed with the Secretary of State. On other Direct Award projects, the Transpennine Express NRC DA, Cross Country NRC DA and East West Rail Deed of Amendment projects are currently underway. FY23/24 Annual Business Planning process for DfT train operators has concluded. |  |  |  | The budget variance is inferior or equal to 5%. | 17510 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 14480m. to 17510m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 14480m. to 17510m. This is primarily due to the following factors. The reason for the variance between the 21/22 Q4 figure and the 22/23 Q4 figure is that the 22/23 baseline costs were not included in the Q4 21/22 report |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. | DFT_0050_2021-Q4
Rail Transformation Programme | DFT | Government Transformation and Service Delivery | In 2018, a deep-dive review into Britains railways was commissioned. The review found that the existing system is fragmented, complicated, and lacks a guiding focus on customers, coherent leadership, and strategic direction. In May 2021, the Government published the findings in the Plan for Rail White Paper and the Rail Transformation Programme was established. The Rail Transformation Programme will deliver a simpler and better railway for the people of Britain. Great British Railways (GBR) will be created, to bring track, train, and whole system finance under a single guiding mind' and tackle the fundamental inefficiency caused by the fragmentation of the railway system. It will re-energise the private sector to focus on reliability, performance, and efficiency, and create an environment for the private sector to play a bigger and better role in delivering innovation and efficiency. Fares, ticketing, and retail experience for the passenger will be modernised, and workforce reform will tackle outdated working practices. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme recently underwent a Gate 0 review, as a Strategic Assessment, which took a look at the programme context holistically with a focus on time, cost, quality and benefits factors. We are given an amber rating, recognising the progress made since our last return. We are re-setting the programme delivery strategy, and re-baselining following the current financial planning round. We are developing a more forward-leaning comms and engagement strategy to build a sense of shared ownership for the reforms. There is continuing strong support and vocal calls for reform across the rail sector and industry. | 2021-05-20 | 2025-01-04 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-01-04. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-01-04. This is primarily due to the following factors. The creation of Great British Railways (GBR) requires legislation and the schedule for GBR will be heavily dependent on this legislation. Ahead of legislation, to deliver early benefits the programme is simplifying and rolling out single leg pricing across the LNER network, trialling demand-based pricing to ensure passenger demand is more evenly spread between services and extending pay-as-you-go ticketing, as well as developing the Long Term Strategy for Rail, simplifying industry practices and exploring new opportunities for the private sector. |  |  |  | The challenging SR21 outcome for DfT rail set a difficult context for reform delivery, including increased risk of future service cuts and liklihood industrial action because of a tight cost-envelope for passenger services and ambitious workforce reforms. Removal of contingency across workforce reform in the SR due to savings/efficiencies commitments remains ambitious. RTP had a successful SR outcome with agreed funding for 80% of original bid, enabling us to progress the programme, although the settlement does reduce contingency and some discretionary elements of reforms so requires rescoping. We expect further clarity once the financial re-baselining exercise for the programme has been agreed. | 1961 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1961m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1961m. This is primarily due to the following factors. The challenging SR21 outcome for DfT rail set a difficult context for reform delivery, including increased risk of future service cuts and likelihood industrial action because of a tight cost-envelope for passenger services and ambitious workforce reforms. Removal of contingency across workforce reform in the SR due to savings/efficiencies commitments remains ambitious. RTP had a successful SR outcome with agreed funding for 80% of original bid, enabling us to progress the programme, although the settlement does reduce contingency and some discretionary elements of reforms so requires rescoping. We expect further clarity once the financial re-baselining exercise for the programme has been agreed. | 5889 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5889m. The benefits in the Plan for Rail have been collected into four benefits pillars: Customer: Improved passenger and freight customer experience Sector: The improvements to the sector to better improve its sustainability Society: Improvements that impact on the role that the railways plays in wider society including levelling-up Financial: A more financially sustainable railwayThe approach of benefits management on the programme has been adjusted to better represent the transformational nature of activities that are being undertaken. To do this we have undertaken a simplification of the structure so that all of the benefits on the programme will sit under the four pillars detailed above.The programme is in the process of developing a collection of performance indicators that will be used to monitor performance in achieving the benefits, allowing the programme to better manage the conflict between different benefits and disbenefits. The purpose of this is to also improve the level of non-financial benefits performance monitoring and also to set levels of benefits that should be met during the transformation period. | DFT_0020_2122-Q2
Rapid Charging Fund | DFT | Infrastructure and Construction | Upgrading connections to the electricity grid along motorways and major A roads to enable private sector delivery of rapid chargepoints, both to alleviate range anxiety in the short term and support mass market uptake of electric vehicles in the long term. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The IPA Confidence Assessment is Amber. This is primarily due to the complexity surrounding outstanding key policy decisions, the tight timeframe for delivery, and resource requirements. OZEV is continuing to work closely with our proposed delivery body, National Highways, on our delivery timelines, looking for potential areas of acceleration. Significant progress has been made with the RCF Pilot, which is expected to open for applications in Summer 2023 (subject to satisfactory review from the Subsidy Advice Unit in line with the Subsidy Control Act 2022). The pilot will allow for an iterate and learn approach to the main fund, and will help inform outstanding policy decisions, alongside outputs from a public consultation, which will be published Summer 2023 (subject ministerial approval). | 2020-11-25 | 2028-04-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-04-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-04-30. This is primarily due to the following factors. The project is on schedule for the project end date. | 23.5 | 23.24 | -1 | The GMPP project did not provide data | 975 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 975m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 975m. This is primarily due to the following factors. Current estimates on capital are based on advice from external consultants. The current demand model and capital costs estimates indicate that the budget is sufficient. Resource cost estimates have also been carried out by consultants. We will confirm costs for the Full Business Case based on further analysis and information from the market. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. Benefits will be confirmed as part of the Full Business Case | DFT_0054_2122-Q1
Transpennine Route Upgrade | DFT | Infrastructure and Construction | TRU is a major multi-billion-pound programme of railway improvements between Manchester, Huddersfield, Leeds and York. TRU will bring passengers more frequent, faster, greener trains, running on a better, cleaner, and more reliable railway. TRU will transform East-West travel across the North of England.It will include full electrification of the route, additional tracks, new digital signalling, and more capability to allow greater freight use. It is a key commitment in the governments 96bn integrated rail plan, published last year, which confirmed support for the TRU Programme. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. This is primarily due to the timing of publication of the proposals in the Integrated Rail Plan (IRP) which remained uncertain and were fundamental to confirm the final end state described in Option G (for programme elements transferred to Transpennine Route Upgrade from Northern Powerhouse Rail (NPR)). The IRP and Spending Review (SR) has now been resolved and the next Infrastructure and Projects Authority review will be April 2023. | 2017-07-01 | 2041-10-17 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2041-10-17. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2041-10-17. This is primarily due to the following factors. A rebaselined schedule will be provided as part of the PBC2 submission in Spring 2023. | 661.5 | 590 | -11 | The budget 612m budget set at SR21, since then the scope has matured significantly, and Northern Powerhouse Rail facilitation projects have been integrated. At the same time, significant efficiencies have been generated which have outpaced inflationary pressures to reduce overall project totals. The consequent resequencing and reforecasting of the project prior to its next major approval in 2023 has resulted in the variance shown. | 11453 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 9185m. to 11453m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 9185m. to 11453m. This is primarily due to the following factors. There has been no cost increase in the programme: the variance relates to the way TRU has been recorded in the GMPP return. The 9,185m forecast excluded two significant cost groups. At PBC1, the forecast included 1,667m of risk provision based on Reference Class Forecasting which was not profiled and so not included in the 9,185m; and 602m of Operator Costs which were also not profiled in Q4 of 2021/22. We will be receiving an updated assured estimate from Network Rail and Train Operator delivery partners in the next few weeks and this should lead to an updated forecast at Q1 2023/24. The whole life costs are nominal inflated values (AFC), as presented in PBC1 | 3088 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3088m. Benefits of the programme are wider public and economic benefits from faster and more reliable journeys, more journey opportunities and an improved environment from a shift of passenger and freight transport to rail, plus decarbonisation, including from electrification. The benefits are 2010 Present Values as presented in PBC1. | DFT_0037_1920-Q3
AI Labs | DHSC | Government Transformation and Service Delivery | The NHS AI Lab was set up as a research and development focused programme to accelerate the safe, ethical and effective adoption of AI in health and social care. Aiming towards the UK becoming a world leader for the development and use of AI-driven technologies to improve peoples health and wellbeing, delivering the most impactful technology to support our health and care system. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. The Programmes RAG rating remains at AMBER (despite continued positive progress on critical Projects). This is due to uncertainty over the future structure of the organisation and its impact on AI Lab funded posts. Work is underway on consultation, staff impact and Business Case extension to allow for a transition date of March 2025 | 2020-07-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-03-31. This is primarily due to the following factors. The current baseline end-date remains unchanged. However, a 12 month extension to 31/03/2025 is being requested to enabled sufficient time to complete delivery and evaluation due to delays impacting progress as originally forecast. | 38.03 | 38.03 | 0 | The budget variance is inferior or equal to 5%. Variance caused by delays against delivery of in flight programmes as well as organisational restructure impacting ability to launch new projects on time. However a re-profile has also been approved and will allow us to retain most of our underspend. The new profile will be formalised through the refreshed business case extension which is in progress. | 160 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 188m. to 160m. This is primarily due to the following factors. Baseline Whole Life Cost have reduced to due Departmental funding re-prioritisation. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. | DHSC_0068_2021-Q4
Digitising Social Care | DHSC | Government Transformation and Service Delivery | The Digitising Social Care Programme has the objective of 80% of CQC registered adult social care providers, and at least 80% of people in receipt of care, having a digital social care record by March 2024. The programme will also support local systems to test care technologies that address local priorities and will provide implementation and evaluation support to develop an evidence base to support the scaling of technologies where there are proven benefits. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. A second IPA Gateway 0 Assurance Review was carried out in March 2023. The programme received an Amber rating. The IPA Review Team determined that the programme objectives were ambitious but not unrealistic. The IPA Review Team highlighted a number of recommendations, that were accepted by the programme in full, and actions plans have been developed to support the moving forward of these recommendations at pace. | 2021-04-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. More than 50% of CQC registered adult social care providers have a digital social care record. The baseline position in December 2021 was 40%. The recommendations set out as part of the recent IPA Gateway 0 Assurance Review will support accelerated delivery against the programme objectives. | 459 | 456.91 | 0 | This forecast totals include the annual cost to the wider system associated with the adoption care technologies. This includes the costs associated with implementation such as dual running, releasing staff time for training and the time spent converting paper records to digital. This is reflected in our PBC and our economic model. | 2698 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 2698m. This is primarily due to the following factors. These forecast totals include the whole life costs to the wider system associated with the adoption care technologies. This includes the costs associated with implementation such as dual running, releasing staff time for training and the time spent converting paper records to digital. These costs also include license and hardware costs for 10 years which is beyond the lifecycle of the programme. This is reflected in our PBC and our economic model. | 12646 | The project's departmental-agree monetised benefits at 22/23-Q4 is 12646m. The project's departmental-agree monetised benefits at 22/23-Q4 is 12646m.The project's departmental-agree monetised benefits at 22/23-Q4 is 12646m.The project's departmental-agree monetised benefits at 22/23-Q4 is 12646m. More than 50% of CQC registered adult social care providers have a digital social care record. The baseline position in December 2021 was 40%. Digital social care records can improve the quality, safety and efficiency of care delivery. | DHSC_0096_2122-Q4
ESR Transformation Programme | DHSC | ICT | The Electronic Staff Record is a single workforce management tool for the NHS offering an end to end solution during NHS employment. ESR provides salary payments and other pay related remuneration to 1.8 million employees, circa 5% of the working population in England and Wales. The Programme will define and deliver the future transformation roadmap for the ESR service from August 2025 including technology, application and service design. The primary drivers are: - Expiry of the current contract for the provision of ESR in August 2025; - The end of premium support for the Oracle eBS software in 2033; - The need to transform the existing solution to provide a modernised digital service to end users coupled with the accurate and timely provision of workforce data. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The SRO has accepted the recommendations received as part of the Stage Gate 2 Review held in March 2022 and an action plan has been put in place to address the recommendations as required. | 2020-01-02 | 2031-02-28 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2031-02-28. This is primarily due to the following factors. The main driver for the project end date is the need to complete transformation and migration to the new workforce solution across all in-scope organisations before the expiry of the existing legacy product in 2033. | 12.19 | 6.47 | -47 | The programme has underspent in the 2022/23 financial year due to slippage in the programme schedule including approval of the OBC taking longer than planned, extension of the timeline for submission of Supplier Questionnaires in order to maximise the opportunity for supplier submissions and a commercial issue impacting on the issuing of the Invitation to Submit Initial Tenders. The impact to programme timelines have required significant reprofiling of budget assumptions. Work to reprofile costs for future years within the existing funding envelope has been undertaken. Forecasted figures for 23/24 have been updated accordingly. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 3449 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3449m. The project's departmental-agree monetised benefits at 22/23-Q4 is 3449m.The project's departmental-agree monetised benefits at 22/23-Q4 is 3449m.The project's departmental-agree monetised benefits at 22/23-Q4 is 3449m. Both cash releasing and non-cash releasing benefits are realised by user organisations and are broadly related to user experience, interoperability, and data insights. These are incremental benefits on top of the established benefits from the existing ESR service solution. | DHSC_0041_2122-Q3
Frontline Digitisation | DHSC | ICT | Our vision is a digitised health and care system where the health service and its users have the digital services and access to information they need to effectively manage and improve health and wellbeing. We are levelling up healthcare systems and providers to a baseline level of core digital capability, as set out in What Good Looks Like, which enables frontline clinical staff to make best use of digital technology to deliver care efficiently, effectively and safely, reducing variations, and improving quality and outcomes | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. Delivery confidence is red as a number of NHS trusts are reporting they are unlikely to be able to fully implement an Electronic Patient Record by March 2025. The Frontline Digitisation programme team is supporting each of these trusts to deliver as quickly as possible while maintaining the highest standards of patient care. | 2021-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. A revised business case to reflect a new programme end date of March 2026 in being prepared. The programme continues to work to the existing cost parameters, with budget being reprofiled to cover the additional year to March 2026, to ensure financial support is available when needed for trusts who are unable to deliver by March 2025. | 474.9 | 474.9 | 0 | The GMPP project did not provide data | 1982 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 2610m. to 1982m. This is primarily due to the following factors. FD Programme budget being reduced to support other NHS England priorities. | 29814 | The project's departmental-agree monetised benefits at 22/23-Q4 is 29814m. The project's departmental-agree monetised benefits at 22/23-Q4 is 29814m.The project's departmental-agree monetised benefits at 22/23-Q4 is 29814m.The project's departmental-agree monetised benefits at 22/23-Q4 is 29814m. Benefits will be realised through local projects via FD programme investment. Systems and trusts undertaking these projects will be expected to undertake local 'As Is' and 'To Be' mapping to clearly articulate the expected benefits and the change management steps needed to access and realise those benefits. Investments will only be made when a project is able to demonstrate a robust return on investment with an appropriate Management approach that ensures realisation. Investment will typically occur over the life of the Programme with benefit returns modelled over 10 years. Systems and trusts will be expected to report actual benefits, referenced against forecasts stated within their business case, these returns will be aggregated to produce overall programme benefit returns. | DHSC_0071_2122-Q1
GP IT Futures Programme | DHSC | ICT | The GP IT Futures programme has delivered a new commercial model to replace the previous General Practice Systems of Choice procurement framework, with the development of a new GP IT Futures capabilities and standards model, Digital Care Services catalogue and underpinning frameworks. This has enabled the NHS to shift the market to provide more flexible, responsive, interoperable and value for money solutions; and helped practices, Primary Care Networks and Integrated Care Systems easily access and deploy the right combination of accredited products and services at whatever scale best meets their needs. This evolving model will continue to drive innovation, competition and value, so clinicians and the wider workforce have systems that improve patient outcomes, reduce burdens and support fully integrated care. | Red |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (SRO rating) to Red (IPA rating). This is primarily due to the following factors. Following the IPA Gate 5 review at the beginning March 2023, the Programme has been in regular contact with the IPA. Action plans against each recommendation have been produced and these, along with outputs from a lessons learned exercise were shared with the IPA and DHSC on 23 March 2023. A formal programme closure report for internal governance has also been prepared. Engagement is continuing | 2016-09-01 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. Although formal closure of the GPIT Futures programme has not yet completed (and will be dependent on actions against the Gate 5 recommendations), the business case and associated funding concluded at the end of FY22/23. The enduring and related programme work has been defined within separate short form business cases and has been submitted for approval. These submissions are in line with the Digital Primary Care strategy and the allocated funding for FY23/24. The new business cases details the work objectives, outcomes, benefits and strategy. | 127.96 | 135.13 | 6 | The budget variance exceeds 5%. The delay in the go live for the new market entrants occured as onboarding of new entrants proved more complex than originally anticipated, and directly led to an overspend on NME & Adapters as the transformation element of the funding was not budgeted for in FY 22/23, but continued into that FY. | 448 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 448m. This is primarily due to the following factors. Programme outturn is 6.4m (5.6m Rev, 0.8m Cap) underspend against the approved baseline over the 7-year business case term. This represents an overall underspend of 1%. | 1441 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1441m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1441m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1441m.The project's departmental-agree monetised benefits at 22/23-Q4 is 1441m. In the FBC, it was forecast that the programme will enable the delivery of benefits in the order of c.1,400m which will be derived through: i.The availability and increasing use of patient facing services (PFS) which support digital primary care ambitions and reduce the administrative burden to general practice and enable self-care by patients.ii.The efficient use of effective, innovative, business requirements-aligned clinical IT systems both by general practice and, in future, by new care models as they become established.iii.Reductions in the administrative burden for care organisations by improved interoperability between care settings. The actual level of benefit realised by the programme were 1,009million , comprising 980.8million of Non-Cash Releasing Benefits and 28.3million of Societal Benefits. This level of benefit was achieved primarily through the continuity of clinical IT systems delivery that the programme enabled in successfully transitioning from GPSoC to the new DCS catalogue model. | DOH_0063_1819-Q3
Integrated Single Financial Environment | DHSC | ICT | The objective of the project is to procure and implement the next generation of the NHSE England group Integrated Single Financial Environment (ISFE) and associated financial services. The procurement phase of the project is now complete and a contract is in place with NHS Shared Business Services (NHS SBS). Implementation is underway for the managed service provision to commence in April 2024. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The has been no change in the DCA, which remains at amber. Steps have been taken to minimise delivery risk, such as adopting early implementation of activities where possible, running activities in parallel and adopting an agile approach, however there is limited contingency available in the plan should there be any slippage, hence the amber rating. | 2018-08-01 | 2024-10-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-10-31. This is primarily due to the following factors. There has been no change to the project end-date, which is 31 Oct 2024. | 6.7 | 5.23 | -22 | The budget variance exceeds 5%. The budget for delivery of the project was exceeded due to an increase in resource following critical recommendation from an IPA review. | 301 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 301m. This is primarily due to the following factors. The Baseline Whole Life Cost is based on submitted bid costs. | 37 | The project's departmental-agree monetised benefits at 22/23-Q4 is 37m. The project's departmental-agree monetised benefits at 22/23-Q4 is 37m.The project's departmental-agree monetised benefits at 22/23-Q4 is 37m.The project's departmental-agree monetised benefits at 22/23-Q4 is 37m. Monetised benefits have been updated to reflect the succesful bid submission. | DHSC_0067_2021-Q3
New Hospital Programme | DHSC | Infrastructure and Construction | The Government confirmed that 40 new hospitals will be built by 2030 and released 3.7bn of initial capital funding to support activity between April 2021 and March 2025. This includes 8 previously announced schemes. In addition, the Prime Minister announced an open competition for 8 further schemes to be built by 2030. This will mean 48 hospitals delivered by the end of the decade | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. | DHSC_0066_2021-Q2
PHE Science Hub | DHSC | Infrastructure and Construction | The UK Health Security Agency Science Hub Programme aims to create a health security campus to provide the UK's leading science centre of excellence. Re-providing and enhancing ageing facilities at Porton and Colindale to bring together expertise from world-leading academic and commercial institutions to protect the public's health security and reduce health inequalities. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. Ministers recognise the need for UKHSA to replace its ageing infrastructure to support the continued delivery of it's core mission to protect public health security. Given the scale of investment required, UKHSA is considering further alternative options that may be available, including investing in existing sites, in addition to the current Harlow plan. In the meantime the programme remains focused on validating designs and requirements; and re-framing delivery options, plans and spending approvals in line with further work needed ahead of the Programme Business Case (PBC) submission and approval. | 2013-06-28 | 2034-10-20 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2025-06-30 to 2034-10-20. This is primarily due to the following factors. The programme schedule has been extended in line with successive funding changes requiring activity to be prioritised and the majority of suppliers demobilised. Following steers from Ministers, the Programme Business Case will be developed further and the programme will be re-baselined. If PBC approval is gained in 2023/24 the completion date for the programme would likely now move out to beyond 2035. | 205.33 | 300.51 | 46 | The budget variance exceeds 5%. The data for the budget and forecast shown are based on figures provided in the June 2020 PBC which will be superseded. Successive changes to budgets have amended the schedule with consequential impact on forecasts. | 2656 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 2656m. This is primarily due to the following factors. Programme business case development, assurance and approvals planning will be re-set in line with the updated programme schedule and budget. The expected whole life cost will be re-baselined following approval of the Programme Business Case. | 8250 | The project's departmental-agree monetised benefits at 22/23-Q4 is 8250m. The project's departmental-agree monetised benefits at 22/23-Q4 is 8250m.The project's departmental-agree monetised benefits at 22/23-Q4 is 8250m.The project's departmental-agree monetised benefits at 22/23-Q4 is 8250m. Benefits included in the current case relate to Health Economic QALYs driven by the collaboration and consolidated science and health security capabilities on a single site. Cost savings generated from the programme are netted against operating costs in the case.Following further work on options, any changes to the programmes planned scope will require a refresh of the Benefits Narrative and review of the benefits being delivered. | DOH_0017_1112-Q1
18m+ Building Remediation Programme | DLUHC | Infrastructure and Construction | The overarching aim of the high-rise remediation programme is to bring all affected 18 metre plus buildings in England, up to the minimum life-safety standard quickly, completely, proportionately, and consistently, while ensuring that residents are considered throughout the remediation process, delivering value for money and pursuing those responsible for the cost of remediation. In 2023, the 18 metre plus programme, [Aluminium Composite Cladding (ACM) and the Building Safety Fund (BSF)], will combine into a single remediation portfolio, including the 11 to 18 metre buildings. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. In 2122-Q4 the ACM and BSF were reported separately with ACM being Green and BSF being Red. Now that the two have been combined into a single report, the DCA has no historic score to compare to.The programme team are aligned with the Infrastructure and Projects Authority (IPA) rating and continue to develop initiatives to deliver the objectives completely, proportionality, and consistently on behalf of the residents. In Jul-22, the Building Safety Fund programme scope changed to a risk based proportionate approach. The programme continues to develop its operating model to continue improving performance in line with its objectives. | 2019-05-09 | 2031-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-06-30 to 2031-03-31. This is primarily due to the following factors. The programme continues to deliver buildings through the pipeline and the scheduled forecast date for completion is Q2 2025 for the Aluminium Composite Cladding (ACM) project and FY30/31 for Building Safety Fund (BSF). The main contributing factor for ACM is the increase in buildings in scope from 428 to 490. For BSF we now have a more accurate-long term modelled forecast across the whole portfolio. | 634.1 | 739.81 | 17 | The budget variance exceeds 5%. The programmes in year budget variance is due to a higher spend than forecasted on the Building Safety Fund. This relates to a positive change, with a higher number of buildings achieving the financial milestones related to funding approval to completion, resulting in greater spend. The financial model has been re-designed to deliver a more robust and consistent 12 month forecast. In response to the increase in buildings and improved forecasting, the approved programme expenditure will increase appropriately, with HM Treasury approval sought through the single remediation full business case in financial year 23/24. | 4124 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 634m. to 4124m. This is primarily due to the following factors. This is largely due to the Private Sector Cladding Remediation Fund (PSCRF), Social Sector Cladding Remediation Fund (SSCRF), and the Building Safety Fund (BSF) programmes now being reported as a single GMPP programme (the Baseline Whole Life Cost used for comparison only relates to PSCRF and SSCRF). In addition, the expectation in 21/22 was that the BSF would have concluded by 26/27. The latest estimate, following the launch of the high-risk proportionate scope in Jun 22, covered in DLUHCs Single Remediation Full Business Case, is that the fund will conclude in 30/31, which has been reflected in the overall programme whole life cost. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. There are no monetised benefits for this programme. The programme will measure success against the objectives of the programme, which are: to bring all affected 18 metre plus buildings in England to the minimum life-safety standard quickly, completely, proportionately, and consistently, while ensuring that residents are considered throughout the remediation process, delivering value for money and pursuing those responsible for the cost of remediation. The benefits of this will ease the burden and drive mitigation of the risk to life and other major fire incidents, reduce the need for interim safety costs, support residents and leaseholders mental and physical wellbeing, and support the efficient functioning of the housing market and the wellbeing benefits of residents feeling safe from dangerous fires in their homes. | MHCLG_0002_1920-Q4
Affordable Homes Programme | DLUHC | Infrastructure and Construction | The Affordable Homes Programme (AHP) is one of the primary vehicles used by Government for the delivery of affordable housing in England. It allocates grant funding to Local Authorities (LAs) and Housing Associations (HAs) to help support the capital costs of developing affordable housing for rent or sale.The AHP operates with a budget of 11.5bn, delivering tens of thousands of homes across England for both rent and sale.Delivery of the programme is delegated to our delivery partners, Homes England (HE) and the Greater London Authority (GLA). Our delivery partners have full delegated responsibility to make spending and allocation decisions in line with their targets, agreed assessment criteria, and within predetermined delegation limits. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The programmes delivery confidence is currently rated as amber. This reflects the risk that the programme will be unable to deliver the commitments in the original business case because of changes in the wider economy (primarily high inflation), and pressures on the finances of social housing providers. In Quarter 4, the programme gained agreement, through a revised business case, to re-baseline the programmes delivery, spend profiles and final targets, with contracts with providers being renegotiated to align with that. This is due to complete in late Spring. | 2021-01-03 | 2029-04-30 | The project's end-date at 22/23-Q4 is 2029-04-30. This is primarily due to the following factors. In Quarter 4, the programme gained agreement to a revised business case for a re-baselined programme of delivery, and contracts with providers are being renegotiated to align to that new agreed position. Once completed, the programme expects to be back on track to deliver updated targets within the original schedule, and the Programme is set to be rated as green in delivery confidence. The re-negotiation of contracts is due to complete in late Spring. | 1895.17 | 1114.36 | -41 | The Affordable Homes Programme has delivered c. 4,400 fewer starts on site than originally forecast this year, leading to less capital spend than planned. This is primary due to changes in the wider economy and environment for social housing landlords impacting providers ability to fund new development. The programme is currently in the process of re-negotiating contracts with providers in order to address the additional costs, as a result of changes to the economy. It is expected that some of the lost delivery is re-forecast and planned in future years, but some may fall away completely. The re-negotiation of contracts is due to complete in late Spring. | 11583 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 11583m. This is primarily due to the following factors. Whole life costs for the programme have remained the same as last year, however overall delivery will fall short of the original business case. This is primarily due to high inflation impacting the costs of building new development. The grant assumptions made in 2020 will no longer support the level of delivery expected at the time. Since then, the programme has gained agreement for a revised, re-baselined business case and contracts with providers are being renegotiated to align with that. Once complete, the programme is expecting to be rated as green for delivery confidence. | 20796 | The project's departmental-agree monetised benefits at 22/23-Q4 is 20796m. The project's departmental-agree monetised benefits at 22/23-Q4 is 20796m. The estimated benefits arising from the Affordable Homes Programmes delivery in 2022/23 are valued at around 165 million. This is based on having delivered 4,000 homes in the 2022/23 financial year, the same figure assumed in the January baseline and business case assumptions on benefits per unit. The vast majority of the benefits delivered this financial year are wider societal benefits and are derived from the net private benefits of building new homes which the department monetises using the Land Value Uplift (LVU) framework, as per DLUHCs appraisal guide. | DLUHC_0138_2223-Q1
Digital Planning Programme | DLUHC | Government Transformation and Service Delivery | The planning system should deliver the things that communities need, making places liveable, sustainable, and beautiful. Communities should trust the planning system and have the ability to engage with what gets built, where. The system needs to be faster, more efficient and more certain, making it clearer to citizens, communities, and developers what the rules and permissions are, and enable a better conversation about the inherent trade-offs involved in deciding what land is allocated and what is built. The Digital Planning Programme will enable a modern and efficient 21st century planning system. The programmes four key interventions will shift a semi analogue system, based on documents, to one that is data-driven, standards based, and powered by modern user centred products and services. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Infrastructure and Projects Authority (IPA) Gateway 2 review took place in September 2022 and resulted in the disaggregation of the planning reform programme. Digital Planning was classified as a GMPP programme in its own right. The Digital Planning Programme was given an amber delivery confidence rating, with the review team endorsing a portfolio approach to the planning reforms. In response to the IPA recommendations and Accounting Officer (AO) assurance review, which took place in October 2022, the programme developed an action plan to take forward the recommendations, with a particular focus on the digital planning adoption strategy. The immediate priorities for the programme remain focussed around adoption, and the delivery of legislation (planning data clauses in the Levelling Up and Regeneration Bill). Both remain on track. | 2020-09-01 | 2027-12-31 | The project's end-date at 22/23-Q4 is 2027-12-31. This is primarily due to the following factors. The programme's end-date at 22/23-Q4 is Q3 2027. This is primarily due to the overall implementation of planning reform and legislation. We expect Royal Assent of the Levelling Up and Regeneration Bill to be reached later this year. Thereafter, there will be a period for secondary legislation and regulations to be laid. There will be a transition period where new style local plans are delivered and adopted. | 21.8 | 19.8 | -9 | Delays to awarding technical support contracts delayed spending in FY22/23 by several months (-2.3m). Part of this underspend (+0.3m) was utilised by providing additional support to Local Planning Authorities for digital citizen engagement projects. | 150 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 150m. This is primarily due to the following factors. The Digital Planning Programme whole life costs cover funding for planning software adoption and development by Local Planning Authorities, and the technical support provided by delivery partners for development and hosting of a planning data platform. Additionally, this includes costs for the adoption of digital local plans. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project's departmental-agree monetised benefits at 22/23-Q4 is 0m. Since the last year, the Digital Planning Programme has separated from wider planning reform. The forecast benefits now reflect the cash-releasing benefits from better data availability and accessibility, leading to cost savings incurred from producing a digital local plan, as well as non-cash-releasing benefits from software development reducing inefficiencies and, thus, time (in terms of hours spent processing and validating planning applications). These benefits were estimated using evidence from digital planning pilots. Further monetisable benefits, such as those for digital citizen engagement, will be identified through the monitoring and evaluation of the programme. | DLUHC_0181_2223-Q3
Electoral Integrity | DLUHC | Government Transformation and Service Delivery | The Electoral Integrity Programme is implementing changes arising from the Elections Act. The Elections Act makes changes to the administration and conduct of elections, including provision designed to strengthen the integrity of the electoral process. Areas where changes are made are: overseas electors; voting and candidacy rights of EU citizens; the designation of a strategy and policy statement for the Electoral Commission; the membership of the Speaker's Committee; the Electoral Commission's functions in relation to criminal proceedings; financial information to be provided by a political party on applying for registration; for preventing a person being registered as a political party and being a recognised non-party campaigner at the same time; regulation of expenditure for political purposes; disqualification of offenders of holding elective offices; and information to be included in electronic campaigning material. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. The programme is addressing the issues identified in the report generated by the Infrastructure and Projects Authority (IPA) Review team following its February 2023 assessment of the programme. Progress made in completing the IPA review recommendations is tracked by the programme's Audit and Approvals Group, and by the Programme Board. | 2017-01-11 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-12-31 to 2025-03-31. This is primarily due to the following factors. The programme will incrementally deliver the business changes arising from the new legislation for use in elections held in May 2023 and May 2024. The programme will continue through to March 2025, to implement changes to EU citizens voting and candidacy rights, and to monitor the realisation of its outcomes. | 38 | 34 | -11 | The budget variance exceeds 5%. Programme headcount and staff costs in 2022/23 were lower than planned for in the programmes budget. | 417 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 145m. to 417m. This is primarily due to the following factors. The baseline whole life cost declared at the end of FY 2021/22 did not include ongoing post-programme running costs and was re-baselined. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. At this stage, the target benefits for the programme are qualitative (non-monetised) only. High-level non-monetised programme benefits are: 1) To reduce opportunities for electoral fraud 2) To increase public trust in the democratic process 3) To remove barriers to participation in the democratic process 4) To improve the efficiency of running effective elections | CO_0025_2021-Q3
Freeports | DLUHC | Infrastructure and Construction | In March 2021, the Chancellor announced 8 Freeport locations in England: East Midlands, Felixstowe & Harwich (Freeport East), Humber, Liverpool City Region, Plymouth & South Devon, Solent, Teesside and Thames. 7 of the 8 English Freeports have now received final government approvals and, subject to the delivery of agreed milestones, will receive a share of 200m over the coming years. This is in addition to a generous package of tax reliefs for businesses investing in Freeport areas, full local retention of business rates, and a range of support from government. Two Scottish Green Freeport locations were announced on 13/01/23 and two Welsh Freeport locations were announced on 22/03/23, following fair, open competitive processes as outlined in the bidding prospectuses. The Scottish and Welsh Freeports are now progressing through the business case process and are expected to move into the Delivery phase in summer 2024. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. This is a complex programme working to challenging deadlines and requires robust monitoring and collaboration from multiple government departments. Since then, the programme has made significant delivery progress, with7 out of 8 English Freeports now fully approved and up-and-running and the final one expected later in 2023. The responses to the previous Project Assessment Review were provided to the IPA ahead of a Stage Gate 0 assurance review in May 2023. | 2019-02-08 | 2027-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-12-31. This is primarily due to the following factors. The Freeports policy is complex and diverse with many technical aspects that need to be addressed prior to a site becoming operational. The English Freeports are moving into the delivery phase with 7 out of the 8 full Business Cases approved. The remaining Full Business Case is expected to be approved later in 2023 when the customs site becomes operational. Two Scottish Green Freeport locations and two Welsh Freeport locations have been selected following fair, open competitive processes, as outlined in the bidding prospectuses. The Scottish and Welsh Freeports are now progressing through the business case process and are expected to move into the Delivery phase in summer 2024. The project end date of 31/12/2027 refers only to the seed funding component of the Freeports programme; other elements are subject to different timeframes.We remain committed to bringing the Freeports policy to Northern Ireland, and discussions continue. | 76.65 | 42.65 | -44 | The initial profiles submitted at spending review were based on estimates. These are being revised once all Freeport Full Business Cases are approved. 7 of the 8 English Freeports have now received final government approvals. The final Full Business Case is due to be approved in later in 2023 once the customs site designation is complete.The revised business cases meant some spending profiles have been moved further back into the next financial year. | 226 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 225m. to 226m. This is primarily due to the following factors. The capital expenditure was agreed in the Spending Review.It was agreed 25 million seed funding per Freeport, 200 million in total for English Freeports. In addition to monitoring and evaluation and technical support for Freeports. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. There are currently no monetised benefits for this programme. Benefits will be realised once the programme completes in 2026. The programme will measure success against the objectives of the programme, which can be summarised as; - To increase in trade throughout through the designated Freeport areas. - To increase in investment within Freeport boundary area, surrounding area and nationally. - To increased number of jobs and average wages in deprived areas in and around the Freeport. - To increase in economic specialisation in activities high in Growth Value Added relative to the current makeup of the local economy. - To Increased local involvement and funding in Research and Development and innovation. - To Increased productivity in each target region, through increased capacity to absorb innovation. As benefits are delivered throughout the end of the lifecycle of the project, they will be monitored through evaluation strategy. | MHCLG_0008_2122-Q1
Grenfell Site and Programme | DLUHC | Infrastructure and Construction | The programme achieved a significant milestone when the Grenfell Tower Memorial Commission (GTMC) published their interim report in May 22. Safety works on the tower completed in Oct 22 (on time, to budget and scope). Active monitoring continues to track the rate of degradation within the tower. Secretary of State held a Town Hall event for Bereaved and Survivors in Mar 23 and a community event in May 23, achieving the highest level of engagement with the community so far. The GTMC are working towards producing a final report in Sep 23. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Current rating is Amber. The Secretary of State has not yet made a decision about the future of the tower to allow more time for engagement and therefore the DCA remains amber. The safety works on the site have completed and the tower is now fully propped. The vision for the future memorial is to be determined by the Grenfell Tower Memorial Commission. The GTMC are working towards a final report and design brief to be published in 2023 | 2019-07-15 | 2029-03-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2028-06-30 to 2029-03-30. This is primarily due to the following factors. - Secretary of State has entered a further round of engagement with bereaved, survivors and residents, delaying the decision on the tower.- Further engagement and intentional conversations surrounding the future of the tower will need to happen in the next round of engagement with Secretary of States approval - The Grenfell Tower Memorial Commissions timelines have been delayed from original plans due to several factors, including the resignation of co-chair Michael Lockwood and the need to increase engagement numbers on views for the memorial. This has meant the final report and design brief publication timelines have been pushed back further into 2023, impacting the overall schedule of the design competition and Royal Institute of British Architects (RIBA) stages to get towards the construction of the memorial. Using this agreed schedule for the memorial, the estimated end date for the project is now March 202 | 15.4 | 15.14 | -2 | The budget variance is inferior or equal to 5%. The programmes budget/forecast variance is mainly due to an underspend on Resource Departmental expenditure limit (RDEL). - RDEL: The programme has continued to replace contractors and consultants with civil servants, which, alongside the introduction of controls on recruitment, have primarily contributed towards the RDEL underspend. - Capital DEL: Following the completion of safety works on time and to budget, CDEL costs have become static to reflect the ongoing maintenance required on site, resulting in a very minor overspend against the revised budget. | 291 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 157m. to 291m. This is primarily due to the following factors. - The change in baseline whole life cost, compared to the previous period, is due to baselines being updated to reflect updates to the programmes Strategic Outline Case. The programmes budgeted whole life cost now covers the costs needed to deliver the responsibilities associated with ownership of the site until the land is prepared for future use determined by the Grenfell Tower Memorial Commission. Changes in 22/23 reflect the reduction in 22/23 budgets in line with the revised programme requirements due to the delay in deconstruction. - To date, HM Treasury have approved Full Business Case (FBC) phase 1 and a Programme Business Case (PBC) covering one year within phase 2. FBC phase 1 covered costs to carry out the final stage of the essential safety works, which concluded in October 2022, while PBC phase 2 covers essential site maintenance. Future business cases will be developed covering a range of scenarios and timelines associated with preparing the site for future use, and to cover the final phase of the programme, assumed to be construction of a memorial |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Due to the sensitivities of the programme, benefits are not tracked. | MHCLG_0001_1920-Q3
Housing Infrastructure Fund | DLUHC | Infrastructure and Construction | The Housing Infrastructure Fund is a 4.2bn major government programme which provides funding for infrastructure projects, which once built, will unlock housing capacity in areas of high housing demand. Through funding 124 infrastructure schemes in all regions of England, HIF is expected to unlock the construction of up to 300,000 homes. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. The programmes delivery confidence rating remained at RED, due to increasing inflationary pressures impacting costs and causing delays in delivery. Since the IPA Gate 0 review, work has focused on resetting programme management processes to improve delivery oversight and forecasting, through a Business Case reset, aiming to: - Maximise unlocked housing and infrastructure delivery, whilst being deliverable within time and cost constraints and within grant funding agreements. - Ensure the programme is on sustainable financial and delivery footing, through reprofiling the budget and noting the need for extended funding availability period. - Provide increased assurance on forecasting, contractual management and change control. - Improve programme and project level reporting, introducing monthly Forward Funding scheme reports to manage project level performance against baselines, aggregated for programme oversight. - Provide robust governance and decision-making methodology as schemes go into default, seek to remediate, or request a Material Change to address challenges faced | 2016-12-30 | 2028-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-03-31. This is primarily due to the following factors. Delayed delivery is primarily due to macro-economic factors impacting the sector. The pandemic, inflation, the war in Ukraine, and supply chain issues have led to additional pressures, with underspends predicted across the current spending period. The updated Business Case recognises these challenges and seeks to reprofile the budget. Time-extension decisions at a project level will be made case-by-case, and the programme will streamline decision-making to drive delivery. The Housing Infrastructure Fund (HIF) will boost resources with additional posts and third-party support within Homes England and DLUHC, to build adequate capacity and capability. The programmes end date is unchanged due to the reset through the business case, including changes to underlying cost/time assumptions; descoping projects getting them back on track or removing/withdrawing them from the programme. The team has implemented quarterly portfolio prioritisation reviews of projects, based on deliverability, value for money and strategic fit to inform decisions on change requests. | 1049.9 | 450.2 | -57 | The budget variance exceeds 5%. The funding drawn in year is lower than forecasted primarily due to the macro-economic factors described which have raised costs across the larger Forward Funding portfolio. In addition to this, contractor appetite, resourcing, and Local Authority capacity have contributed to delay in funding being drawn and spend being deferred into future years. | 4334 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 4334m. This is primarily due to the following factors. Diverted resources will be used to support better performing projects. The whole life cost reflects the natural shift of the programme level budgets against the mitigations that the HIF team has put into place, as projects progress in their lifecycle, shifting costs over time, and in some cases withdraw from the programme. Attrition is due to the withdrawal of one Forward Funding and three Marginal Viability Fund schemes, and the reduction of the resourcing expenditure in future years due to budgetary constraints. | 18400 | The project's departmental-agree monetised benefits at 22/23-Q4 is 18400m. The project's departmental-agree monetised benefits at 22/23-Q4 is 18400m. The current value of 18.4bn is the sum of the final moderated bids that was used to make the original project approvals, plus the removal of the costs and benefits associated with the schemes that were known to be withdrawing at the time it was last calculated (in 2021). The land value uplift estimates within the moderated bids for Forward Funding schemes were based on development appraisals undertaken at the time to support bids. Benefits are under review and have been outlined in the Business case reset. | MHCLG_0004_2021-Q4
Levelling Up Fund | DLUHC | Infrastructure and Construction | The Fund is jointly managed by HM Treasury (HMT), the Department for Levelling Up, Housing and Communities (DLUHC) and the Department for Transport (DfT). At 2020 Spending Review, HM Government committed 4 billion for the Levelling Up Fund for England, subsequently increasing this to 4.8 billion across the whole of the UK with a minimum of 800 million for Scotland, Wales, and Northern Ireland. Round 1 of the Fund supported 1.7 billion of successful projects while HMG announced 2.1 billion to support successful Round 2 projects. The Fund will invest in local infrastructure that has a visible impact, improving everyday life for people. Accordingly, the Fund will focus on three themes: smaller transport projects that make a genuine difference to local areas; town centre and high street regeneration; and support for maintaining and expanding the cultural and heritage assets. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Oversight systems have been established to provide delivery assurance, with the LUF monitoring and evaluation strategy published on 31 March 2022. MoUs have all been agreed with round 1 applicants. The third tranche of payments to round 1 projects, were made in January 2023 and the fourth round of reporting came back in February 2023. The next round of reporting is due in May 2023. The impact of inflation remains a key risk reported by local authorities which has and continues to impact on the timeline for delivery and spend. The departments will operate through their locally based teams to gain further insight into the delivery challenges. We have a 65m Resource Departmental Expenditure Limit (RDEL) package which will be deployed in the form of grant to enable Local Authorities to buy in additional capacity), training and commercial advisors to help unlock delivery challenges. Onboarding of round 2 projects is progressing. The next round of payments for round 1 and 2 projects will be made by the summer. | 2021-03-03 | 2026-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-03-31. This is primarily due to the following factors. The overall LUF programme to March 2026 is broadly on schedule (successful applicants are reporting that they will deliver LUF funding by March 2026), however within this, that timeline (between the start of the programme and March 2026) delivery and spend have slipped to the right. We are responding to that through close monitoring, performance management and the delivery of a 65m capacity support offer. | 537 | 328 | -39 | Our in-year total spends for 22/23 were below the baseline budget outlined in the LUF programme business case reflecting the challenging economic environment particularly the impact of cost inflation. We are supporting places by offering flexibility through a project adjustment request process to make sensible adjustments to the scope and phasing of projects to mitigate delivery challenges whilst also maintaining value for money. We have also agreed a 65million package of support for local authorities, to help ensure they have the necessary capacity and capability to deliver their projects. | 4800 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 4800m. This is primarily due to the following factors. No Change. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Given the wide-scope of projects being funded by LUF, we expect benefits to be seen in the form of: - improvements to high streets and outdoor spaces being made cleaner and more attractive. - refurbishment of permanent facilities which may produce economic benefits for cultural-regeneration based projects but expect benefits to be highly localised. - improvements to local amenities are expected to see direct employment benefits. - physical regeneration of public spaces and buildings, and new cultural assets might have important quality of life impacts for residents by, for example, improving accessibility, encouraging outdoor activity and access to green spaces, increasing footfall and attracting new businesses or reducing social isolation. - transport schemes will see increased connectivity, as well as potential housing benefits or wellbeing benefits from improved connectivity. Monetised Benefits will be calculated once we receive initial output and outcome data from the monitoring forms returned by grant recipients for the quarter one of the financial year 2023 2024 | MHCLG_0017_2122-Q2
Levelling Up Home Building Fund | DLUHC | Infrastructure and Construction | The Levelling Up Home Building Fund will support small and medium sized housebuilders and residential development lenders to diversify and build resilience in the housing market, foster innovation including Modern Methods of Construction and leverage greater private investment into housebuilding. Funding is provided on a recoverable basis through loans or equity into partnership arrangements. This will help create an environment where prospective new entrants, including institutional investors, feel confident and supported to enter the residential sector and existing operators are able to increase their resilience and develop a trading record that will assist them in scaling up their businesses successfully. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The programmes delivery confidence assessment has not yet been assessed by the IPA given this is the first year of operation but has been rated at Amber by the funds Senior Responsible Officer. This reflects the impact of the turbulent economic conditions, during the last financial year (22/23), on the demand for finance by small and medium sized developers (also known as SMEs). Evidence from the market resulted in hesitance to commence and progress new schemes given the economic uncertainty and take-up for funding consequently fell short of original forecasts. However, there has been some level of improvement in market conditions since the new year and additional measures are ongoing or being considered to support delivery and SME developers over the life of the programme | 2020-11-25 | 2031-03-31 | The project's end-date at 22/23-Q4 is 2031-03-31. This is primarily due to the following factors. The programme remains on schedule for completion by March 2031, being the date by which loans or investments funded under the programme should be realised and/or repaid. | 273 | 120 | -56 | The variance to budget exceeds 5% due to the economic challenges for small and medium sized developers arising over the course of the financial year. These included inflationary and supply chain pressures arising following the reopening of the global economy post pandemic, later compounded by rising interest rates, tightening liquidity conditions and weaker consumer demand. This led to a decline in the appetite for developers and investors to acquire and/or develop new sites, with a consequent impact on the demand for development finance and investment. | 2206 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 2206m. This is primarily due to the following factors. There has been no change to the Baseline Whole Life Cost over the course of the year. | 842 | The project's departmental-agree monetised benefits at 22/23-Q4 is 842m. The project's departmental-agree monetised benefits at 22/23-Q4 is 842m. In addition to the receipts due back from the investment, there are lifetime benefits of the programme, these are based on estimating the social value delivered by the additional housing unlocked by the programme. These have fallen slightly; this is driven by changes to the estimate of Net Present Social Value (NPSV). The primary monetised benefit is the Land Value Uplift (LVU) from a change in productive use of the land towards housing which acts as a proxy of the welfare gain enjoyed by new residents. | DLUHC_0135_2223-Q1
Towns Fund | DLUHC | Infrastructure and Construction | The 3.6bn Towns Fund is made up of the Town Deals programme and the Future High Streets Fund (FHSF) competition. The Town Deals programme aims to regenerate towns and deliver long-term economic and productivity growth. This is through investments in urban regeneration, digital and physical connectivity, skills, heritage and enterprise infrastructure. The Future High Streets Fund competition aims to renew and reshape town centres and high streets in a way that improves experience, drives growth and ensures future sustainability. 101 Towns were selected for Town Deals, with 72 places successful through the FHSF competition. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. 101 places have been offered a Town Deal, committing over 2.35 billion, including the accelerated funding. All towns are moving into delivery, after submitting their Summary Documents and drawing down initial funding. To date we have paid out 751m to towns. The Future High Streets Fund has allocated 72 places a share of over 830m. All 72 places are now in delivery and a total of 517m has been paid through the FHSF to deliver agreed projects. Following the IPAs Towns Fund gate zero review in October 2022, the Towns Fund continues to implement the nine recommendations. This includes a full review of the programme risk register and development of a stakeholder engagement plan. Our 6-monthly performance reports, last received in December 2022, indicated that 25% of projects are experiencing delays in delivery, primarily due to rising project costs and supply chain issues. To mitigate, we have a change mechanism for projects in delivery to allow flexibility for places to amend their original plans. | 2018-12-01 | 2026-03-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-03-30. This is primarily due to the following factors. The Towns Fund is due to conclude in 25/26 for Towns Deals and 23/24 for the Future High Streets Fund. 101 Town Deals were offered to all places that were invited to submit proposals as part of the Towns Fund, committing over 2.35 billion, including the accelerated funding provided to towns. To date, we have paid out 751m to towns. The first Town Deal project was officially opened in October 2021: Norwich's new Digi-tech Factory. The Future High Streets Fund has allocated 72 places a share of over 830 million, as part of the 3.6bn Towns Fund. All 72 places are in delivery and are reporting on a 6-monthly basis to provide detail on project delivery progress. To date, a total of 517m has been paid to the 72 FHSF places to deliver agreed projects. | 1011.3 | 821.6 | -19 | The budget variance exceeds 5%. Our in-year total spends for 22/23 was below the original baseline budget as set through Departmental business planning. This is primarily due to the Town Deal summary documents that were not submitted as forecast, causing programme expenditure to slip into future years. Inflationary pressures and an uncertain economic climate have also contributed to financial slippage for Town Deals and Future High Streets Fund (FHSF) places, as they seek to reprioritise projects through the Project Adjustment Request mechanism. | 3104 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 3446m. to 3104m. This is primarily due to the following factors. Towns Fund totals 3.6bn. However, since the original announcement, 100m was allocated to Freeports and 300m to the Levelling Up Fund. 100m of funding was allocated to Heritage High Streets bringing our baseline whole life costs down to c 3.1bn. | 9878 | The project's departmental-agree monetised benefits at 22/23-Q4 is 9878m. The project's departmental-agree monetised benefits at 22/23-Q4 is 9878m. The Towns Fund programme, comprising of Town Deals and Future High Streets Fund, will provide monetised benefits primarily through the delivery of regeneration, skills and enterprise infrastructure, transport connectivity, and digital connectivity projects. Forecasted benefits have been calculated based upon the initial benefit cost ratios (BCRs) set out in the Towns Fund and FHSF economic business cases. Benefits realisation planning will be undertaken in FY 23/24, providing a more accurate projection of the anticipated benefits. | MHCLG_0007_2122-Q1
UK Holocaust Memorial and Learning Centre | DLUHC | Infrastructure and Construction | The programme aims to build a striking new memorial to the Holocaust in Victoria Tower Gardens in Westminster to honour the six million Jewish men, women and children that were murdered during the Holocaust, as well as other victims of Nazi persecution. A Learning Centre will be located with the memorial to explore the British relationship to the Holocaust including the role of the British Parliament and democratic institutions. |  | Red | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Red (SRO rating). This is primarily due to the following factors. The Holocaust Memorial Bill was introduced on the 23 February 2023 to remove the statutory obstacle to planning and is proceeding through Parliament. The nominated Minister will need to retake the planning decision. The DLUHC Permanent Secretary wrote to the Secretary of State, who in return issued a ministerial direction that instructs the Permanent Secretary to continue to authorise expenditure as required on the Holocaust Memorial and Learning Centre programme, ahead of Royal Assent for the Holocaust Memorial Bill and the activation of the spending power contained within it. A revised Full Business Case went back to the DLUHC Investment Sub-Committee requesting an increased budget and contingency due to delays and construction inflation. The Accounting Officer (AO) assessment was published in August 2022, and a revised version is due to be published in 2023. | 2015-01-27 | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | The programme schedule has slipped due to the continuing planning process. We need the UK Holocaust Memorial Bill to receive Royal Assent and the nominated Minister to retake the planning decision, to allow the programme schedule to be defined. Once we are in a position to award construction contracts, we will work with the selected suppliers to identify any opportunities to reduce the construction timetable. | 23.1 | 2.24 | -90 | The budget variance exceeds 5%. The underspend is a result of the programme being unable to move into the construction phase as planned, due to the overturning of the planning decision in April 2022, with costs being pushed into future years as a result. | 124 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 124m. This is primarily due to the following factors. The Baseline costs remain unchanged and are based on the Full Business Case (FBC). The baseline will be reset upon approval of the revised FBC which anticipates increased costs primarily due to programme delays and inflation. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. The programme does not have any monetised benefits. Non-monetised benefits will be that the UK has a suitable national Memorial to the Holocaust, a place where people can pay their respects, contemplate, think and offer prayers, which conveys the enormity of the Holocaust and its impact, and which appropriately represents the fate of other victims of Nazi persecution. The Learning Centre will provide a memorable experience that will give visitors an increased understanding of the importance of the Holocaust in British history, increased awareness of subsequent genocides, and increased awareness of antisemitism. | MHCLG_0005_2021-Q4
Carbon Storage Research Facility (CSRF) | DSIT | Infrastructure and Construction | In line with HMG Net Zero abatement targets and the need for effective and efficient mitigation as replacement technologies develop, Phase 1 of this project will provide an infrastructure option for an innovative, world-class, CO2 deep geological storage research facility in the UK that will improve scientific understanding, regulation, commercial performance and public awareness of this fast growing industry. There will be flexibility built in to allow future (phase 2) options to progress to further enhance, refine, inform and support process and technological innovation as the storage industry develops. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Delivery to time, cost and quality feasible by addressing actions and progressing the development of the project to OBC. Assessment remains Amber. There is much activity planned for the next quarter, including Science Committee, NERC Management Board and submission to the UKRI Infrastructure Fund, all of which will enhance the OBC activity and next round of approvals activity. | 2020-09-30 | 2028-09-30 | The project's end-date at 22/23-Q4 is 2028-09-30. This is primarily due to the following factors. Pre-Front End Engineering Design (FEED) activities continue until 2024. Feed activities progress into 2025 and detailed design expected to last 12 months. 24 months construction have been allowed for from 2026-2028. It is anticipated planning and permitting will take considerable time, however float has been built into the programme to achieve completion in 28/29. | 0.8 | 0.8 | 0 | The budget variance is inferior or equal to 5%. | 315 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 315m. This is primarily due to the following factors. Given early stage of CSRF, the current costings are subject to significant change depending on solution, location, final infrastructure configuration, and costs as the CCS market develops and current inflationary pressures take effect.Whole Life Cost review is being undertaken as part of the ongoing business case process. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Project at early stage. As the Outline Business Case is developed further the benefits will be monetised and included | BEIS_0169_2223-Q2
Matrix Cluster Transformation Programme | DSIT | Government Transformation and Service Delivery | The Matrix Programme seeks to implement the Government Shared Service Strategy for eight government departments by modernising and consolidating back-office systems and services. This will include delivery of a new shared business process service (BPS), a combined enterprise resource planning (ERP) system including ancillary technologies, and a change in ways of working for all users. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | BEIS_0079_2122-Q4
Met Office Supercomputing 2020+ Programme | DSIT | ICT | Delivering our future supercomputing capability through the procurement and installation of a replacement and increased supercomputing capacity. This includes storage, observation networks, post processing systems and services, tooling for data exploitation delivery and support resources throughout the investment lifetime, data centre hosting, networking security services and decommissioning . |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Procurement and approval phase are complete and we are now in the delivery phase of the Programme. IPA actions have been completed | 2018-01-01 | 2032-08-11 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2032-08-11. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2032-08-11. This is primarily due to the following factors. We have experienced supplier delays which had delayed our key implementation milestones, this was due to supply chain issues on behalf of the supplier and their sub contractors. A re-planning exercise is currently being completed with the supplier and should conclude by the end of April. The project end date remains the same | 191.09 | 48.24 | -75 | The Programme is under spent this year as delays to implementation have caused key milestones and subsequent payments to move into later years. | 1242 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1242m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1242m. This is primarily due to the following factors. Whole life baseline costs remain the unchanged, but due to supplier delays we are showing a reduction in the forecast as costs are re profiled. | 17874 | The project's departmental-agree monetised benefits at 22/23-Q4 is 17874m. Benefits forecast has been amended primarily based on the delays to implementation. | BEIS_0005_1920-Q4
New Polar Research Vessel | DSIT | Infrastructure and Construction | Royal Research Ship Sir David Attenborough will replace two existing polar research/supply vessels with one dual purpose ship which planned to save 102m over 30 years |  | Green | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Green. This is primarily due to the following factors. Programme is now into closure phase and all actions have been addressed within BAU | 2014-05-01 | 2022-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2022-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2022-12-31. This is primarily due to the following factors. Programme is now into closure phase. and remains on track to close during 2023. |  |  |  | Please input data on table 9.01 and 9.02. Project spend has stopped this is now a BAU activity. | 1420 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1420m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1420m. This is primarily due to the following factors. The whole life costs represents costs until 2043/44. These costs include the project costs until closure and recurring Antarctic Partition and Logistics infrastructure budget costs. | 3170 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3170m. Project Benefits are being monitored as part of the project closure and will continue in operational phase. | BIS_0014_1415-Q3
Open Networks Programme | DSIT | Infrastructure and Construction | The Open Networks Research and Development (R&D) Fund is the 250 million government supported programme to deliver upon the UKs 5G Supply Chain Diversification Strategy. The Open Networks R&D Fund aims to accelerate the development and deployment of open interface architectures, such as Open radio access network (RAN). Central to the Open Networks R&D Fund is our ambition to: - accelerate open-interface products and solutions - ensuring they are truly interoperable, performant, and sustainable to support our long-term vision for a more open and innovative telecoms market. - incentivise and derisk accelerated deployment in the UK - to encourage and accelerate network operators to adopt and deploy open network solutions. - develop an internationally recognised UK telecoms ecosystem - positioning the UK as a leading global market and focal point for research into open network technology. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Programme was reviewed as 'AMBER' in the Gate 0 review conducted in January 2022. Work has been undertaken to clearly outline the Open Networks Programme, with all competitions now launched and a number of projects live and in delivery. The team also works to closely manage risks around underspend and risks impacting timelines/benefits realisation. | 2021-09-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The Open Networks Programme is scheduled to run until 31 March 2025, with all project scheduled to close on or before this date. The team is working to mitigate the risk around retaining resource to this date, acknowledging that the 'hard stop' date for the end of the Programme also requires careful planning to ensure all closure activities are carried out in a controlled. timely manner. | 81.7 | 68 | -17 | We have surrendered some of our funding back to HM Treasury due to projects not starting work as soon as had been anticipated in the original Spending Review bid. We expect our spend to be within 1% of our new 63.1m Diversification budget at year end. | 325 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 325m. This is primarily due to the following factors. Since 1 April 2022 the programme has spent combined RES-del and CAP-del 65.6m. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. The Open Radio Access Network (RAN) specific benefits relate to the direct benefit of increasing the adoption of Open RAN technology and number of Open RAN vendors, including competition benefits, cost efficiencies and ecosystem benefits. Programme success measures have been approved and signed off by the programme SRO and a baselining study has been completed. The success measures have taken into consideration the direct impact of the programme based on the theory of change and logic model, as well as the wider Diversification strategic objectives. The programme team is currently commissioning an initial evaluation of the Programme that is due to report in March 2024. | DCMS_0107_2223-Q1
Project Gigabit | DSIT | Infrastructure and Construction | The UK Gigabit Programme (Project Gigabit) will deliver subsidised gigabit-capable broadband to hard to reach areas of the UK that would otherwise have been left behind by broadband network providers in their commercial rollout plans. There will be local, regional and cross-regional contracts available for broadband network providers of all sizes to bid for, managed through close working relationships with local authorities and the devolved administrations. This approach will be complemented by vouchers, hubs, gigabit-capable Superfast contracts and barrier busting measures to improve pace and flexibility of delivery. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. Project Gigabit has made good progress since the last IPA review, with the programme continuing to align to its time, cost and scope expectations, as set out in the business case. All recommendations from the previous gate 0 were acknowledged and actioned appropriately. Some areas for further improvement include seeking commercial support from the Cabinet Office to ensure that competition can be demonstrated for each procurement, and introducing a formal learning from experience regime to build on lessons learnt and pilot activity for the benefit of future Gigabit delivery activity. | 2021-04-01 | 2030-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. There is no deviation to the schedule. | 198.1 | 79.1 | -60 | The budget variance exceeds 5%. The budget allocated for Project Gigabit (Capital) in 2022/23 totalled 164.3m, with a post supps budget of 48.5m. The 2022/23 outturn is currently forecasted to be 42.4m. The main reason driving the underspend, since the Supplementary Estimate position, relates to Vouchers, where the average value of a voucher was lower than expected with lower than expected claims, and Gigabit Infrastructure Subsidy (GIS) procurements and subsequent mobilisation taking longer than expected. | 5112 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 5035m. to 5112m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 5035m. to 5112m. This is primarily due to the following factors. 8 (m) following the outcome of a Treasury Approval Point in January 2022. The forecast has since increased to 4,756.2 (m) based on updated delivery plans including the re-evaluation of assumptions including cost per premises and the timing of delivery. The result of these changes has still produced a forecast saving, with capital funding across the life of Project Gigabit being under 5bn. | 13509 | The project's departmental-agree monetised benefits at 22/23-Q4 is 13509m. Benefits have changed due to the new benefits model and changes to the premises delivery profile for Project Gigabit products. | DCMS_0019_2021-Q4
Shared Rural Network | DSIT | Infrastructure and Construction | The Shared Rural Network (SRN) programme is a 1 billion deal with the four Mobile Network Operators (MNOs) - EE, Three, Virgin Media O2, Vodafone - to deliver 4G coverage to 95% of UK landmass by the end of the programme, underpinned by spectrum obligations. The most significant coverage improvements will be in rural parts of Scotland, Northern Ireland and Wales, providing guaranteed coverage to 280,000 premises and 16,000 km of roads. The SRN programme is split between public and privately funded elements. In line with the six year capital funding period, the legally binding spectrum obligations for the SRN must be met by January 2027 and the programme will continue to deliver coverage improvements up to that point. The programme remains on track both the government and MNOs are confident that this combined coverage is expected to be delivered to 95% of UK geography by the end of 2025. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The SRN Programme team has resolved the majority of the recommendations including those deemed critical and essential in the November 2022 Gateway 0 Review. A number of recommendations focused on the relationship with the Home Office and the key commercial site share agreement between the Mobile Network Operators and the Home Office. Significant progress has been made in both these areas: The relationship with the Home Office is much stronger, underpinned with stronger Governance and improved information sharing between the organisations. The Programme has also actively worked on the recommendations including the need for the programme to keep evolving in preparation for its delivery phase; the team has increased PPM skills through successfully onboarding staff with extensive Project Delivery experience, with some joining from sponsorship and/or grant-distributing programmes. | 2020-03-11 | 2040-03-11 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2040-03-11. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2040-03-11. This is primarily due to the following factors. Correction of previously incorrect information: The current Grant Agreement notes funding up to and including FY 2040/41. The Transparency Notice was published on 11/03/2021, stating that SRN will start in February 2021 and is a 20 year programme. Publication of the Transparency Notice was delayed due to ongoing Brexit negotiations spilling over from 2020 to 2021. Funding could not be released until the Notice had been published and this in turn required changes to the Grant Agreement. | 22 | 7.5 | -66 | The budget variance exceeds 5%. Not applicable | 512 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 512m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 512m. This is primarily due to the following factors. Total expenditure (whole life costs) forecast aligns to the business case. | 1351 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1351m. The Shared Rural Network Programmes monetised benefits baseline and forecasts have been provided. These numbers were both generated for the Full Business Case in February 2020. Work to quantify the benefits involved a comprehensive literature review looking at the potential benefits of mobile coverage, before generating a shortlist of viable use cases and monetising them. Work is currently underway to improve our benefits predictions for the Shared Rural Network. | DCMS_0020_2122-Q1
Building Safety Regulator | DWP | Government Transformation and Service Delivery | The Building Safety Regulator, under One HSE, will lead the regulatory regime to protect people and places in all forms of buildings. The Building Safety Regulator will have three key functions: a) leading the implementation of the new, more stringent regulatory regime for higher risk residential buildings in scope; b) promoting competence among industry professionals and regulators who have key roles in delivering safe, high-performing buildings; c) oversight of the building safety and performance system. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. To address this rating the programme will continue to manage the associated delivery risks, working closely with our colleagues and stakeholders to implement the measures required. | 2021-03-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Over the last quarter the Programme has delivered against plan to support the secondary legislation programme, reviewed the business cases in line with conditions set by HMT and prepared for their submission for formal approval. The programme has also initiated delivery, through the digital development required to establish the public and internal systems and tools to operate BSR and the start of operational recruitment to establish the teams required to staff the BSR functions. | 32.02 | 21.99 | -31 | The bulk of the R-DEL variance relates to staff-related costs and reflects lower than expected staff costs across both payroll and contractors due to recruitment delays and a tight supply position in the specialist contractor market. Additional underspends are due to delayed engagement of the Digital Delivery partner, revisions to Insight and Communications activity plans and lower than expected training and recruitment costs. The C-DEL underspend is due to delayed BETA activity and lower than expected IT hardware investment. | 1023 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1032m. to 1023m. This is primarily due to the following factors. The baseline whole life costs have marginally reduced as a result of the baseline now reflecting expenditure figures as per the approved OBC but excluding optimism bias solely in year 22/23 as per IPA advice to ensure consistent in-year reporting (the 21/22 Q4 figures will have included optimism bias for 22/23). It is important to note that the FBC, currently under assurance checks, indicates a significant reduction to whole life costs as optimism bias assumptions are revised downwards. | 3831 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3831m. The baseline whole life costs have marginally reduced as a result of the baseline now reflecting expenditure figures as per the approved OBC but excluding optimism bias solely in year 22/23 as per IPA advice to ensure consistent in-year reporting (the 21/22 Q4 figures will have included optimism bias for 22/23). It is important to note that the FBC, currently under assurance checks, indicates a significant reduction to whole life costs as optimism bias assumptions are revised downwards. | DWP_0008_2122-Q2
Health Transformation Programme | DWP | Government Transformation and Service Delivery | The Health Transformation Programme is a critical part of the department's disability strategy. It will procure new functional assessment service contracts, modernise our service and be a key enabler for reform proposals detailed in The Health and Disability White Paper published 16/03/23. The Health Transformation Programme aims to deliver: A vastly improved claimant experience: including reduced journey times and improved claimant choice in terms of channel to claim. A more effective and efficient service for the taxpayer: reducing reliance on paper and integrating service delivery, reducing demand for health assessments by triaging. Greater capability to innovate and deliver change: including White Paper reform. All devolved benefits in Scotland, including Personal Independence Payment (PIP), are out of scope for the Health Transformation Programme. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. With continued support from the Infrastructure Project Authority, HTP has progressed well with business case approval for Functional Assessment Service (FAS) and the Functional Assessment Service IT secured alongside comprehensive preparation for FAS to go live in 2024. The Department received a legal challenge to one of the FAS contract lots, which has delayed the procurement. However, a resolution has now been agreed with contracts still scheduled to be in place during 2023 to start in 2024. Following publication of the Health & Disability White Paper, HTP has been identified as a key delivery vehicle and work is underway to understand the impact. Plans to extend the Health Transformation Area are also underway and the next phase will be undertaken in close partnership with the new FAS providers. However, the programme remains challenging and complex so detailed scenario plans, that develop options for the most significant risks, have been developed so the programme has robust contingencies ready should they be needed. | 2018-03-28 | 2029-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2028-12-29 to 2029-03-31. This is primarily due to the following factors. The Programme schedule was previously extended as we made a short extension to the existing disability assessment services contracts, until March 2024, to facilitate the procurement and safe transition to the new contracts in order to prevent disruption to services. The Department then received a legal challenge to one of the FAS contract lots which has delayed the procurement. On 25th May the Department announced the outcome in three of the four contractual lots and procurement activity on the remaining lot has resumed, with contracts still scheduled to be in place during 2023 to start in 2024. | 125.99 | 58.42 | -54 | 2022-23 Costs are lower than baseline as a result of challenges in bringing in resource coupled with changes in the plans and timetable for introducing operational initiatives meaning that the Programme did not incur the associated set up and recurring costs. | 3158 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 3673m. to 3158m. This is primarily due to the following factors. Figures now reflect the outcome of the Functional Assessment Service (FAS) procurement exercise and the approved Final Business Case for the project. | 5439 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5439m. The reduction in benefits relates to an update on prior year benefits to the latest baseline position and the incorporation of FAS savings within FAS provider bids. | DWP_0028_1819-Q3
Pensions Dashboard Programme | DWP | ICT | Pensions dashboards will enable individuals to access their pensions information online, securely and all in one place, thereby supporting better planning for retirement and growing financial wellbeing. Dashboards will provide clear and simple information about an individual's multiple pension savings, including their State Pension. They will also help them to reconnect with any lost pots. | Red |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (SRO rating) to Red (IPA rating). This is primarily due to the following factors. In March 2023 the Department for Work and Pensions (DWP) announced via a Written Ministerial Statement (WMS) that there would be changes to the mandatory connection deadlines for pension providers and schemes. The statement explained that the Pensions Dashboards Programme (PDP) was unable to meet the connection deadlines set out in legislation.PDP is working closely with DWP who have appointed a dedicated Reset Director with experience in large change programmes to oversee the reset, working alongside the existing PDP team. The reset team will:. assess the programme;. revise the plan; and. mobilise for delivery.DWP published a further WMS in June 2023 outlining that regulations have been put before Parliament to replace the previous staging timeline with a single mandatory connection deadline. This will be complemented by guidance which will set out when schemes will be expected to connect. The connection deadline set out in law by DWP will be 31 October 2026. | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | 19.86 | 19.2 | -3 | N/A as variance is below 5% | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | DWP_0029_2021-Q4
Synergy Programme | DWP | Government Transformation and Service Delivery | The Department for Environment, Food and Rural Affairs (DEFRA), Department for Work and Pensions, Home Office (HO) and Ministry of Justice (MOJ) are collaborating together in a cluster to achieve the Government's Shared Services Strategy by transforming shared services to make them smarter, swifter and more streamlined. Synergy is a business transformation programme to replace the current services provided by Shared Services Connected Limited (SSCL) and focusing simplifying and aligning processes, data systems and services, to transform our users' experiences and drive interoperability between departments, resulting in increased productivity and value for money, provided through a single Software as a Service (SaaS) Enterprise Resource Planning (ERP) platform and business process service. The four departments have committed to working as a single cluster with departments responsible for their departmental transformations. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Synergy programme agrees with the IPA commentary on the Programme Delivery Confidence Assessment. The programme continues to manage the significant risks arising from the complexity and scale of change required. Risk management remains embedded across the programme, managed by dedicated programme risk resources and reviewed at the monthly Programme Board. Successful implementation will enable and utilise the full potential of cloud technology to drive further efficiencies, savings and better user experience. The magnitude of change required in each Department cannot be underestimated and will require strengthened programme transformation leadership and capability (which we are actively shaping) and cross Government support at all levels in order to deliver step changes in effectiveness of shared services across those Departments. | 2021-04-01 | 2028-12-29 | The project's end-date at 22/23-Q4 is 2028-12-29. This is primarily due to the following factors. The Programme has completed a planning refresh and was baselined by the Synergy Strategic Programme Board at the end of April. This planning refresh has brought a greater understanding and added more detail of the activities needed to design and procure technology, delivery partners and also change ways of working that will meet our user experience and benefits ambition and enable this to be presented in a compelling Full Business Case. Delivery dates have been updated accordingly. | 20 | 15.15 | -24 | In Financial year 22/23 Synergy expenditure (15m), was below the 20m drawdown. This is largely due to timing of expenditure on staffing and consultancy in departments. In March 2023, HMT agreed flexibility to allow the carry forward of the anticipated underspend in 23/24 (It is proposed to share an initial view of this with HMT) to support the Full Business Case approval into Q1 of financial year 24/25, through a date only extension. The Programme is strengthening its financial management, linking closely with department teams to develop a resourced integrated plan. This will underpin managing expenditure in 2023/24. | 2488 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 2488m. This is primarily due to the following factors. The programme has agreed funding for the current Spending Review period to 2024. However this is a cross department programme which extends beyond the current Spending Review period. Projected funding for the next Spending Review period will need to be agreed with HMT so that the programme can deliver its scope and benefits. | 1089 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1089m. Benefits are being matured, through asking Department functional directors to identify connected and end to end strategic opportunities, alongside maturing the already identified benefits as the design develops. We are ensuring our work helps shape and align to the cross-Government benefits work. | DWP_0042_2122-Q3
Universal Credit Programme | DWP | Government Transformation and Service Delivery | Universal Credit replaces six separate benefits and tax credits for working age people, bringing together in and out of work systems into one, to make work pay. When fully rolled out it is expected that around 6.5 million households will benefit from Universal Credit. Legislated for in 2012-13, it has now entered delivery phase. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The overall Delivery Confidence Assessment Rating remains AMBER. Whilst commencing to increase the number of Tax Credit only claimants with Migration Notices, as planned, on 3 April 2023 is a major step forward for the programme there remain significant challenges to completing migration of approximately 1 million legacy households to UC by end of March 2025 including competing Operational delivery demands and potential delivery challenges as a result of supporting wider Departmental and Central Government priorities.Publishing our learning from the Move to UC Discovery Phase in January provides a firm basis for us to engage more effectively with Stakeholders and Partners in the coming months, working with them to best support claimants on their migration to Universal Credit. The latest IPA Gate 0 review reported an AMBER delivery confidence with work now focussed on planning and preparing for the next few months as we quickly and rapidly increase the numbers of notifications issued per month. | 2011-11-17 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-12-31 to 2025-03-31. This is primarily due to the following factors. Whilst increasing the number of Tax Credit only claimants issued with Migration Notices commenced as planned in April 2023 there remains significant challenges to completing migration of approximately 1 million legacy households to UC by end of March 2025 including competing Operational delivery demands and potential delivery challenges as a result of supporting wider Departmental and Central Government priorities. | 1437.84 | 1412.25 | -2 | N/A as variance is below 5% | 17305 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 12717m. to 17305m. This is primarily due to the following factors. Policy decisions have led to an increase in operating costs by putting more claimants into full conditionality. Although this is more expensive to run, the benefits of having more claimants in full conditionality outweigh and are now over 70bn. | 70638 | The project's departmental-agree monetised benefits at 22/23-Q4 is 70638m. Policy decisions have led to more claimants being put into full conditionality which, as a consequence, has increased the benefits of the programme to over 70bn. | DWP_0009_1112-Q1
Workplace Transformation | DWP | Government Transformation and Service Delivery | The Workplace Transformation Programme is a 10-year programme which focuses on how and where we will work, determining our future locations and working practices. This will deliver efficiencies and enable genuine modernisation and transformation within DWP. Alongside this there is a structured programme of essential works to ensure our ageing buildings remain safe and functional for claimants and colleagues delivered through our Estate function. Together they support the Government's Property Strategy to deliver a smaller, better, and greener estate and the Places for Growth objectives - making DWP a great place to work and improving the customer experience. | Amber |  |  | 2020-07-01 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. WPT is complex, as an enabling Programme it has a number of key dependencies including future size of the workforce, how that workforce is deployed, and the underpinning ways services are delivered (the operating model) during modernisation/transformation. However, the programme has a burning platform for future location strategy delivery due to lease events in 2028 which will need to drive decision-making for the next phase.PBCv2.0 for 23-24 funding is due for HMT approval in May 2023. PBCv3.0 timeline is in development. PBCv3.0 will seek funding for the remainder of this SR, 24-25 and across the next.To date, the Programme has achieved a majority of Deliverables while actively managing the few where delivery slipped due to external influences.Planned building closures, consolidations and refurbishments proceed to plan. The 'retain, re-train, re-deploy' strategy has resulted in lower people exit costs than forecasted.The phased approach for Temporary Jobcentres closure commenced as planned, the Programme taking advantage of where early lease-breaks present. | 250.6 | 82.15 | -67 | The baseline uses the Programme Business case (PBC) set in March 22 which aligned to the site level strategy at that point. This baseline is therefore over one year old. Since then, the site level strategy has been subject to change following feasibility stages and deep dives. The outturn for 22/23 was 168.5m below the original PBC baseline, this was due to a number of factors, including the impacts of IFRS16 accounting treatment, lower than anticipated number of people exits, absorption of training costs within existing allocations, building costs per square metre being lower than original estimates and pausing of activity on sites not demonstrating value for money. Additionally, to ensure successful delivery of benefits enabled by site closures, some improvement work has been reprofiled into the remaining years of the SR. Despite the lower outturn the realisation of benefits remains on track with no impact to successful delivery of the programme. To improve the cost management of the programme in future years we have undertaken additional scrutiny of the delivery plans and assumptions, as well as strengthening financial reporting processes. | 862 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 862m. This is primarily due to the following factors. The actual spend figure above, reflects the first delivery year 22-23 of WTP although the Baselined Whole Life Cost figure, reflects the latest approved Programme Business Case (v1), approved for 22-23. The revised Whole Life Cost figure will be updated alongside PBCv2, including the impacts of IFRS16 (lease accounting), which will be included in the Q1 GMPP report. | 3536 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3536m. By right-sizing, the estates baseline can be reduced by 80m-90m per year from 2028/29. Subject to future funding ultimately deliver substantial gross savings of 3,536m (inc. Vat and inflation, exclude depreciation) over a standard 30-year estate business case period. | DWP_0013_2122-Q2
Echo 2 Programme | FCDO | ICT | The ECHO 2 Programme is the next generation communication and connectivity bearer for both the FCDO and British Council evolving from the current ECHO 1 network. The ECHO 1 contract delivers the FCDO and British Council global telecommunication and connectivity network through a single supplier. Transitioning to ECHO 2 will improve global communication resilience and provide run cost saving by contracting a network service organisation to manage connectivity while enabling the FCDO and British Council to procure internet connectivity for its sites. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. IPA AMBER RAG status relect the risk of legal challenge to the ECHO 2 contract award. That challenge was made, settled and the Programme is now on contract and in delivery. Next IPA assessment is planned for Q3 23. | 2015-09-01 | 2024-07-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-01-23 to 2024-07-31. This is primarily due to the following factors. The delay has been incurred in the Design, Build and Test phase, mitigated by a reduction in the number of sites to be transitioned. It has resulted in an extension of the incumbent supplier by a further six months, increasing the Programme costs, howeve costs remain within the Programmes Full Business Case (FBC) approved limit and the benefits case remains extant. | 45.57 | 33.18 | -27 | The budget variance exceeds 5%. The ECHO 2 baseline forecast for FY22/23 (RDEL & CDEL combined) was 45.57m and the actuals for the year ended at 33.69m. The variance is a result of the eight month delivery delay to the programme and subsequent delay of transition and dual running costs. | 313 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 313m. This is primarily due to the following factors. The Programme continues to report against the OBC figure of 312.94m and should be converted to the FBC figure of 265.23m as soon as the contract re-baseline with the Network Service Integrator (NSI) supplier is concluded. The programme is reporting a 6.6m underspend against its FBC forecast of 258.6m, which includes a forecast for the current eight month Programme delay. | 103 | The project's departmental-agree monetised benefits at 22/23-Q4 is 103m. The project's departmental-agree monetised benefits at 22/23-Q4 is 102.99m. The Programme is forecasting an increased financial benefit of 25m on conclusion of the Dynamic Purchasing Service (DPS) competitions and as a result of reduced internet circuit run costs. | FCO_0010_1617-Q3
FCDO Integration | FCDO | Government Transformation and Service Delivery | FCDO Integration is the portfolio of the essential activities that are required to merge the two legacy departments (FCO/DFID) to fully form the FCDO, and to enable it to operate effectively and efficiently as a single organisation. The Integration Portfolio will be the core focus of internal change for the FCDO until Summer 2023 and will include activities such as delivering key technology, removing duplication in systems, aligning local Country-Based Staff (CBS) pay scales where this has not yet happened, introducing a single aligned pay structure for UK-Based staff and bringing new entrants in on single Terms and Conditions. The successful delivery of the Integration Portfolio will lay the foundations for One FCDO. | Green |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Green. This is primarily due to the following factors. The IPA completed an Assurance Action Plan Review last summer following on from the Gate 0 review of February 2022. The Integration Portfolio successfully received a green rating for the Assurance Action Plan and is now in the process of preparing for a Gate 5 review in summer 2023, having successfully completed delivery of a core portfolio of programmes - providing the functions necessary to operate effectively as one FCDO. | 2020-06-16 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The project's approved end-date at 22/23-Q4 was 2025-03-31. Following the IPA's Assurance Action Plan Review that took place in 2022, the FCDO rescoped the portfolio to focus on the essential activities that are required to merge the two legacy departments to fully form the FCDO, and to enable it to operate effectively and efficiently as a single organisation, which required a shorter timescale. The portfolio has successfully completed delivery, and programme closure reports are being reviewed. The forecast end date is now at the end of quarter two, 23/24 which is expected to be confirmed at the Gate 5 review, in June 2023. | 8.68 | 8.68 | 0 | The GMPP project did not provide data | 41 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 6m. to 41m. This is primarily due to the following factors. The agreed Whole Life Cost for the merger activity since the announcement by the Prime Minister at the time on 16 June 2020 is 41.2m. Over the life of the portfolio, the methodology through which the costs were determined was changed, particularly following a recommendation of the Gate 0 review in February 2022. As a result, this total differs from the data which was reported through the GMPP returns but is more accurate. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. Following consultation with the IPA and since the merger was a political decision with the majority of benefits being qualitative, it has been agreed that it is not necessary to calculate monetised benefits. | FCO_0014_2122-Q1
Hera Programme | FCDO | ICT | The Hera programme has delivered a single integrated Finance and HR system (using the Oracle Cloud platform) for the Foreign, Commonwealth and Development Office following the merger of DFID and the FCO. It was built on the former Atlas programme in the FCO but was substantially reshaped incorporating the requirements of the new department. Hera is an essential platform for wider FCDO Transformation and will enable the new department's finances and structures to be fully integrated in line with Ministers objectives. Hera will be a platform to deliver government strategy for providing shared services in the UK and overseas for Partners across Government | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. An IPA Gateway 5 review was undertaken in March 2023 which rated the Programme as Amber making helpful recommendations on the transition to BAU and the establishment of a Roadmap of changes alongside completion of the outstanding modules for Learn and Talent in 2023. | 2016-05-01 | 2023-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-10-31 to 2023-12-31. This is primarily due to the following factors. While the programme has delivered its key releases during 2022, transition to Business as usual, implementation of additional Learn and Talent Modules and development of the Hera Roadmap will complete by December 2023. | 23.4 | 28.58 | 22 | The budget variance exceeds 5%. Underspend on implementation costs in 22-23 reflects deferment of additional modules for Learning and Talent planned for implementation in 2023. | 102 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 102m. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's projected Baseline Whole Life Cost at 22/23-Q4 decreased from 102.4m to 101.77m. | 127 | The project's departmental-agree monetised benefits at 22/23-Q4 is 127m. The project's departmental-agree monetised benefits at 22/23-Q4 is 127.42m. The projected benefits increased following the review of the Full Business Case in Q4 of 22/23. | FCO_0012_1718-Q4
Washington Embassy Refurbishment | FCDO | Infrastructure and Construction | Refurbishment and upgrading of key buildings on our Washington, USA, compound. These buildings currently fail to fully meet health and safety requirements. Further investment in modernising these buildings will futureproof our ability to deliver effective diplomatic and operational solutions in our most important global post. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Programme completion anticipated to be delivered against revised delivery dates | 2017-01-01 | 2023-08-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-12-12 to 2023-08-01. This is primarily due to the following factors. Original programme set pre-Covid and revised to take into account subequent delays/supply chain issues | 17 | 20 | 18 | Original budget revised post-Covid | 122 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 122m. This is primarily due to the following factors. The projects whole life cost remains on track. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The business case approved by HMT in 2019 focussed on building refurbishment to avoid further significant decline and was not asked to include operational monetised benefits. | FCO_0011_1718-Q3
Local Land Charges (LLC) Programme | HMLR | Government Transformation and Service Delivery | Deliver a digital national Local Land Charges Register and service that covers all of England and Wales, thereby improving home buying through the digital service, with spatial data at its core. In-house delivered migrations are doing well and operating to plan, with the overall pace of delivery doubling year on year. The delivery plan has been refined, taking into account the successful onboarding of two Migration Service Delivery Partners. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme is doing well with in-house delivered migrations operating to plan and the overall pace of delivery has effectively doubled year on year; however, the length of time taken by the suppliers to get up to speed has meant their contribution to overall volume is less than set out in the original FBC. An updated business case, which takes into account supplier performance, will go to ministers imminently this sets out how the programme will complete in line with the cost and benefits estimates of the original business case, but delivery will take an additional year.Recent recruitment campaigns in the Digitisation and Business Analysts Teams has brought stability in these areas, ensuring the Programme has the capacity and capability to meet delivery volumes.Additionally, the Programme won the 'Championing Continuous Improvement' award by Smarter Working Live for collaborative efforts to improve processes and speed of migration delivery. | 2014-03-01 | 2027-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-03-31. This is primarily due to the following factors. The refreshed Business Case seeks approval to extend the delivery plan into a fifth year, FY25/26, following delays in the Migration Service Delivery Partners. There is no impact on the overall cost envelop, just movement of spend into FY25/26. | 50.25 | 26.95 | -46 | The budget variance exceeds 5%. This year's forecast spend has been lower than predicted due to delayed spend with external digitisation suppliers, including delays in contract award, onboarding and exiting the implementation stage. Consequently, there has been an underspend due to the movement in forecast for Transition Payments and New Burdens payments to LAs. | 331 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 331m. This is primarily due to the following factors. Whole life costs for our refined delivery plan remain within the overall cost envelope in the approved Business Case | 9616 | The project's departmental-agree monetised benefits at 22/23-Q4 is 9616m. The project's departmental-agree monetised benefits at 22/23-Q4 is 9616m.The project's departmental-agree monetised benefits at 22/23-Q4 is 9616m.The project's departmental-agree monetised benefits at 22/23-Q4 is 9616m. Compared to financial year 21/22-Q4, benefits at FY22/23-Q4 remain the same. This is primarily due to the Programme continuing to deliver to schedule although this will be reviewed as the Business Case is refreshed this quarter. | BIS_0015_1516-Q1
Building Our Future Locations Programme | HMRC | Government Transformation and Service Delivery | HMRC's Locations Strategy, announced in 2015, is key to enabling its wider transformation. The Locations Strategy is delivering the Phase One Government Hubs and supports the Governments Places for Growth Programme by creating opportunities and career paths in towns and cities across the UK. HMRC's new estate provides safe, modern and inclusive workspaces with high-speed digital infrastructure enabling improved collaboration, smarter working and enabling a culture where everyone feels valued. These incorporate flexible layouts that will meet future changing demands and priorities. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Green (SRO rating). This is primarily due to the following factors. The Programme has now successfully delivered 12 regional centres and 2 Specialist Sites, with 11 of these being awarded Inclusive Environments Recognition by the Construction Industry Council (CIC). During Financial Year 2022/23, the Locations Programme successfully opened a further 3 regional centres in Nottingham, Glasgow and Manchester, enabling over 10k HMRC staff to move into those new offices within the planned timescales. Following the lifting of lock down restrictions, we were also finally able to hold the opening ceremonies for 10 of our new regional centres. Ourremaining projects are at a stage where we are still considering options and Outline Business Cases will be produced from Q1 23/24 onwards. | 2016-01-05 | 2026-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-03-31. This is primarily due to the following factors. The current assumption is that the programme end date will be 2028/29, to allow the safe delivery of our remaining deliveries and to the conclude our work on Phase 1 of the Government Hubs. | 221.2 | 232.79 | 5 | The budget variance exceeds 5%. 2022/23 full year final position at end of Q4 is 32% lower than baseline. This is primarily due to the baseline position included 9.6m for Moves Assistance Payments (MAP, formerly Daily Travel Allowance) which the programme no longer funds, and revised delivery timelines in several projects, and a move to Hybrid working which greatly reduces the cost to HMRC. | 2836 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 2836m. This is primarily due to the following factors. The baseline Whole Life Cost as at Q4 2022/23 is unchanged from 2,836m reported in the 2021/22 report. It has not been formally updated since the Programme Business Case v1.0 was approved by HMT in April 2017. | 74 | The project's departmental-agree monetised benefits at 22/23-Q4 is 74m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 74m. This is due to: Monetised benefits represent estate running cost savings as a result of exiting legacy estate and moving into new Regional Centres and Specialist sites. | HMRC_0015_1617-Q1
Contact Engagement Programme | HMRC | Government Transformation and Service Delivery | The Customer Engagement Programme, CEP, has replaced HMRC's telephony and digital platforms. It has also replaced the customer contact interface for advisers and delivered credible management information solutions across the new telephony and digital platforms to improve experience for customers and colleagues. Over time, this will allow HMRC to transform the way we interact with customers; becoming a more effective and efficient organisation, driving digital take up where appropriate and providing improved tools to support our colleagues to resolve customer contact effectively through a 'once and done' approach. | Green |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. The programme is preparing to close having delivered the replacement telephony platform. There is still some work to do to complete data and reporting deliverables, highlight optimisation opportunities and agree roles and responsibilities for maintaining the service but once this has been completed the programme will be able to close | 2020-03-31 | 2022-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2022-06-30. This is primarily due to the following factors. The programme is due to complete the remaining two data and reporting deliverables into live running and support prior to programme closure in line with the programme plan. All programme closure activities are on track and being progressed via weekly update meetings with the Infrastructure & Projects Authority, weekly closure reporting meetings and the monthly programme board. | 51.63 | 51.62 | 0 | The budget variance is inferior or equal to 5%. | 236 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 226m. to 236m. This is primarily due to the following factors. The programme team required an additional 3 months and skeleton team to manage exit from the outgoing platform.Telephony costs had a new consumption based charging mechanism which now reflects demand fluctuations. Current estimates suggest an increase on previous estimates over the next two years, however this is likely to be reduced, as other initiatives focus on reducing the demand for telephony. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. The activity covered under the contact engagement programme is an enabler for other spending review initiatives, for example, single customer account. The scope covered replacement of the existing technology and these future programmes will drive benefits and value add from optimisation and exploitation of the new platform. | HMRC_0026_2021-Q1
Critical Platform Transformation CPT | HMRC | ICT | Through applied industry standard identification, the programme has delivered several software, hardware, and component upgrades, whilst reducing HMRCs legacy IT estate. The programme has supported several internal programmes enabling HMRCs transformation activities to mature, supporting legislative, ministerial and policy driven change. This has increased our stability and resilience offering, to create a more modern IT and working environment. The programme will continue to deliver against the strategic aim to create further modern platforms, products fit for 21st century. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme is made up of 13 workstreams to focus on and deliver technical health improvements in different parts of the HMRC IT estate. 8 of those workstream are experiencing some delays due to the availability of supplier and internal resource. To get back on track for an overall green status, plans are ongoing to maximise resourcing activity for prioritisation of key resources. | 2021-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-03-31 to 2025-03-31. This is primarily due to the following factors. The programme was initially a single year mobilisation as part of the 2020 spending review allocation. Further investment in the programme was agreed as part of the 2021 spending review which extended the programme by 3 years to enable the programme to deliver significant change across the department and actively contribute to HMRC's risk reduction whilst increasing information technology resilience and stability. | 69.7 | 72.78 | 4 | The budget variance is inferior or equal to 5%. | 341 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 85m. to 341m. This is primarily due to the following factors. The whole life cost has increased as a consequence of additional investment being agreed in the 2021 spending review allocation to extend the programme by 3 years. The additional spend is in relation to information technology and resource costs, and also includes, in line with HM Treasury guidance, a period of information technology running costs. | 5 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 5.28m. This is due to: The benefits represent sustainable cost savings including license cost savings, storage cost savings, 3rd party contract savings, decommissioning cost savings and other IT infrastructure run cost savings. | HMRC_0032_2122-Q1
Data Protection Remediation Programme | HMRC | Government Transformation and Service Delivery | The Programme (DPRP) will deliver remediation activity to ensure HMRC regulatory compliance linked to its legal obligations under UK General Data Protection Regulation (UKGDPR) and the Data Protection Act 2018 (DPA 2018). | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Delivery confidence is Amber while the programme take steps to re-baseline scope. Actions being taken to move towards Green include having the required business resources in place to support delivery and ensuring the programme deliver all scope items following the re-baselined delivery plan. | 2021-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The programme is currently on track and expects to complete by 31st March 2025. | 14.65 | 13.37 | -9 | The variance is mainly due to some planned activity not being required as some systems no longer needed any remediation, or were removed from the scope of the programme, supplier costs being overestimated, and the revision of the programme plan to move some work into the next financial year. | 85 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 205m. to 85m. This is primarily due to the following factors. The whole life costs have reduced from 205m in Q4 21/22 to 84.54m at Q4 22/23 as some systems no longer needed any remediation or were removed from the scope of the programme and reduction in forecasts of supplier costs |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. The programme does not have any monetised benefits | HMRC_0029_2122-Q3
Debt Respite Programme | HMRC | Government Transformation and Service Delivery | The Debt Respite Scheme (DRS) is a government policy supporting vulnerable customers in problem debt. DRS legislation applies to all creditors (including HMRC) and offers debtors legal protection from creditor action on qualifying debts, for example recovery and enforcement action stops, and interest fees and charges are paused. DRS covers England and Wales and is administered by the Insolvency Service who notify creditors when customers enter/exit DRS. There were two scheme elements: Breathing Space (BS) implemented on 4th May 2021 and Statutory Debt Repayment Plan, to be introduced i August 2024 but that was de-scoped following HM Treasury led consultation in August 2022. The Programme completed closure activity March 2023. There were two programme phases for Breathing Space: Phase 1: To meet the legislative deadline using a medium-term part auto/part manual solution was implemented on 4th May 2021 Phase 2: The long-term fully automated IT solution, implemented in February 2023, removed manual interventions reducing the administrative burden on HMRC. |  | Green | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Green. This is primarily due to the following factors. The Programme was consistently rated as Green through monthly Programme Boards and also independent assurance reviews, most recently at Infrastructure and Projects Authority (IPA) Gate 5 review on 6th March 2023 in terms of delivery confidence reflecting that 'successful delivery of the programme to time, cost and quality' wasn't at risk. | 2020-01-02 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2024-12-01 to 2023-03-31. This is primarily due to the following factors. The Programme completed all of the relevant activities to complete the successful delivery of the Breathing Space element of the Debt Respite Scheme. The second scheme element was Statutory Debt Repayment Plan (SDRP), following feedback from His Majesty's Treasury (HMT) led Public Consultation in August 2022, the decision was made to remove this from scope. Any future decisions on SDRP will be based on the outcome of the Governments review of the Personal Insolvency Framework. | 17.46 | 7 | -60 | The budget variance exceeds 5%. The reason for the variance is because the programme closed down early and no work was carried out on SDRP. | 136 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 99m. to 136m. This is primarily due to the following factors. The most recent business case approved whole life costs (including service line costs) covering the period from 2019/2020 to 2030/2031. The programme secured funding via Spending Review 2021 (SR21) up to 2024/2025. The programme completed closure activity in March 2023 and the Service will move over to Business as Usual (BAU). An agreed amount of budget for 23/24 and 24/25 will also be transferred to BAU to cover operational pay-bill and Chief Digital Information Office (CDIO) service lines during the SR21 period. CDIO are the team responsible for HMRCs IT estate, including building and running IT services, leading digital transformation projects and delivering operational support to our colleagues and customers. For 25/26 onwards, funding will form part of the BAU/CDIO baseline in the next Spending Review period. Due to the Debt Respite programme closing early lifecycle costs have reduced from 135.68m to 58.02m. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. There were no monetised benefits identified for the Programme. The main driver behind the Programme was for HMRC to fulfil its legal obligations as a creditor. In delivering the service customers with HMRC debt should have a better experience with HMRC. This is being measured through sample testing of customer feedback (compliments and complaints) | HMRC_0031_2122-Q1
Debt Transformation | HMRC | Government Transformation and Service Delivery | Debt Transformation is a five year programme to provide a new functional and future proofed debt management system to replace the current system, and manage an incremental transition to new services, sequencing the on-boarding of tax regimes whilst decommissioning legacy information technology (IT) enabling a single view of a customers' total indebtedness and allowing for a customer-centric approach to debt collection. The programme will reduce business system failure risk therefore protecting revenues and provide the opportunity to realise key efficiencies and revenue benefits to HMRC. It will help reduce debt balance and contribute towards our strategic objectives; making it easy to get tax right and hard to bend or break the rules, collect the right tax and pay out the right financial support. In addition, it will support wider government economic aims through a resilient agile tax administration system. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The amber status is due to concerns regarding supplier capacity, whole programme funding and wider understanding of the migration approach. These concerns are being explored through the Department's business planning process for 2023/24. | 2020-05-04 | 2025-12-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-12-01. This is primarily due to the following factors. The programme is made up of three projects initially which have already been delivered with further activity scheduled to replace the current debt management system. All plans are on track and the programme expects to complete by 1st December 2025. | 18.35 | 16.11 | -12 | The budget variance exceeds 5%. The baseline included a contingency in case the costs were higher than estimated. The contingency was not ultimately required as information technology costs especially those that are time and materials have come in less than forecast. | 102 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 79m. to 102m. This is primarily due to the following factors. Revised information technology costs were received which includes a further five years live running costs as well as re-planning activity, for the programme that includes increased delivery resources. | 76 | The project's departmental-agree monetised benefits at 22/23-Q4 is 76m. The project's departmentaly-agreed monetised benefits at 22/23-Q4 is 76.06m. This is due to: The benefits largely represent additional tax revenue and reduction in staffing costs | HMRC_0028_2122-Q3
Enterprise Security Programme ESP | HMRC | ICT | The Enterprise Security Programme will improve the security of HMRC's systems and processes by further strengthening our cyber security; build an increased level of resilience to emergency situations; improve our security culture and capability; and to increase digital inclusion. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Year 2 delivery concluded with successful completion of critical delivery milestones which contribute to business case outcome of reducing HMRCs security risk. The programme is anticipating scope changes as a result of other changes in scope in programmes Enterprise Security Programme has dependencies on. A full impacting exercise is underway to assess impact on cost, time and benefits. | 2022-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-03-31 to 2025-03-31. This is primarily due to the following factors. Following successful delivery of the year 1 programme which was funded with Spending Review 2020 investment, a further 3 year investment has been approved under spending round 2021. The current business case provides approval to deliver on the agreed outcomes by March 2025. | 41.6 | 29.5 | -29 | The reduction is due to the fact that the funds available to the programme were restricted during the year. This has been managed by re-profiling the spend and delivery plans into future years whilst still remaining within the overall programme timeline and spend allocation | 142 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 29m. to 142m. This is primarily due to the following factors. The whole life cost of the programme has increased following a 3 year investment as a result of Spending Review 2021. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. Enterprise Security Programme is a risk reduction programme and is not reporting cash releasing benefits. | HMRC_0033_2122-Q1
HMRC Northern Ireland Programme | HMRC | ICT | The NI Delivery Programme is managing changes to HMRC Customs and Indirect Tax systems to enable HMRC and traders to operate, within the terms of the Northern Ireland Protocol, now replaced by the Windsor Framework. Also, for the UK to remain aligned with other EU customs legislation for Northern Ireland. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Substantive progress continues to be made with delivery against the programme strategic outcomes. The 2023/24 delivery plans have been baselined and the announcement of the Windsor Framework in February 2023 has provided clarity on the way forward. The programme is reporting Amber, whilst it assesses the impacts of delivering the new Windsor Framework requirements against existing priorities. | 2022-04-01 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. The programme is broadly on track to deliver during the lifecycle. The plans now also include delivery of HMRC Windsor Framework system requirements including for the 'green lane' for October 2024. | 163.8 | 149.4 | -9 | The costs of delivery in 2022/23 were lower than the original baseline mainly driven by elements that were paused due to the negotiations around the NI Protocol, the removal of some scope from programme baseline and the deferral of some elements of system re-platforming. | 388 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 388m. This is primarily due to the following factors. The project's departmentally-agreed Whole Life Cost at 22/23-Q4 is 388m. This is due to: The baselined whole life costs for the programme includes programme team resourcing, technology costs and on-going live service support to deliver the original scope of the programme. Delivering the system requirements for the new Windsor Framework will require additional funding over the next 2 years. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. The programme is managing changes to customs and indirect tax systems to comply with policy and legislative requirements | HMRC_0164_2223-Q3
Infrastructure Programme | HMRC | Government Transformation and Service Delivery | The Infrastructure Programme was established to support and enable the Government priority of maintaining the flow of trade following the end of the EU Transition period and to ensure full border controls were in place by the end of the staged customs controls timeline. The programme has delivered Inland Border Facilities (IBFs), via the Short Straits and Holyhead, where the ports did not have the ability to complete the checks themselves. On 31st December 2020, we opened 11 temporary IBFs, the next phase brought facilities up to full operating capacity and migrated the temporary facilities to provide two enduring sites. Following completion of the two phases, the Programme are now decommissioning and reinstating the temporary facilities. The Programme is on track to complete all temporary site closure activity by summer 23 and move towards formal closure of the programme and transfer of the ongoing operations of Sevington and Holyhead into HMRC business as usual. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The programme RAG status remains amber this quarter. At Holyhead Inland Border Facility, following the notice of delay from our contractors, a revised programme of work brings forward the practical completion date from 2nd August to 11th July 2023 which has been validated and provides an assured way forward. Additional assurances have been put into place to manage the dependency on our contractors to keep to agreed schedules and this is being monitored. This quarter has seen the decommissioning and re-instatement work at our interim sites at Dover, North Weald, Birmingham and Warrington come to a conclusion and all work has been completed successfully. At Ebbsfleet site the Phase 1 Decommissioning work has been completed and Phase 2 Reinstatement works are progressing well and on track for completion on 30th June 2023. | 2020-01-24 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Work is underway to build a site at Dover and to construct permanent facilities at Holyhead. The temporary Inland Border Facilities will also be decommissioned and closed in a controlled manner. The programme expects to complete by 31st March 2025. | 127.18 | 125.02 | -2 | The budget variance is inferior or equal to 5%. | 533 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 775m. to 533m. This is primarily due to the following factors. The cost decrease is linked to savings made on early closure of sites, and reductions in operational costs due to the introduction of a single site operator for enduring sites. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. The primary benefit of the programme is to meet the policy requirement to establish Inland Border Facilities at strategic locations across the UK to enable the continued flow of trade across our borders. The programme will not realise any monetised benefits but will continue to incur costs. | HMRC_0027_2021-Q2
Making Tax Digital | HMRC | ICT | Making Tax Digital aims to improve business record keeping providing businesses with a modern digital experience, encouraging compliant behaviour and acting as a building block to HMRC's transformation plans. | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (IPA rating). This is primarily due to the following factors. The Income Tax Self Assessment is challenging due to its size and complexity and the Written Ministerial Statement in December 2022 confirmed the phased delivery of mandation from 2026. MTD successfully transitioned MTD for VAT to business as usual in October 2022, and Penalty Reform for VAT went live in January 2023. MTD is redesigning and streamlining its programme structure to gain better transparency of plans and co creation with software developers to achieve successful outcomes for all our customers and agents. | 2016-04-01 | 2028-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2025-04-01 to 2028-03-31. This is primarily due to the following factors. Making Tax Digital (MTD) current scope includes Income Tax Self Assessment mandation, VAT enhancements and Penalty Reform to harmonise penalties across tax regimes. MTD aims to support UK businesses to go digital and provide them with a modern digital experience, encouraging compliant behaviour and act as a building block to HMRCs transformation plans. | 153.15 | 149.36 | -2 | The budget variance is inferior or equal to 5%. | 885 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 885m. This is primarily due to the following factors. The baseline costs reflect the scope for MTD across VAT, ITSA and Penalty Reform as set out in the Programme Business Case that was signed off by HMT Treasury Approval Point in June 2021. A new iteration of the Programme Business Case is in development. Once the new version of the Business Case receives TAP approval, the baseline position will be revised to align. | 2146 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2146m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 2145.84m. This is due to: The benefits represent additional tax revenue and customer cost savings | HMRC_0017_1617-Q2
Payments | HMRC | Government Transformation and Service Delivery | HMRC has inconsistent payment rules, methods and processes, and we do not use the payment mechanisms our customers now expect. Customers frequently make mistakes in paying us and risk being pursued for debts they do not owe. In addition, the UKs Banking Industry is approaching the biggest changes in infrastructure and processes it has for generations. HMRC must be able to respond to these mandatory changes in order to continue to receive and make payments. This proposition is all about improving the processes which support this critical function and as such delivers HMRC's payments strategy and supports all four HMRC's strategic objectives. The Payments Programme will support HMRC's new vision HMRC to be a trusted, modern tax and customs department. HMRC has a vital purpose: we collect the money that pays for the UKs public services and help families and individuals with targeted financial support. Through this programme we will make it easier for customers to pay, and be paid by, HMRC. To support this we are improving and building digital services |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The overall programme status is Amber. Three of the programme's sub projects have an Amber status against current, indicative milestones and two of the programmes Key Performance Indicators (Delivery against Cost (Finances) and Delivery against Benefits) are rated Amber. However, the programme will deliver its Ministerial Commitments by the final programme delivery. There are key issues and risks are around supplier resourcing and dependencies on other programmes (Technology Resourcing Programme). We have imported work from Making Tax Digital and a risk remains around the associated funding and categorisation of work. The programme went through a period of restricted change (from 06/12/22 to 31/01/23) that impacted our ability to deliver some of our projects to schedule during Q4. The programme is reworking schedules and developing workarounds to mitigate these risks, and is looking to enact a back to green plan. | 2021-04-01 | 2026-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-03-31. This is primarily due to the following factors. The Programme is currently on schedule and expects to complete by 31st March 2026. | 23.62 | 24.17 | 2 | The budget variance is inferior or equal to 5%. | 149 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 108m. to 149m. This is primarily due to the following factors. Lifecycle costs have increased from 108m at Q4 21/22 to 148.79m at Q4 of 22/23. There has been a change in cost profile. The original forecasts were produced 3 years ago, before the programme began. Inevitably there was always going to be a variance between those forecasts and the actual spends and forecasts that become clearer as the programme matures and more detailed costs are developed. Easy Consistent Payment Methods is a large (very large) project with a number of deliverables. Some of those deliverables relate to the National PAYE System and stopping the issue of Payable Orders. The programme has also been asked to take on work from Making Tax Digital at an estimated cost of 5m which is currently not in its budget allocation. | 589 | The project's departmental-agree monetised benefits at 22/23-Q4 is 589m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 588.63m. This is due to: The monetised benefits represent additional tax revenue, reduced staff costs, and a reduction in printing and postage costs. | HMRC_0027_2122-Q2
Pensions Programme | HMRC | Government Transformation and Service Delivery | The Pensions Programme will modernise the administration of Pensions Tax Relief by replacing the legacy online service with the Pensions Online Digital Service (PODS) (called "Managing Pension Schemes" on Gov.uk). PODS functionality will make it quicker and easier for Pension Scheme Administrators to self-serve, make claims (including Relief at Source claims) and fulfil all their pensions tax obligations. Modernisation will: - help Pension Scheme Administrators (PSAs) and their Practitioners get it right first time, while increasing HMRCs ability to spot activity that bends or breaks the rules. - minimise manual processes for HMRC, PSAs and Practitioners, saving time and money - provide quality and more timely data for compliance, delivering increased tax yield. The Programme will help deliver two government priorities for individuals and Pension Tax Relief by: -implementing top-up payments for disadvantaged customers in net pay arrangement pensions -developing IT services to support the McCloud compensation scheme. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Pensions Programme is currently reporting an Amber Delivery Confidence Assessment. This assessment is regularly reviewed and is currently driven by the following three areas:(1) McCloud Remedy: The McCloud Calculator is scheduled to go live on 2nd October 2023. We are still finalising this delivery plan to ensure this will be achieved.(2) Digitisation of Relief At Source: It will be several months before we have cost estimates and detailed delivery plans.(3) Pensions Online Digital Service: We continue to experience supplier delays with a specific release, impacting our delivery plan. If this is not resolved by July 2023, it could start to impact the benefits position. We have escalated this to the HMRC supplier management team to assist with resolution | 2021-03-01 | 2027-03-31 | The project's end-date at 22/23-Q4 is 2027-03-31. This is primarily due to the following factors. The programme is progressing to existing plans and expects to complete by 31st March 2027 | 22.4 | 14.5 | -35 | The baseline costs were developed before lower-level cost estimates or supplier impacts were available and as such, the forecast had a high level of uncertainty. In addition, the assumption was that a major piece of work would be progressed much earlier than proved possible. This issue was identified early in the year and the programme mitigated some of the potential underspend by bringing forward some future work, but this has resulted in a circa 8m in-year underspend. | 113 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 113m. This is primarily due to the following factors. The project's departmentally-agreed Whole Life Cost at 22/23-Q4 is 113m. This is due to: The Baseline Whole Life Cost of 112.51m is based on the assumptions that the Programme will deliver its Ministerial commitments relating to Pension Online Delivery Service and McCloud Remedy and the Low Earners' Anomaly over the period from 2021/22 to 2026/27. In addition, it includes costs associated with de-commissioning the legacy service and supporting Pension Scheme Administrators to migrate to the new online digital system. We have also built in the costs associated with exploiting the data to bring in the Benefits included within this report. | 270 | The project's departmental-agree monetised benefits at 22/23-Q4 is 270m. The 270m baseline figure was indicative early analysis. More recent and more detailed analysis, taking account of current risk estimates and economic determinants, has revised the estimate down to 243m (additional tax yield). | HMRC_0095_2122-Q4
Protect Connect | HMRC | Government Transformation and Service Delivery | The Protect Connect Programme aims to safeguard the operation of HMRCs most critical repayment risking services, future-proofing them by hosting them in the Cloud and laying the essential foundation for development of future strategic risking capabilities. This aligns both the HMRC Compliance and IT strategies, enhancing the understanding of customers and developing increased insight using a single data and analytics platform. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme's delivery confidence remains amber because it is behind schedule. Both VAT testing and SA testing have been impacted by additional work needed to resolve data quality issues. The VAT system is currently in a live state with access restricted to analysts who are reviewing it prior to rolling-out to all users.The funding for the additional work in 2023/24 has been secured through HMRCs governance processes and we are working closely with HM Treasury to seek their approval of the spend. Significant progress has been made on mobilising a team to support and maintain the system following implementation. Work is well advanced to develop and agree detailed benefit realisation plans to underpin the expected benefits. | 2019-04-25 | 2023-09-05 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-05-31 to 2023-09-05. This is primarily due to the following factors. The programme is making good progress towards going live, although the schedule has been impacted by additional work required to fix data issues with key feeder systems. The programme board is currently tracking progress on a weekly basis in readiness for a decision regarding VAT implementation. Good progress has been made in completing majority of the testing (including interfaces outside of the programme) and training of users, and a detailed implementation plan is being finalised to support implementation. | 42.8 | 41.65 | -3 | The budget variance is inferior or equal to 5%. | 235 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 115m. to 235m. This is primarily due to the following factors. The whole life cost increase is primarily due to the programme business case lifecycle being extended from 5 to 9 years in order to comply with HM Treasury Green Book standards to include a 5 year run period, post go-live. | 802 | The project's departmental-agree monetised benefits at 22/23-Q4 is 802m. The monetised benefits represent, efficiencies, effectiveness, decommissioning costs and environmental. | HMRC_0028_2021-Q3
Securing our Technical Future | HMRC | ICT | The Securing our Technical Future programme has been established to "stabilise" HMRC's current IT estate which is aged and exiting HMRC Business Services from the three legacy data centres to new destination platforms, Cloud and Crown Hosting (for physical assets) by December 2023. The objectives of the programme underpins HMRCs strategic objectives for April 2021 to 2025, to provide a more resilient and modern IT estate with stable services that are more flexible, ultimately enabling HMRC to run an effective tax/benefits system for internal and external customers. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. The Securing our Technical Future programme has now migrated 336 Services (61% of the total) and has successfully built three technology halls in Crown Hosting (our on premise datacentre) ready to receive a large amount of the remaining service migrations before December 2023. The Amber status is due to significant concerns regarding resource availability and a proposed reduction in funding for the next financial year. The level of technical debt within the IT estate continues to result in significant challenges for the programme requiring a larger amount of effort than originally planned which caused an extension to the programme end date. To mitigate this, we do have the correct escalation routes in place to manage supply and demand issues. As the programme is facing a reduction to funding for the next financial year, we are currently working though the impact of this on programme scope to ensure the best value for money for HMRC whilst securing our IT services and data centres. | 2018-04-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-06-30 to 2024-03-31. This is primarily due to the following factors. In June 2022 a decision was made to change the platform migration approach for over 50% of the remaining services due to the significant technical debt which was elongating costs and time. The change in platform migration approach combined with a lack of subject matter expert knowledge has resulted in a number of projects being more challenging than anticipated. This has led to an extension of the programme duration with the aim to migrate out of the legacy data centres by 31st December 2023 and closure activities to occur until 31st March 2024. The programme is now facing a potential budget reduction for the financial year 2023/24 and is working to determine a viable and cost effective method to exit the remaining services from the legacy data centres by 31st December 2023.. | 192.44 | 148.76 | -23 | The budget variance exceeds 5%. The key reason why there has been an in-year decrease is due to the programme being required to deliver within the constraints of the reduced funding available. There has also been a reduction in programme scope that meant funding was re-utilised elsewhere in the business and HMRC are re-assessing the strategic direction. | 499 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 312m. to 499m. This is primarily due to the following factors. The whole life costs for the programme have increased to 498.8m following a revision to the platform migration approach. These costs represent the increased complexities across the programme and the challenges relating to the alternative migration approach which have resulted in the programme duration being extended. | 24 | The project's departmental-agree monetised benefits at 22/23-Q4 is 24m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 23.73m. This is due to: The aim of the programme is to migrate HMRC IT services out of the legacy data centres resulting in more efficient performance for HMRC IT services and decreasing business expenditure. | HMRC_0020_1819-Q3
Single Customer Account | HMRC | Government Transformation and Service Delivery | The Single Customer Account (SCA) Programme will deliver the digital transformation expected by our customers, required for the department, and defined in the tax administration strategy by developing a task based, personalised and intuitive multi-channel digital experience. It will consider the end-to-end customer journeys in order to drive adoption and make digital channels the first choice for our customers. In doing so, we will increase voluntary compliance through automation across digital channels and increase customer satisfaction. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. Following an IPA review in January 2023, the review found a well-run programme with a clearer view and organisational understanding of what it intends to achieve. The Programme is deliverable and well-led, has senior backing and clear near-term deliverables, but will require attention and commitment of resources to maximise success. Activity continues to pivot the programme into delivery:The immediate next phase of work is clear, scope beyond is less obvious. Its critical that the programme continues to develop the criteria for agreeing, prioritising scope and remove friction in the organisation to deliver often and at pace to deliver the highest value to customers. The programme will continue to evolve the cost model and benefits to support business case delivery.Recognition of difficulty in defining the end-state which doesnt have a big bang moment, the roadmap will be refined to optimise as a communications tool for wider visibility of activities. | 2021-04-01 | 2026-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-03-31. This is primarily due to the following factors. SCA Programme is on track to complete on scheduled project end date 31/03/2026 | 29.5 | 24.57 | -17 | Forecast expectations going into the year included a provision for risk in the event of underestimation of our expenditure which has been managed out of our estimate, resulting in confidence and assurance in the cost base. Spend was lower in the early part of the year due to mobilisation times for IT delivery resource and external contractor expertise taking longer than initially projected. The Programme is now fully mobilised creating a steady state of run rate resulting in a predictable level of forecast. | 126 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 129m. to 126m. This is primarily due to the following factors. The whole life cost forecast has decreased over the past twelve months primarily due to managing out of the forecast any provision made for risk during the 22/23 financial year in addition to mobilisation times for IT delivery resource and external contractor expertise taking longer than initially projected. Current forecast position represents the result of this further assurance over the end to end cost to the Single Customer Account. | 43 | The project's departmental-agree monetised benefits at 22/23-Q4 is 43m. The monetised benefits identified represent the full-time equivalent reductions due to the migration of customer journeys from paper/telephony to digital services. Initial phase 1 deliverables will begin to realise cashable benefits next quarter. Profiles will continue to iterate as scope and populations are finalised. The programme continues to develop the criteria for agreeing, prioritising scope and remove friction in the organisation to deliver often and at pace to deliver the highest value to customers. | HMRC_0032_2122-Q3
Single Customs Platform | HMRC | ICT | The Single Customs Platform Programme is building on the successful delivery of Customs Declaration Services live service programme. The 2022/23 financial year scope continues to give greater focus to the end-to-end customer journeys and places an even greater emphasis on the role of the customer, that will improve live service and system stability / resilience. There are 3 key areas of scope that must be delivered in order to achieve this are: 1) Single Customs Platform IT delivery Delivery of Customs Declaration Services functional and non-functional delivery requirements, data and reporting. 2) Customs Declaration Services Migration Migrate traders using the Customs Handling of Imports, Exports & Freight system onto Customs Declaration Services 3) CHIEF Decommissioning Completion of Customs Handling of Imports, Exports & Freight system closure activity for both the service and all the systems that it supports | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Single Customs Platform Programme is currently amber rated, due to the ongoing work required to support the exports migration date in November 2023. Activities include ongoing engagement with internal and external stakeholders, to ensure mitigating actions are taken to address issues through the implementation of monthly IT fixes to steer the Programme back to a green rating. | 2022-04-04 | 2025-03-31 | The project's end-date at 22/23-Q4 is 2025-03-31. This is primarily due to the following factors. We are currently on schedule to deliver as planned | 132.3 | 129.4 | -2 | The budget variance is inferior or equal to 5%. | 243 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 243m. This is primarily due to the following factors. The project's departmentally-agreed Whole Life Cost at 22/23-Q4 is 243m. This is due to: The whole life cost of the project is to ensure full declarant migration from CHIEF to CDS and ensure a stable and resilient CDS system, supported by IT costs (functional and non-functional requirements), delivery and Programme resources, infrastructure changes, commercial changes in suppliers and trader support for migration e.g. communications. | 26 | The project's departmental-agree monetised benefits at 22/23-Q4 is 26m. The Single Customs Platform Programme is a 10-year benefits driven business case which contributes to the strengthening of border capability and enables His Majesty's Government ambitions in line with the 2025 UK Border Strategy. Following the HMRC set standards for Benefits Management, the Programme has completed the agreed approach, profiled and agreed with HMRC business groups. The next stage is to follow the same benefits management approach to identify all benefits onwards. Work is well underway with the majority of 2023/24 benefits identified, working with internal business groups, plans are expected to be signed off by September 2023. Monetised benefits represent process savings due to removal of manual work arounds, increase compliance and improved customer journeys. | HMRC_0159_2223-Q2
Single Trade Window Programme | HMRC | Government Transformation and Service Delivery | The UK Single Trade Window (STW) will provide a seamless customer experience by delivering a digital gateway that serves as a single point of interaction between users and all UK border processes and systems and ensures that available data, information and events provide greatest value to traders and Government. The UK STW strategic objectives support the Government's ambition to have the world's most effective border by 2025; one that creates prosperity, enhances security, improves the flow of goods and engenders industry innovation. Delivering the service will be a crucial step in encouraging legitimate trade for businesses and bringing together the Government's collection, assurance and use or border data. A customer-centric design and regular engagement with industry representatives across a broad range of sectors are key to this benefits-driven service. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme is in the final stages of procuring a technical delivery partner to co-design, build and operate the UK Single Trade Window digital platform. In preparation for this we are collaborating with partner departments undertaking user research to inform design in readiness for the first strategic release, expected in Winter 2023. To maximise the benefits of the programme, there is a dependency on primary legislation receiving Royal Assent (expected in Spring 2024) which will enable HMRC to collect and share information across government. This dependency is being actively managed with contingency options in place. We have worked with Cabinet Office on the draft border target operating model (TOM) and are now in consultation with HM Government teams and industry before the final version is published. | 2020-06-23 | 2027-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-03-31. This is primarily due to the following factors. The Programme will be delivered through planned strategic releases, which remain on track for completion by 31st March 2027. We do not envisage a deviation from the planned schedule | 30 | 25.1 | -16 | The small programme underspend for the 2022/23 financial year is primarily due to the complexities of onboarding a technical delivery partner to a programme of this size and scale and the need for readiness and mobilisation activities to move into the next financial year. Onboarding is now planned for mid-May 23. Other reasons for the underspend include financial credits received from suppliers following the consolidation of completed work orders and the actual costs of work coming in less than forecasted. | 198 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 198m. This is primarily due to the following factors. The small reduction in whole life cost can be attributed to resource cost savings for the delay from Jan 2023 to May 2023, of the onboarding of the technical delivery partner | 5740 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5740m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 5740m. This is due to: The envisaged monetary benefits predominantly reflect expected savings for UK businesses through reducing the administrative burden. There will also be benefits to government departments which will come mainly through improved data collection and sharing between government services and systems. | CO_0035_2122-Q1
Technology Sourcing Programme | HMRC | ICT | The programme is an essential component of the HMRC strategic programme to modernise and transform our IT estate and the services delivered to citizens and colleagues. At the end of March 2023, the programme achieved its next milestone by delivering an initial interim operating model. HMRC will work through to 2025 to implement critical enterprise skills, practices, standards and tools needed to run and change our IT services. This will enable HMRC to deliver IT, utilise technology and work more effectively as an organisation |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. The IPA status rating is consistent with the programme status assessment for the end of Quarter 4. We have completed all key June 2022 procurements and are focusing our attention on business readiness and the target operating model. | 2018-12-11 | 2025-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-12-31. This is primarily due to the following factors. The Programme is currently on schedule and we expect that the Programme will complete by December 2025 | 642.69 | 642.69 | 0 | The budget variance is inferior or equal to 5%. | 6855 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 7085m. to 6855m. This is primarily due to the following factors. Original baseline costs of 7,084.84 (m) were set in 18/19 and in the 4 years since then the programme has needed to respond to necessary transformational changes to reflect business needs. This has been done without losing sight of its overall programme aims and objectives. Therefore baseline has been updated in this quarter to reflect the latest approved Business Case. The overall impact of this has resulted in a reduction of 230.13 (m) in total spend from 7,084.84 (m) to 6854.71 (m), reflecting lower transition costs in moving to the new TSP procured contracts. There has as also been an increase in incremental monetised benefits of 29.49 (m) from 62.99 (m) to 92.48 (m). | 92 | The project's departmental-agree monetised benefits at 22/23-Q4 is 92m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 92.48m. This is due to: Benefits have increased largely due to lower supplier costs through effective re-procurement of contracts that had previously been in place for some time. | HMRC_0025_2021-Q1
Trader Support Service | HMRC | Government Transformation and Service Delivery | The Northern Ireland Trader Support Service TSS was established to provide a free-to-use service to support traders to meet their obligations under the Northern Ireland Protocol (NIP) following the end of the EU transition period on 31/12/20. The TSS helps traders move goods between Great Britain and Northern Ireland or bring goods into Northern Ireland from outside the UK. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. TSS has continued to deliver a high quality service, along with improvements to customer experience and critical business alignment. Alongside maintaining support for traders, TSS is exploring potential scope requirements to deliver the Windsor Framework (which sets out the latest EU/UK agreement on Northern Ireland) including the new 'Green Lane' for goods remaining in the UK. | 2020-06-29 | 2023-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-12-31 to 2023-12-31. This is primarily due to the following factors. We secured agreement from HMT to extend TSS for one year in order to maintain support for traders, while negotiations on the Northern Ireland Protocol were ongoing. The programme has delivered improvements and enhancements to the core customer journeys in the past 12 months, alongside supporting traders through guidance, online tools and targeted assistance. Since the publication of the Windsor Framework on 27 February 2023, TSS is exploring potential changes to support implementation of the Framework and the new 'Green Lane' for goods remaining in the UK. | 131.3 | 114.7 | -13 | The budget variance exceeds 5%. The cost of delivering TSS in 22/23 was lower than our baseline due to driving efficiencies within the running of TSS. | 532 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 379m. to 532m. This is primarily due to the following factors. We secured agreement from HMT to extend TSS for one year in order to maintain support for traders. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmentally-agreed monetised benefits at 22/23-Q4. There are no monetary benefits for this Programme as it is not driven by financial benefit. It is driven by necessity through an obligation to assure that trade between Northern Ireland and Great Britain continues to flow freely within the UK customs territory, supporting traders to meet their legal obligations under the Windsor Framework (previously the Northern Ireland Protocol). | HMRC_0029_2021-Q3
Unique Customer Record | HMRC | Government Transformation and Service Delivery | The Unique Customer Record Programme will deliver a single consolidated dataset relating to our customers (and their relationships to other customers) that will bring customers information and tax affairs together and linking them to historic contact information. It underpins the transformation of our end-to-end customer service, enabling customers to view all of their affairs through the single customer account and making it more straightforward for them to meet their obligations. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The delivery confidence is amber due to tight delivery timelines. Actions being taken to bring the programme back to green include ensuring delivery plans remain on track and within budget allocation. | 2021-04-12 | 2024-05-07 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2026-07-01 to 2024-05-07. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2026-07-01 to 2024-05-07. This is primarily due to the following factors. As the programme is now more mature in its lifecycle, it now has more accurate plans. This is reflected in the current programme end date which the programme remains on track to meet. | 24.5 | 19.6 | -20 | The variance is largely due to the reduction in contingent labour costs and build costs | 96 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 140m. to 96m. This is primarily due to the following factors. The decrease is largely due to the reduction in IT Costs, paybill and contingent labour costs. There has also been a reduction in the 23/24 budget allocation. | 175 | The project's departmental-agree monetised benefits at 22/23-Q4 is 175m. The UCR Programme will deliver a consistent unique customer record for each of our customers and implement changes to Business Ownership and management of data that permanently maintains the integrity of that Unique Customer Record as a corporate asset. The monetised benefits represent increased tax and compliance yield | HMRC_0033_2122-Q3
Unity Programme | HMRC | Government Transformation and Service Delivery | The shared service strategy for government launched in March 2021 setting out the vision to transform Shared Services across the Civil Service improving end users experience. To achieve this 5 clusters have been formed across the civil service. HM Revenue & Customs (HMRC), Department for Transport (DfT) and Department for Levelling Up, Housing and Communities (DLUHC) collectively make upthe Unity Programme. The Unity Vision is to transform HR, Finance and Procurement across HMRC, DfT and DLUHC groups, creating a unified shared service which is user centric, swift and cost effective. Our colleagues will be empowered through intuitive, streamlined and automated processes, improving their experience and enabling everyone to spend more time delivering essential servicesfor the public. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. The quarterly assessment has changed to red for this quarter. This recognises that the Programme has a number of key design decisions outstanding, which all three departments must agree, in order to remain on our critical path to stand up shared services for HMRC and Department for Transport in June. The programme also lacks a number of critical skills and dedicated resources, which further puts progress at risk. The programme has been working with its delivery partner to create a critical decision path and a back to amber plan which has been agreed with the Programme Board. The programme will be focusing on this plan over the next quarter, to get key decisions agreed, key resources in place and build stakeholder confidence in the plans in advance of moving into the delivery phase. The lifecycle RAG is deemed amber as we can deliver against end lifecycle outcome. | 2021-02-01 | 2026-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-12-31. This is primarily due to the following factors. Our current planning assumption is that we will complete the programme and stand up the full HMRC led shared service function (people and systems) by the end of 2026 for HMRC and Department for Transport, with Department for Levelling up Housing and Communities joining in 2026/27. This is in line with the shared services strategy for government. | 26.09 | 17.46 | -33 | Programme costs were significantly lower than originally forecast in 22/23. The Outline Business Case was not approved until November 2023, which was much later than anticipated and meant that the delivery phases of the programme were pushed back. The Technology Delivery Partner was therefore appointed in Q4, later than originally planned, the programme team was not ramped up until Q4 and the next version of the business case pushed into 23/24 which meant that the original plans to spend 3.3m on a Technology Delivery Partner in 22/23 did not materialise. | 214 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 145m. to 214m. This is primarily due to the following factors. The project's departmentally-agreed Whole Life Cost at 22/23-Q4 is 214m. This is due to: The Whole Life Costs of the Programme are made up of IT solution implementation costs, costs to create the Shared Service (people, transition and business change etc), cost of the programme team and Subject Matter Experts to deliver programme, commercial, and delivery partner costs. The Programme's previous GMPP returns reported costs until 25/26 , this now reflects Whole Life Cost up until 31/32. | 43 | The project's departmental-agree monetised benefits at 22/23-Q4 is 43m. The project's departmentally-agreed monetised benefits at 22/23-Q4 is 42.576m. This is due to: The Programme is forecasting 42.58m sustainable efficiencies over the life cycle, with cumulative efficiencies of 238.72m. This is an increase in cumulative savings of 8.65m due to increased IT savings (0.38m) and staff productivity (19.6m), offset by a reduction in headcount savings (18.65m) due to the revised delivery timeline at our outline business case delaying benefit realisation to 2024/25. All assumptions are being revalidated in our preparation of the programme business case in Q1 23/24. | HMRC_0031_2122-Q3
NS&I Rainbow | HMT | Government Transformation and Service Delivery | The aims of the programme are to: 1. Measurably reduce the costs of running the business and growing revenue 2. Become a self-service digital business with support for the vulnerable and excluded 3. Deliver more nimbly, reduce risk and enhance scalability | Red |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (SRO rating) to Red (IPA rating). This is primarily due to the following factors. Since the last update, we have been focussing on replanning to obtain a re-baselined plan while continuing to close out dialogue activities. The Programme is now reaching the conclusion of procurement activities (with PPB due to complete by late Summer 2023) and therefore we are preparing the activities required for the move into a delivery-focussed programme. Given this, we would expect the Delivery Confidence to start improving over the coming months as more elements of the plan start to crystalise. Funding will remain a key item, however. We have remained in close dialogue with DRM about the expected envelope and approvals timeline over the summer. | 2019-06-03 | 2025-07-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-07-31 to 2025-07-31. This is primarily due to the following factors. We have:-Successfully achieved operational readiness for Procurement Package A and delivery is in the final phase.Recently identified the optimum procurement route for package B and have replanned and rebase-lined the Programme accordingly. A 1 year continuance to the incumbent contract to cover the delays due to the failed PPB procurement has been approved by HMT.We are in the process of exiting Dialogue for packages C & D and will shortly be issuing invitations to submit final tenders.Identified the winning bidder for B2B package E and are in the process of consulting our clients.Appointed our delivery partners for Service Integration and Management (SIAM) and Technology Build.Work is now starting on preparing the Final Business Case and preparing for the IPA Gateway 3 in June. | 56.89 | 35.75 | -37 | The Programme's ability to spend in line with our allocations and earlier forecasting has been impacted by factors including delays in onboarding the required programme resource impacting delivery to the original schedule particular PPB meaning associated costs will be incurred in future years instead of FY 2022/2023 | 1158 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1158m. This is primarily due to the following factors. Since the 2021-22 Q4 submission, we have gained clarity on, and refined a number of the assumptions used in the financial model which has led to a revised whole life cost.Package A cost estimates are now based on the awarded IBM contract plus agreed change requests. The forecasts for the remaining three main procurement packages are based on initial bidder submissions with adjusted timings to reflect the current plan. The current plan assumes the existing provider, Atos, will provide termination assistance services during 2024-25. The greater certainty associated with the updated assumptions has enabled us to revise the optimism bias calculation. We also gained clarity on the VAT position following independent advice and made updates. In addition to these changes, we have updated inflation assumptions in line with latest ONS estimates. | 590 | The project's departmental-agree monetised benefits at 22/23-Q4 is 590m. The project's departmental-agree monetised benefits at 22/23-Q4 is 590m.The project's departmental-agree monetised benefits at 22/23-Q4 is 590m.The project's departmental-agree monetised benefits at 22/23-Q4 is 590m. The Baseline Benefits are taken from the Outline Business Case. Benefits we noted at that time included:A reduction in FTE for delivery of the Customer Interaction Centre resulting from a move to more online self-service interactions.A reduction in FTE for back office operational processing as customers are able to complete more tasks online with fully automated processes.A reduction in print, paper and postage costs as customers move to paperless following online initiativesA reduction in debit card costs as customers move to more cost-efficient payment methodsA reduction in technology costs as we move to fully supported systems and less bespoke software. | HMT_0004_2021-Q2
Cerberus | HO | Government Transformation and Service Delivery | Border Force is making a transformative change to its analytics and targeting capabilities, better securing the border with improved operational outcomes, driving operational efficiencies, and therefore achieving considerable cashable savings through the decommissioning of expensive legacy systems. |  | Red | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (IPA rating) to Red (SRO rating). This is primarily due to the following factors. In Financial Year 22/23 Cerberus set out to deliver eight Level0 milestones, achieving five. Three milestones covering Air Passenger and Sea Containers modes have been moved or re-planned into future delivery. Our red rating reflects complexities in delivering Air Passenger and RoRo milestones at the end of Financial Year 22/23. A programme decision was made to focus delivery on achieving the RoRo milestone (met on the 31/03/2023), as a result the delivery of an Air Passenger Minimal Viable Product has moved into Financial Year 23/24. Discussions are currently underway to agree plans for an Air Passenger Minimal Viable Product. | 2019-10-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-04-01 to 2025-03-31. This is primarily due to the following factors. The original end date of the programme was recorded incorrectly in GMPP reporting and is now recorded correctly. | 43.9 | 43.9 | 0 | The budget variance is inferior or equal to 5%. Not required as variance is less than 5% | 198 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 172m. to 198m. This is primarily due to the following factors. Whole Life Cost - 198.2m (including sunk costs)- The Whole Life Cost of 172m excludes sunk costs. | 172 | The project's departmental-agree monetised benefits at 22/23-Q4 is 172m. The project's departmental-agree monetised benefits at 22/23-Q4 is 172m. At the end of Financial Year 21/22, Cerberus delivered functionality to the decommissioning of BSM system. Since this point associated costs have been saved which are cashable to the Home Office at a value of 0.5million per annum. At the end of Financial Year 22/23 further releases have enabled a reduction in FTS user licences resulting in a further 0.3million per annum cashable saving. This functionality is also forecast to realise benefits associated with increased threat interdiction. A proportion of these can be monetised with a value of approximately 9.3million over the appraisal period. Further technology savings will be realised later than originally forecast due to delays of project milestones. Delivery in Air passengers and Sea container modes will realise a further 11.7million per annum cashable savings in this area. Interdiction benefits will also continue to accrue and increase up to a total of 65.9million of monetised benefits over the appraisal period, alongside strategic benefits from non-monetised threats. Further delivery will also facilitate efficiency savings cashable to the Home Office with a value of approximately 7.0million over the appraisal period. Further efficiency benefits are expected from increased automation, but these have not yet been quantified. This is an area of focus in the near future. | HO_0042_2021-Q3
Digital Services at the Border (DSAB) | HO | ICT | To deliver digital services that will provide systems capable of transforming the way that Border Force (BF) and its partners operate. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The work to deliver a second data centre has taken longer than planned as it was being developed in parallel to previously untested capability. It was delivered in February 2023 and constitutes a major milestone towards providing appropriately resilient services and disaster recovery to a Critical National Infrastructure. Work to develop Helios (the replacement watchlist) has been delayed whilst work to develop a new Personal Search Algorithm is completed that meets the requirements for a Critical National Infrastructure. Several change requests have identified additional Must Have requirements to enable the new Watchlist to go live. The impacts are currently being assessed and a revised delivery schedule is to be proposed shortly. | 2014-02-12 | 2023-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-04-30 to 2023-09-30. This is primarily due to the following factors. The later than planned delivery of the second data centre The need for an updated person search algorithm that is compatible with a critical national infrastructure. Continuing shortages in global supply chains Continuing difficulties in the recruitment of resources with the requisite technical skills Additional Must have requirements to keep pace with the latest technology. | 56.69 | 71.78 | 27 | The budget variance exceeds 5%. DSAB has spent 71.8million against a budget of 61.7million, an overspend of 10.1million. DSAB began 22/23 with a budget of 57million and annual run rate of 95million+, a financial challenge of over 38million, or +66% of the programmes entire budget. Initial sentiment for overcoming this issue was positive, since early planning indicated an end or at least significant ramping-down of delivery activity in November 2022. However, technical milestones quickly moved out to beyond the end of the financial year, leaving DSAB facing the certainty of an adverse financial variance that would need to be mitigated as quickly and as fiercely as possible. DSAB finance has spent the entirety of the past financial year striving to close the gap between actual spend and allocated budget. Overall, despite numerous increases in monthly costs across multiple workstreams and immense pressure from continual high-value recharges from DDaT N&I and ES, DSAB has ended the financial year within 1% of the programmes Period 11, Period 6, and average full-year forecast accuracy targets. | 596 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 596m. This is primarily due to the following factors. At this time, DSAB change programme activity has continued for an entire financial year beyond the planned closure/completion date of 31st March 2022, and said activity is not expected to cease until Quarter 2 of 2023/24. These increased timescales have inevitably resulted in increased Whole Life Cost, whereby programme delivery has and will continue to be performed for two additional financial years (i.e. 22/23 and 23/24), offset by deferred Business As Usual /Run costs during that same time period. Overall, Whole Life Cost have increased over the course of this year's GMPP reporting in order to reflect lack of closure at the end of 21/22 and current programme forecasting to Quarter 2 of 23/24. | 15 | The project's departmental-agree monetised benefits at 22/23-Q4 is 15m. The project's departmental-agree monetised benefits at 22/23-Q4 is 15m. Whilst DSAB has delivered elements of its scope, until it completes delivery, the benefits cannot be fully realised, although the end users/business may be benefiting from part of the delivered outputs EG. Border Crossing. This also highlights that all benefits will not be realised until completion of DSAB, and many will evolve quickly with the hand over to Future Border and Immigration System (FBIS) to build upon the foundations DSAB has delivered for onward development and improvement. The wider reaching security benefits were not quantified as deemed too difficult to assign a value and are not limited to DSAB and will traverse across FBIS and Migration & Borders to track the benefit realisation. The benefits will be reviewed as part of the wider programme closure in light of the change of scope. A review of the economic case has been undertaken. | HO_0031_1415-Q1
Emergency Services Mobile Communications Programme (ESMCP) | HO | Infrastructure and Construction | Emergency Services Mobile Communications Programme (ESMCP) is a cross government programme to deliver the new Emergency Services Network (ESN) critical communications system; replacing the current technology Airwave. ESN will transform emergency services' communications, by moving away from the largely 'voice only' proprietary and legacy Airwave radio system to a new combined voice and data service that leverages off-the-shelf technology and reuses commercial mobile telephone networks. Enhancements exist to prioritise emergency service calls above regular commercial traffic on the mobile network. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. The Programme has closed most of the recommendations from its last Independent Project Assurance Review (PAR) in January 2023. A review of progress against the January 2023 PAR actions is being undertaken in April 2023, followed by a session with the Major Programme Review Group (MPRG) on 21 April 2023. The programme have updated their commercial strategy, and are working through the procurement, governance and compliance for the contracts. Actions are underway to address the other outstanding PAR recommendations relating to skills, resourcing and security. | 2011-06-01 | 2026-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-12-31. This is primarily due to the following factors. ESMCP is updating its Full Business Case (FBC) to gain endorsement on the direction of travel and agree the delivery timetable and costs to complete the programme.Furthermore, with a new supplier expected to be procured in 2024, our forecasts for completing the transition from Airwave to ESN and then the shutdown date of Airwave is yet to be confirmed. | 890.34 | 728.74 | -18 | The budget variance exceeds 5%. The overall forecast underspend is mostly driven by a change in Programme delivery plans and the exit of a key supplier. Some activities identified that could be paused/delayed during the substantial shift in the commercial arrangements and re-procurement, along with coverage build re-plans. These underspends and deferred activities are moving costs and timelines to the right. The impact will be reflected in the next iteration of the Business case. | 11263 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 12026m. to 11263m. This is primarily due to the following factors. The whole Life budget cost is based on the last approved full business case July 21. Whole Life cost include ESN programme, ongoing run and legacy Airwave costs. The full business case is currently been updated. | 3746 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3746m. The project's departmental-agree monetised benefits at 22/23-Q4 is 3746m. | HO_0016_1213-Q1
Fraud And Cyber Crime Reporting and Analysis Service | HO | Government Transformation and Service Delivery | The Fraud and Cyber Crime Reporting and Analysis Service (FCCRAS) is a 150m transformation programme that will replace the existing system and services for reporting and analysis of fraud and cybercrime through Action Fraud and NFIB (National Fraud Intelligence Bureau). Action Fraud and NFIB are run through the City of London Police(CoLP) and are national services because fraud and cybercrime span beyond geographical boundaries and so localforce responses are ill-suited to tackle these crimes. These services are jointly funded by the Home Office (majority funder) and the City of London Corporation. The objectivesGovernment haveidentifiedfor the programme to deliver are: improved victim experience and satisfaction, lead to better criminal justice outcomes, prevent crime and reduce harm, contribute to an improved understanding of the threat from serious and organised crime and improve systems inter-operability and align with national programmes. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The IPA assessment and recommendations were welcomed. As Senior Responsible Officer, I recognise the recommendation for ensuring there is a clear and agreed plan with suppliers to develop and deliver a minimal viable product and transition to the new service and this process is under way. This process will give greater confidence of success in our go-live date for the new service in March 2024. We also welcome the recommendation for a continued emphasis on recruiting and retaining the team to deliver, including the continued visibility of any issues with the FCCRAS Programme Board, and have a dedicated workstream to ensure our capacity to delivery is maintained and grown. | 2020-09-01 | 2024-08-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-08-31. This is primarily due to the following factors. The replacement of the existing system continues to be planned for Go Live in March 1 2024. All preferred suppliers have now been selected, and the Full Business Case, that will enable contracts to be signed ahead of the Discovery phase of the programme, passed its final approval stage for 31 March 2023. | 29.27 | 29.27 | 0 | Not required as variance is less than 5% | 224 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 226m. to 224m. This is primarily due to the following factors. In the September 2021 Outline Business Case (OBC) the whole life revenue costs were budgeted to be 193m (with a shortfall of 13m for current supplier legacy costs) and whole life capital costs to be 33m. Revised whole life revenue costs and whole life capital costs based on the Full Business Case, that was approved on 31 March 2023, will be included for the 2023/24 GMPP returns. | 402 | The project's departmental-agree monetised benefits at 22/23-Q4 is 402m. The project's departmental-agree monetised benefits at 22/23-Q4 is 402m. On 31 March 2023, the Full Business Case (FBC) was approved. The FBC has revised the baseline benefits net present value (NPV) of 340.2million. This revised benefits assessment still remains strong and includes several non monetised benefits that have not been captured in the cost-benefit analysis. These benefits includes functionality to protect more businesses and people through giving targeted, timely advice on how to avoid the latest threats, and increased ability to block and disrupt crime through providing real time information to institutions and organisations who can take down the fraudulent sites, activities and bank accounts we know are enabling criminal activity. | HO_0045_2122-Q1
Future Border and Immigration System Programme | HO | Government Transformation and Service Delivery | The United Kingdom exited the European Union on 31 January 2020. From 1 January 2021, free movement ended and was replaced by a new points based immigration system. The Future Border and Immigration System will enable the United Kingdom to take back control of our border, it will simplify, enable and digitise our systems to put customers at the heart of a firmer, fairer and easier to navigate border and immigration system. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The programme received a delivery confidence rating of Amber for the whole of the programme following an Independent Review (September 2022). The programme have looked to address a number of actions following the review, including reviewing how strategic intent for the Enable pillar is framed through establishing the Enable Board where stakeholders agreed the role and scope of Enable. The programme has also clarified and documented plans for the transition of completed projects and products into the business as usual operating environment, formulating a Transition Team alongside resourcing changes and funding work to ensure projects/products are subject to normal budget planning processes once in business as usual. | 2018-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. Compared to 2022-Q4, programme end-date remained scheduled to finish on 31 March 2025. This is primarily due to the programmes flexible approach in relation to delivery which has seen the re-prioritisation of programme deliverables resulting in continued successful delivery throughout 21/22. We do however continue to see additions to the plan because of the ever-changing political climate (Ukraine, Plan for Growth, ongoing discussion on net migration and the operation of the points-based system, etc). Currently the programme finish date hasnt change but continued additions to scope is increasing the risk delivery timescales if this continues. | 404 | 273.2 | -32 | The budget variance exceeds 5%. Optimism bias and contingency totalling 71m that was removed as part of spending review allocation. This results in the programme showing a larger under spend vs baseline than actual budget. In-year budgets were reduced by 10m in line with Optimus savings in Q1 and further savings have been identified with Digital Data and Technology Capital Departmental Expenditure Limit project lines, programme resource and Comms Media & Marketing through in year re forecasts. FBIS continues to take a proactive approach to managing underspends and addressing optimism bias in workforce plans. At P06 it was agreed that forecasts would reduce by a further 31m to return funds centrally early and ensure programme budgetary governance remains robust. The programme continues to deliver against key milestones despite taking on additional scope. | 3428 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 3357m. to 3428m. This is primarily due to the following factors. Costs are for the development and implementation of the United Kingdoms Future Border and Immigration System; as well as the running costs for the additional demand as a result of the new system.Figures up to and including 22/23 are based on actual expenditure and end year forecasts. Baselines from 23/24 and beyond have been taken from a departmentally approved Programme Business Case produced in Autumn 2021. The FBIS Business Case is due to be refreshed in April 2023 and the GMPP will be refreshed with latest figures in Q1 of 23/24. | 40905 | The project's departmental-agree monetised benefits at 22/23-Q4 is 40905m. The project's departmental-agree monetised benefits at 22/23-Q4 is 40905m. The Programme will help to deliver a range of benefits to its customers, the Home Office, UK economy and wider international economy. The Simplify Pillar will continue to deliver a simplified immigration process through the improvement of existing routes and introduction of new ones and the delivery of a digital, simplified, and modern sponsorship system that enables a more efficient operation for users.The Enable pillar will transform the customer and caseworker experience through implementing and enabling digital systems. Modern services and aligned customer and caseworker capacities are vital for the successful delivery of the Programme and enhancing border security.The Digitise Pillar will utilise technology to improve border security. This will be achieved through watch listing and analytics to identify at risk persons before they arrive to the UK. This Pillars aim is to create an end state of contactless border, where passports and documents are replaced by biometrics. | HO_0039_1920-Q4
Future Suppliers Services | HO | Government Transformation and Service Delivery | Future Supplier Services (FSS) aims to re-procure UK Visas and Immigration's (UKVI) United Kingdom and overseas front-end customer services to primarily provide biometric information to support their visa application and, in certain circumstances attend interviews. These services are currently outsourced under the Front-End Services United Kingdom and Next Generation of Outsourced Visas contracts and the project is procuring equivalent services to maintain visa services; while maximising value and efficiency, which is a critical enabler for building and sustaining the United Kingdom's growth and prosperity. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Amber rating reflects the programme re-baseline of timelines due to slippage in procurement activities. We remain confident that the service we are procuring will deliver the expected benefits, and that the procurement for the service remains competitive. We are working to mitigate the risks to the schedule, and ensure contingency is in place to ensure FBC approval and begin the implementation phase. | 2019-12-12 | 2024-10-28 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-07-31 to 2024-10-28. This is primarily due to the following factors. Due to the delay in completing the Best And Final Offer procurement process slipping by six weeks, the programme timelines have been re-baselined. This has reduced the RAG rating of the programme and increased confidence in programme delivery. | 46 | 5.55 | -88 | The budget variance exceeds 5%. The baseline totals are based on Outline Business Case, however, the programme has been delayed by a year due to external circumstances. Finances are being reviewed and updated as part of the Full Business Case, which is being completed at the moment, and is due submitted for internal approval in May 2023 when the programme will update its forecast and re-baseline the costs | 637 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 637m. This is primarily due to the following factors. The programme remains within the OBC Envelope |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. The overriding benefit of the FSS programme is to provide business continuity. Without these new contracts, there would be a complete shutdown of Visa application services due to an inability to perform visa enrolment, facilitate digital interviewing, or provide support to UKVI customers requiring touchpoint assistance. These front-end services are key to ensuring UKVI continues to deliver Visa services to all customer groups and preventing digital exclusion.UKVI has ensured that current contracts do not end before new arrangements are in place, to ensure continuation of business-critical services, and thus fulfilling Home Office statutory and regulatory obligations. | HO_0043_2021-Q4
HMPO Transformation | HO | Government Transformation and Service Delivery | His Majesty's Passport Office (HMPO) Transformation Programme aims to modernise the passport business by digitising the end to end process and by automating much of the application assessment work. This will provide His Majesty's Passport Office cashable savings and improve the customer experience. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. The recent review has reduced the Programme RAG status to Amber reflecting several changes introduced to meet previous review recommendations. And whilst His Majesty's Passport Office is confident it will achieve the programme objectives, extensive work is also concluding on the re-baselined delivery plan as discussed at the recent review, with reviewed options to deliver best value for money. The final internal agreed option will be presented to Finance Investment Committee in April 2023. | 2016-04-01 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. Work is concluding on the rebaselined delivery plan, with reviewed costs and options to deliver best value for money. The current forecast for Programme end is 2025, The final internal agreed option will be presented to Finance & Investment Committee in April 2023. | 86.39 | 86.39 | 0 | The budget variance is inferior or equal to 5%. Not required as variance is less than 5% | 709 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 289m. to 709m. This is primarily due to the following factors. The project has rebase lined during this period and the new figures includes the resource dual running cost for the period and the business as usual run costs beyond that point which the previous figures didn't. The overall project based whole life cost over the comparable period to the previous years report are currently at 288.86m which is a reduction on last years forecast by 0.38m due to minor changes to forecast and actual spend across the programme. | 230 | The project's departmental-agree monetised benefits at 22/23-Q4 is 230m. The project's departmental-agree monetised benefits at 22/23-Q4 is 230m. The programme has already delivered benefits of 30m per annum and the above is the remaining benefits over a 10 year period. Once the programme has full rolled out by April 2025 the benefits are expected to be a further 30m per annum based on operational efficiencies and contract cost savings. | HO_0044_2021-Q4
Home Office Biometrics (HOB) Programme | HO | ICT | Home Office wide convergence programme for biometrics within Home Office, covering border security, law enforcement and intelligence | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. A review at the end of March 2023 delivered an Amber rating. Since the previous review all recommendations have been completed and good progress has been made in the delivery of key projects and the re-procurement to replace the strategic matcher supplier. There remain supplier challenges which could impact the programme but these are being carefully managed and addressed by the programme team to ensure delivery through 23/24 remains on track. | 2014-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-09-30 to 2025-03-31. This is primarily due to the following factors. The programme has successfully delivered a number of key projects during 22 / 23, however the Programme end date has been impacted by challenges to the delivery of the Strategic Matcher Project, and the decision to run the delivery contract through to a conclusion in February 2023. The later end date is to provide a smooth transition to the new supplier subject detailed negotiations as part of the procurement process and accommodate the now later and staged delivery of Strategic Matcher capabilities, and ensure completion of the programmes strategic scope. | 85.9 | 85.9 | 0 | The budget variance is inferior or equal to 5%. Not required as variance is less than 5%. | 1222 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1148m. to 1222m. This is primarily due to the following factors. Challenges delivering the Strategic Matcher Project and increased costs for overall delivery, including increased costs for the new supplier for Strategic Matcher and the extension to the Programme End Date. | 1002 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1002m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1002m. The HOB programme will provide significant quantified non cashable benefits. The programme is a key enabler for business areas and benefits will be directly visible to a variety of end users. | HO_0033_1415-Q3
I-LEAP | HO | Government Transformation and Service Delivery | The I-LEAP programme will provide new alerting digital platform capabilities to police and border officers in the UK, and to their equivalents in partner countries, enabling increased opportunities at the national border or within country to identify persons and objects of interest to law enforcement agencies. It will do so by first enhancing the UKs connectivity with INTERPOL by providing law enforcement agencies with a real-time connection to INTERPOL datasets (Phase 1). In the longer-term (Phase 2), I-LEAP will also enable real-time alert exchange with key international partners who share the UKs interest in further strengthening alert-sharing capabilities. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The I-LEAP programme achieved a number of critical delivery milestones during 2022/23. In April 2022 approval was gained for wider I-LEAP rollout, following successful pilots to police forces. A Gateway 0 Review was undertaken in September 2022. and an Amber delivery confidence assessment rating was provided. A second iteration of the Full Business Case was approved in 22/23 to reflect the programme now aiming to secure a multilateral agreement with the EU. As of March 2023 the programme now has 6 live forces using I-LEAP, 5 of which have all 3 INTERPOL datasets (nominals, stolen vehicles, lost, stolen and fraudulent travel documents). Over 800,000 searches have been conducted using I-LEAP since commencement. | 2020-06-09 | 2028-01-28 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-04-01 to 2028-01-28. This is primarily due to the following factors. The project end date has been adjusted to January 2028 which reflects the expected I-LEAP Phase 2 completion date (rather than April 2024 which is when Phase 1 is due). The current priority of the programme is delivering Phase 1. There are known risks to the schedule, such as rollout to UK Border Force, which are being actively managed and mitigated. Phase 2 is in the early phases of development and the schedule remains dependent on achieving international agreements with the EU and other countries. | 10.48 | 9.2 | -12 | The baseline total is from the latest I-LEAP business case. The in-year variance of 1.28m between baseline and forecast represents the removal of costs related to potential retrospective VAT charges and an identified underspend on external delivery partner costs. | 90 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 76m. to 90m. This is primarily due to the following factors. An updated business case has been approved, with a whole life cost of 90.19m from FY22/23. There are several factors which have driven the increased cost, including the move to a multilateral approach with the EU, and higher levels of optimism bias in the forecasting. | 125 | The project's departmental-agree monetised benefits at 22/23-Q4 is 125m. The project's departmental-agree monetised benefits at 22/23-Q4 is 125m. The benefits for the programme are non-cashable and are at the societal benefit level in alignment with law enforcement policy priorities. | HO_0048_2122-Q1
Immigration Platform Technologies (IPT) | HO | ICT | The Immigration Platform Technologies (IPT) Programme is delivering the technology and information systems to support the immigration service through delivery of three integrated modern technology services that are cheaper to operate than those they replace. IPT will achieve operational efficiencies, optimise use of data and provide a more modern and streamlined customer journey. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. This increased delivery confidence is due to the Programme delivering to schedule against the revised 2022 programme plan and remaining on track to close September 2023. | 2013-04-01 | 2023-01-27 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2021-10-29 to 2023-01-27. This is primarily due to the following factors. Due to elements of the programme previously being underestimated and Departmental priorities impacting planned betas the Immigration Platform Technologies programme plan was revised. The revised plan, which schedules programme closure in September 2023, received approval April 2022 and the Programme is delivering to schedule. | 70.99 | 69.59 | -2 | The budget variance is inferior or equal to 5%. Not required as variance is less than 5% | 719 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 337m. to 719m. This is primarily due to the following factors. The programme has revised the programme plan due to elements of the programme previously being underestimated and Departmental priorities impacting planned betas. This caused extension of the programme timelines and required retaining delivery resources for longer. The impact to future costings has been reflected in the 2022/23 programme business case. IPT Whole Life Costs have increased due to extended programme timeline to c. September 2023 from previous business case iterations; additional run costs of Casework Information Database have been taken on by the programme as a result of not having gone live, and therefore the Business As Usual organisation not having funding for those excess run costs. | 183 | The project's departmental-agree monetised benefits at 22/23-Q4 is 183m. The project's departmental-agree monetised benefits at 22/23-Q4 is 183m. IPT has delivered elements of its scope and has begun realising benefits. However full benefit relisation will not occur until the decommisisoning of the legacy system CID (Casework Information Database) | HO_0029_1314-Q4
National Law Enforcement Data Programme (NLEDP) | HO | ICT | With the expansion of the National Law Enforcement Data Portfolio (NLEDP) we are now known as the Law Enforcement Data Service (LEDS) programme. The LEDS Programme is delivering a replacement to the current Police National Computer (PNC) service which will facilitate a range of future transformational capability and functionality that will be at the heart of protecting the public for years to come, aiming to replace the current PNC to enable retirement on PNC by March 2026. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The programme leadership is strengthened by the appointment of a permanent, highly experienced Programme Director and new Senior Responsible Owner who brings a wealth of experience from a Policing background. The programme remains large and complex with areas of significant risk which are closely managed and monitored.Stakeholder relationships between Policing and the programme are very strong, with evidence of effective integrated joint working and ownership at the Force level. Adoption is well advanced with five key products rolled out and others in development.There is confidence that the programme is now in a position to successfully deliver a PNC equivalence, or better, by March 2026. It is appropriate that the programme now starts to focus on the complex choreography of moving away from PNC and, in parallel, work up the full transformation vision for a law enforcement data capability that will service a vast array of customers. | 2014-04-01 | 2025-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-12-31. This is primarily due to the following factors. The programme has completed reset, the revised end date of the 31/12/2025 was agreed as part of the business case approved in July 2021 to complete the required delivery and adoption activities to replace PNC before it ceases to operate on 01/04/2026. LEDS has moved to a product-centric delivery approach with continuous, user-centred product delivery, a proven approach to de-risk a complex critical national infrastructure programme.The programme successfully released Photos at the Road Side(P@RS), Property, Drivers, Vehicles products to users underpinned by Audit capability all via the strategic Law Enforcement Cloud Platform(LECP). Property will be fully transitioned from PNC later this year with Drivers and Vehicles searches reaching Public Beta around the same time. 2-Way Replication has been demonstrated successfully but needs to be coupled with a LEDS product functionality to give more confidence in its capability, anticipated to be in place through Wanted Person capability later this year. | 63.74 | 55.39 | -13 | The budget variance exceeds 5%. The variance (c8.5million) arose due to 3 main factors. 1. The Programme received a VAT 'credit' against the accruals for prior Financial Years of c3million. 2. Procedural issues arose with regards to certain elements of the forecasted Adoption Grant; this resulted in a c3.5million underspend. 3. Whilst the programme resources have increased considerably (from 139 Fixed Term Employees last report to 293 Fixed Term Employees this report) the projection was for a slightly higher number of resources to be on the Programme by end of year, due to delays in onboarding. This reduction in resources cause a c2million underspend. | 602 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 736m. to 602m. This is primarily due to the following factors. The Baseline Whole Life Cost (WLC) in the previous report (c736million) was based on the Programme pre-reset; this pre-reset WLC was also far greater than the forecast in the previous report (based on actuals and future forecast) of c589million. This report has updated the baseline from the pre-reset to the post-reset baseline hence the reduction. When we compare the forecast in the previous report (c589million) to the current forecast (c602million) there is a c13million increase which is due to the Programme having a greater understanding of the requirements (against assumptions) and certain roles which were not in the previous report (e.g. enhanced Security and Engineering & Architecture teams) which has resulted in the increase. | 523 | The project's departmental-agree monetised benefits at 22/23-Q4 is 523m. The project's departmental-agree monetised benefits at 22/23-Q4 is 523m. The total benefits baseline has increased from 520.96 (million) to 523.35 (million). This is because of an improved forecasting methodology which has led to reapportionment of benefits. This has meant that there has been an increase in Government non cash-releasing benefits and wider UK public benefits as well as a decrease in government cash releasing benefits and the introduction of dis-benefits. The dis-benefits arise from officers needing to be trained to use both the old and the new system while both systems are being dual run. | HO_0036_1617-Q2
Nuclear Security Portfolio | HO | Government Transformation and Service Delivery | Nuclear Security Portfolio has been established to maintain and improve the UKs defences from radiological and nuclear terrorism, and its preparedness for such a risk. | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | 2021-03-26 | 2023-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2025-03-31 to 2023-09-30. This is primarily due to the following factors. Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | HO_0047_2122-Q1
Police Uplift Programme | HO | Government Transformation and Service Delivery | In July 2019 the government committed to recruit 20,000 additional police officers in England and Wales by March 2023. As a result, the Police Uplift Programme was established to support the 43 police forces across England and Wales in the recruitment of the additional officers. The programme is a collaboration between the Home Office, the National Police Chiefs Council and the College of Policing, reflecting the nature of policing. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. With the support of the PUP, policing across England and Wales, recruited 20,000 additional officers. Stats were published by the Home Office on 26 April 2023, that showed that as at 31 March 23, 20,951 additional officers have been recruited. This achievement is testament to the hard work of policing and the support of the collaborative programme. So much so, that the PUP won Project Delivery Team of the Year Award at the 2023 Government Project Delivery Award. The programme continues to prepare for closure by the end of Quarter 2 23/24, with the IPA undertaking a Gate 5 review in June 2023, before submitting formal closure documentation over the summer to the HO and IPA. The programme is working with the HO and the IPA to prepare for closure by the end of Quarter 2 23/24. | 2019-07-29 | 2023-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2024-03-31 to 2023-09-30. This is primarily due to the following factors. Policing has recruited the additional officers, as scheduled. The programme is continuing preparations for closure, as planned, by the end of Quarter 2 23/24. | 1687 | 1687 | 0 | The budget variance is inferior or equal to 5%. Not required as variance is less than 5% | 3649 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 3646m. to 3649m. This is primarily due to the following factors. The Whole Life Cost of the Uplift is 3.6 billion over 5 years. The 1.2 billion that was previously reported reflected the additionality each year and central funding to 21/22. The 3.6 billion reflects the totality of funding from 19/20 to 22/23. In 19/20 PCCs were provided 28.8 million to kick-start recruitment. In2020/2021,700 million was allocated to PCCs atthe Police Settlement for the first 6,000 additional officers, with some funding for financial pressures. For 21/22 for the next 6,000 additional officers, up to 425 million has been provided to policing - 423 million to PCCs and 2 million to CoLP for fraud. The previous years 700 million was maintained in the baseline. For 22/23, PCCs were provided a further 550 million for the remaining 8,000 additional officers support financial pressures. The 23/24 Police Settlement provides 3 million for programme closure in 23/24. The settlement also provides funding for forces to maintain additional officers. | 20140 | The project's departmental-agree monetised benefits at 22/23-Q4 is 20140m. The project's departmental-agree monetised benefits at 22/23-Q4 is 20140m. The Home Office Finance and Investment Committee agreed in June 2021 that the benefit of the PUP is the 20,000 additional officers, as the programme is the supporting infrastructure to recruit the additional officers. Forces are responsible for recruiting the additional officers. However, these figures will not be presented in the GMPP return.The programme has agreed with PPD (following consultation and engagement with relevant parts of the HO) the best way to present the forecast benefits of the PUP, totalling 20.13bn (PV) over the appraisal period, against the baselined figures taken from the FBC agreed to by FIC in 2022, also totalling 20.13bn (PV) over the appraisal period (of which 6.95bn is related to the cost of just the 8,000 remaining officers). The benefits are societal benefits as a result of the investment in policing but fall beyond the agreed remit of the programme and are therefore not owned, tracked or monitored via the programme. The HO is currently developing how it will assess the impact on policing of an increased workforce, which the HO will be responsible for, as it will continue beyond the lifetime of the programme (supporting forces to recruit by 2023).As part of closure activity, the Home Office has developed an evaluation plan to understand the impact of additional officers. Ministers have agreed the plan, and engagement with policing has commenced | HO_0041_2021-Q3
Sovereign Borders | HO | Government Transformation and Service Delivery | Delivering a fair but firm immigration and asylum system cracking down on abuse of the system and supporting those needing the UKs protection through fundamental end-to-end system reform; a new system differentiating those genuinely in need of our protection from others; judicial reforms; and effective returns. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. November 2022 Gate 0 awarded the programme an Amber delivery confidence rating reflecting the good progress in moving the programme from policy to delivery phase. An action plan is in place to address the recommendations which will be completed in April. | 2020-04-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The programme is on track to complete phase 2 at the end of March 2023. Rescoping work is currently underway to reflect that implementation of the Illegal Migration Bill will be delivered through the programme and phase 3 deliverables will now come on stream from October 2023. | 52.9 | 47.5 | -10 | The programme came in under budget for 2022/23 due to later than assumed Royal Assent of Nationality & Borders Act, delays in recruitment of operational staff and better understanding of delivery costs. | 1574 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 1574m. This is primarily due to the following factors. Whole life costs will be reviewed as the approach to implementation of the Illegal Migration Bill becomes clearer | 5057 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5057m. The project's departmental-agree monetised benefits at 22/23-Q4 is 5057m. The monetised, non-cash releasing and wider economic benefits have been presented in this GMPP return. These benefits will be reviewed as the approach to implementation of the Illlegal Migration Bill becomes clearer. Additional non-monetised benefits include social benefits, including (but not limited to) increased and improved support for migrants and reduced injuries and fatalities. | HO_0034_2122-Q3
Suspicious Activity Reports (SARS) Reform | HO | Government Transformation and Service Delivery | The Economic Crime Plan, jointly published by Home Office, His Majesty's Treasury and UK Finance in July 2019, includes commitments to Suspicious Activity Reports (SARs) reform, recognising the regime as the cornerstone of our whole response to economic crime. Through a whole system approach to economic crime, SARs Reform Programme is addressing 3 out of the 52 actions in the Economic Crime Plan to enable higher levels of detection, prevention, and enforcement (nationally and internationally): Action 30: SARs IT transformation and a design for the SARs regime target operating model. Action 31: Greater feedback and engagement on SARs. Action 32: Ensuring the confidentiality of SARs. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. The programme is currently reporting as green and are on-track to deliver all projects as planned. The first capability release for the new SARs IT Digital Service replacement (The Bulk Release) successfully went live in March 23, with the remaining SARs IT service delivery in planning stages and on track for a Q1 24/25 delivery.The UK Financial Intelligence Unit (UKFIU) uplift was successfully delivered in March 23, with project closure processes commencing. | 2018-12-17 | 2024-07-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2024-04-02 to 2024-07-01. This is primarily due to the following factors. The programme's delivery of its outcomes and benefits remains on-track. The IT Transformation's Bulk Release successfully went live in March 23; the UK Financial Intelligence Unit (UKFIU) expansion was also successfully delivered in March 23.The remaining SARs IT service delivery went through a re-planning exercise which led to the project end date shifting by 3 months - it is now in the Discovery phase. Alpha and Beta phase(s) are on track. | 18.09 | 18.45 | 2 | Not required as variance is not more than 5%. | 138 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 133m. to 138m. This is primarily due to the following factors. The whole life cost of the programme has increased to c138m due to additional funding allocated to stand-up a full National Crime Agency (NCA) IT project team, to ensure they're fully resourced to deliver the IT transformation project. The programme has also allocated additional funds for the development of the full SARs IT replacement, with the introduction of new suppliers to deliver Alpha and Beta phases, following the departure of the Bulk Release delivery supplier, ATOS. | 410 | The project's departmental-agree monetised benefits at 22/23-Q4 is 410m. The project's departmental-agree monetised benefits at 22/23-Q4 is 410m. Due to a more detailed understanding of the programme's Defence Against Money Laundering (DAML) benefits, we have seen an increase in our overall baselined monetised benefits from 400m to 410m | HO_0040_1920-Q4
A400M | MOD | Military Capability | To deliver into Service a worldwide, protected Tactical Air Transport capability able to rapidly project, sustain and recover Air and Joint Forces, to meet UK standing commitments and support enduring and contingent operations in the most demanding timescales. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. A400M Atlas is rapidly gaining capabilities at a faster rate than previously expected, in some cases several years ahead of the schedules anticipated during the 2020 Integrated Defence Review. However, residual risk remains. | 2000-05-17 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-03-31. This is primarily due to the following factors. NA | 228.41 | 210.56 | -8 | The budget variance exceeds 5%. This is primarily due to the following factors:An underspend is currently forecast following the reprofiling of final delivery requirements. | 3817 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 3802m. to 3817m. This is primarily due to the following factors. Principally the result of fluctuations in foreign exchange rates. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0001_1112-Q1
Armed Forces Recruiting Programme | MOD | Military Capability | The Armed Forces Recruiting Programme is the Tri-Service programme responsible for delivering a single; common Tri-Service Recruiting Operating Model for the Armed Forces. The Programme seeks to bring the three single Service recruiting activities together under one future recruiting service with a commercial partner and a single digital platform. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. While the Delivery Confidence remains stable at Amber there is significant risk to this approach to recruitment into the Armed Forces, particularly during the transition phase. | 2018-03-15 | 2024-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-09-30. This is primarily due to the following factors. Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to deliver the armed forces a single recruitment strategy and operating model. | MOD_0119_1920-Q2
Armour MBT 2025 | MOD | Military Capability | The Armour Main Battle Tank Programme will deliver the Challenger 3 capability. Challenger 3 will be Defence's only guaranteed, 24 hr, all weather, mobile anti-tank capability. This programme will modernise and improve the British Army's Main Battle Tanks to the standard needed on today's battlefield. Upgrades include enhanced survivability; greater lethality, improved surveillance and target acquisition as well as removing obsolescence. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Global supply chain risks and key supplier issues that could impact delivery, and resource shortfalls and challenges to recruit the required skill and experience levels. | 2014-12-04 | 2031-05-22 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2026-06-01 to 2031-05-22. This is primarily due to the following factors. The end-date of June 2026 reflected the obsolesce scope of the original Challenger 2 Life Extension Project when it was established in 2015. This should have been adjusted in 2019 when the scope of the programme was increased to deliver a genuine capability uplift to Challenger 2. This effectively reset the Performance, Cost and Time envelope of the programme, and was further refined through the revised assessment phase and Full Business Case submission in November 2020. The end-date of May 2031 reflects Full Operating Capability being delivered by November 2030 at P50 confidence. | 107.86 | 87.87 | -19 | The budget variance exceeds 5%. This is primarily due to the following factors: Delays to Epsom Armour have impacted trials, ammunition integration work and along with supply chain issues, it has been necessary to defer payments until milestones are satisfied now expected in the Financial Year 23/24 | 1435 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1372m. to 1435m. This is primarily due to the following factors. Reprofiling into future years, also the recent initial pre-negotiated Epsom proposal being higher than originallyestimated |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0104_1617-Q1
Armoured Cavalry 2025 | MOD | Military Capability | The Armoured Cavalry programme is central to the Army's Integrated Review and Future Soldier. It will deliver a multi-role Ground Mounted Reconnaissance capability, centred on the Ajax family of vehicles and their training and support systems, into service with the British Army. The six Ajax variants deliver a step change in capabilities compared to current in-service vehicles in the areas of Intelligence, Surveillance, Target Acquisition and Reconnaissance sensors, multi-domain integration, lethality, protection, and mobility. Ajax will equip units in both Armour and Deep Reconnaissance Strike Brigade Combat Teams in 3rd (United Kingdom) Division. 589 vehicles will be delivered through a firm-price contract with General Dynamics Land Systems (United Kingdom). | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Red to Amber. This is primarily due to the following factors. The impact of noise and vibration upon the overall programme schedule to Full Operating Capability has been significant. Significant effort has been made between the Army, Defence Equipment and Support and General Dynamics Land Systems UK to produce a jointly agreed, risk adjusted schedule. This is being used to reset programme approvals against increased confidence in deliverability, compliance, and value for money. | 2014-01-22 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2025-04-30 to 2030-03-31. This is primarily due to the following factors. The time required to quantify, understand, and address the issues of Noise and Vibration has had a significant impact upon all areas of the programme, but most particularly upon the already delayed Ajax production schedule. A jointly agreed, risk adjusted reset schedule is in place out to Full Operating Capability. | 458.44 | 325.55 | -29 | The budget variance exceeds 5%. This is primarily due to the following factors: Delays in achieving an agreed Drop 3 Standard and the associated impact upon the vehicle build schedule. Turret Deliveries were also reduced in line with production causing a further underspend. The remaining in-year variance is split across Demonstration Phase Activities due to Noise and Vibration issues as well as Training Systems procurement; removal of Fire Support Overwatch assessment work and In-Service activities. | 6854 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 6854m. This is primarily due to the following factors. Re-profiling from earlier years and inflation, inclusion of contract change proposal assessments, potential requirement changes and an increase in raw materials and consumables. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0091_1415-Q3
Astute Boats 1-7 | MOD | Military Capability | To deliver the seven Boat Astute Class within approved performance, cost and time parameters, while actively contributing to the sustainment of the UK submarine design and manufacturing capability. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The Astute build programme has achieved its major build and commissioning milestones through this financial year, however, the programme still carries significant schedule risk for the remaining boats because of workload demands and the limited number of Suitably Qualified and Experienced Personnel available. | 1997-03-17 | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | 304.89 | 384.48 | 26 | The budget variance exceeds 5%. . This is primarily due to the following factors: Inflationary impact realised from increased supplier pay settlements and rates. The committment to new contracts with the prime supplier, including the contracts to install essential safety and capability change packages to the remaining boats. | 10827 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 10833m. to 10827m. This is primarily due to the following factors. The programme remains on track to complete within budget. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0076_1213-Q1
AURORA | MOD | Military Capability | Project Aurora will deliver the plutonium component manufacturing capability required to support the UKs enduring nuclear warhead programme. It is current in early design. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The complexity and scale of the project and the ongoing challenges with resources. | 2019-01-31 | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | 79.09 | 79.09 | 0 | The budget variance is less than or equal to 5%. | 2355 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 2355m. This is primarily due to the following factors. At this early stage of the project, the initial confidence model output for the total cost of Aurora suggests the costs will be between 2,000m and 2,500m, however this estimate will be refined as the project progresses. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0131_2122-Q1
Brimstone 3 | MOD | Military Capability | Brimstone 3 sustains the precise, low-collateral air-to-surface Brimstone capability on the Typhoon platform, and is planned to be integrated onto the Protector platform. |  | Red | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (IPA rating) to Red (SRO rating). This is primarily due to the following factors. There are challenges with resourcing sufficient suitably qualified and experienced people across the programme and delivery teams, and within industry. A series of deep-dives, along with a monthly Programme Board with the new Senior Responsible Owner have been put in place to address these challenges. Programme Governance and the availability Management Information is also being refreshed alongside a plan to improve Programme performance. Opportunities are being identified to bring schedule back within the approved timeline. The programme is also exploring opportunities to spiral capability developments to ensure capability is delivered at the earliest opportunity. | 2017-07-01 | 2029-04-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2029-04-30. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0141_2122-Q1
CHINOOK CAPABILITY SUSTAINMENT PROGRAMME (CSP) | MOD | Military Capability | Chinook Capability Sustainment Programme Tranche 1 will provide a modern and cost effective transformational change to the UK Special User's vertical heavy lift capability with the procurement of 14 new-build Chinook aircraft. The aircraft will be able to operate and survive in a multitude of environments, conducting high-tempo missions with minimal logistics footprint and high-levels of interoperability with key allies, to beyond 2050. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. Inflationary pressures and supply chain delays will increase affordability risk and programme success relies heavily on the release of capability information from the US to the UK. The Programme is currently working through rescheduling activities with the US Department of Defence which will culminate in a revised schedule and financial profile. The lack of key skills and experience, though mitigated by the arrival of a new Programme Director, Programme Manager and five Programme Control contractors, remains a risk given the high degree of churn. | 2017-03-31 | 2030-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-12-31. This is primarily due to the following factors. NA | 85.35 | 56.51 | -34 | The budget variance exceeds 5%. This is primarily due to the following factors: The Programme has not been able to commit funds at the rate anticipated as a consequence of US Government's delay in placing contracts due to resourcing challenges. | 1602 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1519m. to 1602m. This is primarily due to the following factors. The cost growth due to a net 18 month deferral. The programme will re-baseline when the full implications are confirmed. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0009_2122-Q2
Clyde Infrastructure | MOD | Military Capability | The Clyde Infrastructure Programme has been established to manage the design, delivery and transition into operational use of new build and updated infrastructure facilities at HMNB Clyde in order to enable the continued safe and secure operation of submarines, support the arrival of the next generation 'Successor' Ballistic Missile Submarines, and create a single submarine centre of specialisation. | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | 2015-09-07 | 2032-04-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2032-04-01. This is primarily due to the following factors. NA | 113.48 | 111.2 | -2 | The budget variance is less than or equal to 5% | 1869 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1585m. to 1869m. This is primarily due to the following factors. The Clyde Infrastructure Programme has been subject to Reference Class Forecasting analysis focused on Faslane and Coulport Portfolios and challenges in delivering in a Nuclear and operational environment. The increased Whole Life Cost considers the impacts of operational constraints, resource availability, extraordinary inflation and material availability. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0118_1718-Q3
Collective Training Transformation Programme | MOD | Military Capability | The Collective Training Transformation Programme will deliver the Future Collective Training System to transform collective training for the Army. Through a long-term, collaborative relationship with industry the Future Collective Training System will deliver increased training system flexibility to allow the Army to train when, where and how it needs in order to meet Defence outputs. Through improved access to data analytics and a more flexible blend of live, virtual, and constructive training, the Future Collective Training System will improve the training enterprise and experience for soldiers and commanders at all levels. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Good progress has been made during the past 12 months including securing Outline Business Case approval.There are however still many uncertainties and risks between now and Full Business Case. Furthermore, approvals are only given at 50% confidence and so prudence in overall Delivery Confidence Assessment is appropriate. | 2018-10-12 | 2040-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2032-01-01 to 2040-03-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 01/01/2032 to 31/03/2040. This is primarily due to the following factor: The project end date has been taken to the end of the 15 year contract award period and not the 10 year planning cycle. | 8.95 | 5.44 | -39 | The budget variance exceeds 5%. This is primarily due to the following factors: Delays in letting support contracts and a delayed internal transfer of funding for staff. | 974 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 655m. to 974m. This is primarily due to the following factors. The Whole Life Cost has increased as the Project End date is now taken to the end of the 15 year contract award period and not the 10 year planning cycle. The underlying costs have remained stable. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0121_2021-Q4
Core Production Capability | MOD | Military Capability | The Core Production Capability (CPC) delivers safe nuclear reactor cores to meet the Royal Navy's submarine programme; now and for the long term. At programme closure; CPC will have provided the Royal Navy with the means to propel a renewed Deterrent submarine fleet; and will have provided the UK with a modern; safe; and Sovereign capability to manufacture further cores for a fleet of flexible and adaptable attack submarines. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. Significant and ongoing challenges associated with achieving the required core delivery date for Dreadnought and the importance of that milestone to sustaining the Continuous at Sea Deterrent. | 2012-04-23 | 2028-04-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-04-30. This is primarily due to the following factors. Whilst the programme schedule has been maintained compared to 12 months ago, in future this schedule will be revised to incorporate the completion of the infrastructure design phase. | 171.38 | 178.46 | 4 | The budget variance is less than or equal to 5%. | 3772 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 3772m. This is primarily due to the following factors. This represents the full costs including budget estimates for scope that has not yet been approved. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0078_1213-Q1
Crowsnest Programme | MOD | Military Capability |  |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. The programme has maintained it's schedule over the last 12 months with increased confidence in deliverability. Technical challenges have been overcome with two software capability upgrades being successfully deployed. | 2013-03-31 | 2023-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-06-30. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 30/06/2023. This is primarily due to the following factor: Revised approval is being sought which will extend programme closure to reflect the current rate of Merlin Mark 2 platform modification across the fleet to enable Crowsnest to be fitted. | 29.78 | 23.94 | -20 | The budget variance exceeds 5%. This is primarily due to the following factors: Delayed activity due to contractor performance and the knock-on delays to the initial provisioning of spares. | 503 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 505m. to 503m. This is primarily due to the following factors. A small net movement reflecting improved contractor performance offset by reprofiling spares purchases. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0017_1112-Q1
Defence Estate Optimisation | MOD | Military Capability | Defence Estate Optimisation Portfolio is a long-term investment of 5.1Bn to modernise the defence estate. It is an ambitious portfolio of construction activity; unit and personnel moves; and site disposals that will deliver a better structured; modern; and more sustainable estate to support military capability. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Recognition of the long complex timeline of the Portfolio, which is now maturing swiftly into the delivery phase. The impact of cost growth driven by emerging net zero sustainability requirements in addition to the construction industry inflation are currently being assessed. | 2016-09-30 | 2041-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2041-03-31. This is primarily due to the following factors. NA | 97.47 | 51.3 | -47 | The budget variance exceeds 5%. This is primarily due to the following factors: 1. A change in the commercial approach regarding Service Family Accommodation purchases, has resulted in a reduction of an in-year spend opportunity. 2. The adoption of the new Delivery Commercial Procurement Strategy throughout the programme has resulted in in-year funding being allocated into future years; in line with the new approach to design and build. While funding has been reprofiled in line with new build stages; in service dates remain extant. | 5438 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 5394m. to 5438m. This is primarily due to the following factors. Following the Integrated Review and the Future Soldier Programme, the Programme has been rebaselined and endorsed by the Portfolio Board and programme schedules updated. Following the schedule amendments, budgets have been realigned. This has resulted in a reduction in resource costs including removal of the need for Private Finance, offset by an increase in construction costs driven by the increase in the indices rates used to apply inflation. | 5466 | The project's departmental-agree monetised benefits at 22/23-Q4 is 5466m. Disposal receipts received for vacated sites, reduced infrastructure running costs at vacated sites and avoidance of lifecycle replacement costs at vacated sites. | MOD_0114_1718-Q1
DREADNOUGHT | MOD | Military Capability | The Dreadnought Programme will maintain the UK's sovereign ability to deliver a deterrent effect by means of a submarine-launched; inter-continental ballistic missile nuclear weapon capability. The programme will achieve this by replacing in-service the current Vanguard Class SSBNs with four Dreadnought Class SSBNs. The programme requirement was detailed in the Government White Paper 2006: The Future of the UK's Nuclear Deterrent; and subsequently endorsed in both the 2015 Strategic Defence and Security Review and the 2021 Integrated Review of Security; Defence; Development and Foreign Policy. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Dreadnought submarine programme remains on track for the First of Class HMS Dreadnought to enter service in the early 2030s. Staged investments have delivered good progress on the whole boat design, production and supporting infrastructure development. However it should be recognised for a programme of this compexity, scale and duration, there is real risk, not least from interfacing programmes of work, and it is therefore prudent to assess as Amber in Delivery Confidence. | 2011-04-14 | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | 2488.82 | 2535.5 | 2 | The budget variance is less than or equal to 5%. | 33989 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 33989m. This is primarily due to the following factors. The Dreadnought programme remains on track to deliver to schedule and within the original 31 billion plus 10 billion contingency budget made in the Strategic Defence and Security Review 2015. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0080_1213-Q1
E7 Wedgetail | MOD | Military Capability | The E-7 Wedgetail programme will provide a 5th generation Airborne Early Warning and Control capability, with a Multi-role Electronically Scanned Array radar that is interoperable and interchangeable with key allies to an anticipated Out-of-Service date of at least 2042. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. The Wedgetail Programme is in the manufacture phase with all three aircraft in modification at STS Aviation (Birmingham). The first aircraft was fitted with its distinctive Multi-role Electronically Scanned Array sensor in September 2022. However, continued challenges within the global supply chain are preventing progress towards a Green rating. | 2018-05-08 | 2027-06-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-06-01. This is primarily due to the following factors. The Wedgetail Programme is expected to reach Full Operating Capability in 2026, with the milestone date to be approved in the Full Business Case. As a result, the Programme end-date will be amended as refined by the Integrated Master Schedule. | 198.53 | 205.1 | 3 | The budget variance is less than or equal to 5%. | 1877 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1895m. to 1877m. This is primarily due to the following factors. The final Programme estimate of Whole-Life Cost will be presented in the Full Business Case. The current Whole Life Cost has reduced due to the transfer of domestic infrastructure funding requirement to Air Infrastructure and the Lossiemouth Development Programme. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0120_2021-Q2
European Common Radar System Mk 2 | MOD | Military Capability | The Phase 4 Enhancement (P4E) to the Typhoon aircraft includes upgrades to mission management systems, GPS resilience and navigational precision. It also provides the vehicle for the integration of the European Common Radar System Mk2 onto the aircraft. The radar is being developed to enable the aircraft to simultaneously detect, identify and track various targets on land and in the air and is vital to maintain Typhoon's control of the air. It also provides a new Electronic Warfare capability and sustains Typhoon capability to operate in contested and congested Electromagnetic environments. The programme is being delivered via multiple interdependent contracts. Radar development is being led nationally by the UK; whereas the wider P4E changes to the aircraft systems are being developed with the other Typhoon Partner Nations as part of the international Eurofighter Programme. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Following successful completion on schedule of the acceptance test procedure, the European Common Radar System Mk2 prototype and supporting documentation was dispatched for the next stage of development. Delayed completion of the Antenna Power Supply and Controller Critical Design Review has impacted the date for the full Radar System Critical Design Review. However, the delay does not impact critical path development activities towards the Initial Operating Capability which are centred around antenna development and are progressing in parallel. | 2023-02-20 | 2023-01-20 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2040-01-01 to 2023-01-20. This is primarily due to the following factors. NA | 153.01 | 173.32 | 13 | The budget variance exceeds 5%. This is primarily due to the following factors: A pull forward of funding from later years to reflect work already completed by Industry at risk. As a result the funding profile for future years has been adjusted accordingly. | 2740 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 565m. to 2740m. This is primarily due to the following factors. The P4E/ECRS Mk2 Programme Full Business Case was approved in March 2022, securing an Approved Budgetary Level funding envelope from its design and manufacture through to the equipment's Full Operating Capability. There has been no change to the programmes requirements and the funding levels remain extant. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0137_2122-Q1
Fleet Solid Support | MOD | Military Capability | Auxiliary Shipping to provide stores, ammunition and food sustainment to Naval Forces at Sea. | Green |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. The Programme has concluded the manufacture contract competition, submitted and gained approval of the Full Business Case and subsequently awarded the prime contract. | 2016-03-14 | 2033-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2030-04-30 to 2033-03-31. This is primarily due to the following factors. The approval of the Full Business Case has enabled the schedule to be re-baselined and the Programme end date to align to the end of final budgetary approved year. | 71.05 | 69.57 | -2 | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0116_1718-Q2
Future Combat Air System | MOD | Military Capability | The Future Combat Air System Acquisition Programme will identify the combat air system to replace Typhoon. The Future Combat Air System will be primarily responsible for delivering Control of the Air, and contribute to Attack and Information, Surveillance and Reconnaissance. It will be able to operate inside a multi-domain information environment or in isolation. The system will exploit open mission architectures to allow freedom of modification and rapid technology insertion. It will be enabled through a combination of crewed and uncrewed platforms and complex weapons with the optimal force mix to be determined during the Concept and Assessment Phase. An international programme by design, the UK is working with several international partners to define the longer-term partnership construct for the Enterprise | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. On-going dependencies impacting the programme from other MOD areas and a shortage of resources impacting skills and capabilities. Other programme areas have remained Amber since Q4 2021 with on-going mitigation in progress. Remedial action for a route to Amber is being implemented but it is expected to take several years to achieve due to the size and complexity of the programme. | 2019-04-26 | 2070-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2070-12-31. This is primarily due to the following factors. NA | 256.94 | 247.77 | -4 | The budget variance is less than or equal to 5%. | 12556 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 10687m. to 12556m. This is primarily due to the following factors. The inclusion of a budget for FY32/33. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0122_2021-Q4
Future Cruise Anti Ship Weapon (FCASW) | MOD | Military Capability | The Future Cruise Anti Ship Weapon programme aims to deliver a next generation complex weapon to meet the UK's Selective Precision Effect At Range Capability 5 (SPEAR 5) and Future Offensive Surface Warfare (FOSuW) requirements. In doing so it is the cornerstone of UK/Fr bilateral cooperation as part of the 'Lancaster House Treaty' and supports UK Freedom of Action, prosperity and critical UK industrial capability. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. The Programme is half-way through a 3-year Assessment Phase; the Assessment Phase remains on track with a range of concepts and options being matured to support choice and inform future decisions. The programme is assessed as Amber whilst the long-term deliverability of these choices is fully explored. | 2017-07-01 | 2070-03-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2070-03-01. This is primarily due to the following factors. This is an indicative date, and a final programme end-date will be provided at Full Business Case. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0139_2122-Q1
Future Defence Infrastucture Services (FDIS) | MOD | Infrastructure and Construction | The Future Defence Infrastructure Services Programme aims to deliver arrangements for the future delivery of Facilities Management services across the UK Defence estate. The first tranche of the programme will replace the existing suite of predominantly Hard Facilities Management Next Generation Estates Contracts. The second tranche of the programme will replace the existing Soft Facilities Management 'HESTIA' Contracts. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. The challenging nature of the schedule and associated dependencies of the Defence Soft FM Programme. A pause to the schedule to address affordability issues has put the programme's current schedule at risk. | 2016-06-07 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 388.83 | 380.51 | -2 | The budget variance is less than or equal to 5%. | 5767 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 5767m. This is primarily due to the following factors. Tranche 1 whole life costs have been established through the tender and approvals process and remain affordable. Tranche 2 whole life costs have increased. This comes as a result of macro-economic factors including inflationary pressures and factors related to the labour market. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces across the UK defence estate with the necessary infrastructure services. | MOD_0129_2122-Q1
Ground Based Air Defence (GBAD) | MOD | Military Capability | The Land Ground Based Air Defence programme will modernise the Army's air defence capabilities in the face of rapidly developing threats and is a very high priority for the Army. This includes the development of an integrated layered air defence system comprising Small Air Targets and Short and Medium Range Air Defence, and technology that allows engagement of targets at optimum range and early air raid warning. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Resourcing issues which put the schedule at risk have improved, and the production of a revised programme roadmap has led to milestone adjustments. An incremental approach to capability delivery should present opportunities to realise some early benefits. | 2018-07-02 | 2033-12-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2033-12-30. This is primarily due to the following factors. NA | 9.37 | 8.07 | -14 | The budget variance exceeds 5%. This is primarily due to the following factor: Work relating to Land Ceptor is behind schedule and did not commence as planned in FY22/23 | 2303 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1787m. to 2303m. This is primarily due to the following factors. The programme is still in its Concept Phase and ahead of Outline Business Case and Full Business Case approvals. The scope of the programme, associated costings and budget provision is not yet fully defined and continues to mature. The Whole Life Cost is based at this stage on the budget for the next 10 years only (plus previous year expenditure) and, as such, the reported Whole Life Cost this year includes a budget for FY2032/33. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0144_2122-Q1
Joint Crypt Key Programme | MOD | Military Capability | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. | MOD_0111_1718-Q1
Land Environment Tactical Communication and Information Systems | MOD | Military Capability | The Land Environment Tactical Communication and Information Systems programme is a capability and business change programme that will deliver the Land Domain's deployed digital backbone through the sustainment, evolution or replacement of Communication and Information Systems and associated applications to underpin the transition to a Single Information Environment. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. The programme remains on track, with significant gains being made in the Dismounted Situational Awareness, Multi-Mode Radio and Trinity projects. Discussions with General Dynamics Mission Systems (UK) on how best to deliver the totality of Morpheus are continuing. | 2013-05-01 | 2035-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2035-12-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 13523 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 13140m. to 13523m. This is primarily due to the following factors. The impact of inflation, alignment of Morpheus, implementation of the Bowman Combat Infrastructure and Platform Sustainment Future Change Request and Trinity contract negotiations. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0105_1617-Q1
Land Intelligence, Surveillance, Target Acquisition and Reconnaissance (ISTAR) | MOD | Military Capability | The Land Intelligence, Surveillance, Target Acquisition and Reconnaissance Programme will deliver an adaptable, robust and agile system that will enable the Army to find the enemy at range in all operational environments. The bedrock of the system will be an open system architecture, designed to be fully integrated with current and future communications and information systems to enable digital integration across the Army, wider Defence, and our primary allies. This will enable a fully networked Intelligence, Surveillance, Target Acquisition and Reconnaissance system consisting of multiple sensors, that can be centrally commanded and coordinated. Automation will be used to speed up decision-making and reduce electronic emissions between component parts. The architecture, platforms and sensors required for the system will be developed and acquired separately, with a series of common standards ensuring that they remain compatible with the network. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Delays across the sub-programmes have added time and cost, the delays have also affected the ability to synchronise outcomes across the programme. In the short-term, workforce churn and relative inexperience of new team members is likely to increase risk. Uncertainty over the timing and content of workstrands on which the programme is dependant is another significant driver of delivery confidence. | 2019-01-25 | 2027-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2027-12-31. This is primarily due to the following factors. NA | 30.57 | 24.51 | -20 | The budget variance exceeds 5%. This is primarily due to the following factors: The delay to the Watchkeeper Mid Life Extension Strategic Outline Business Case | 1598 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1521m. to 1598m. This is primarily due to the following factors. Delays and increased inflation and Foreign Exchange. The normal Formal Change Request process has turned planning assumptions into more assured data which have refined costs and time in several sub-programmes. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0056_2122-Q3
Lightning Programme | MOD | Military Capability | F-35B Lightning is a key element of Combat Air - a 5th Generation combat air vehicle with advanced sensors, mission systems and low observable technology. The F-35B provides real strategic opportunity, and its impressive capability has already been demonstrated and is recognised. It is jointly operated by the RAF and Royal Navy from both land and sea, with a main operating base at RAF Marham which currently houses 617 Squadron and 207 Squadron, the Operational Conversion Unit. The Lightning Force growth through delivering the second squadron, 809 NAS, at RAF Marham is a key dependency for the successful delivery of a critical Defence milestone of Carrier Strike capability. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. Approval of an Outline Business Case has enabled ANVIL Phase 2 (the infrastructure for the 2nd Squadron at RAF Marham) to begin. This is a key enabling Project within the Programme. However Slow Force growth is preventing the Lightning Programme from delivering a 2nd Front-Line Squadron, now planned for 1 December 2023. | 2001-10-01 | 2069-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2048-03-30 to 2069-03-31. This is primarily due to the following factors. Future procurement of an additional 26 aircraft delivering a fleet of 74 which would allow the Out of Service Date of the aircraft to be extended to 2069 andalign with the QUEEN ELIZABETH class aircraft carrier Out of Service Date. Tranche 1, the initial phase of the Lightning Programme, is expected to achieve Full Operating Capability in late 2025, at which point the Lightning programme graduates to become Business as Usual. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0079_1213-Q1
Maritime Electronic Warfare Programme | MOD | Military Capability | The Maritime Electronic Warfare Programme consists of two main projects: Maritime Electronic Warfare System Integrated Capability and Electronic Warfare Countermeasures. The Maritime Electronic Warfare Programme will provide a Maritime Electronic Warfare capability enabled by openness, with the potential to keep pace with developments in anti-ship missile technology, contribute to the development of shared situational awareness and provide Force Protection through automated coordination of response to missile attack. Force Protection/Self Defence will be provided at an individual unit level or as part of a wider Task Group of ships. The programme will deliver improved operational effectiveness and reduced through life cost of surface ship Electronic Warfare capabilities. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Delivery confidence for Maritime Electronic Warfare System Integrated Capability Increment 1 continues to improve with Preliminary Design Review achieved in September 2022. This has provided some stability and flexibility to the management of resource across both Projects. Electronic Warfare Countermeasures is at an earlier stage of maturity, however the Assessment Phase activity is progressing well with Increment 1a Invitation to Negotiate Tender Assessment commencing in October 2022 and contract award expected by the end of 2023. Electronic Warfare Countermeasures Increment 1b has commenced a feasibility study to further clarify the technical readiness level in the market and quantify the degree of technical risk in delivering to meet the Key User Requirements. | 2016-09-30 | 2035-10-29 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2034-06-30 to 2035-10-29. This is primarily due to the following factors. The prioritisation of Maritime Electronic Warfare System Integrated Capability Inc 1 and Electronic Warfare Countermeasures Increment 1a and tolerating the impact to Maritime Electronic Warfare System Integrated Capability Increment 2. Higher than expected complexity of the two prioritised increments. | 27.75 | 27.43 | -1 | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0123_2021-Q4
Maritime Patrol Aircraft | MOD | Military Capability | To deliver a Maritime Patrol Aircraft to provide persistent, responsive, effective and adaptive military capabilities in the Under Water, Above Water, Littoral and Land environments. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Pressure remains on achieving Full Operating Capability (now October 2024) due to budgetary challenges, work force growth issues driven by synthetic training device delays, and reliance on some broader dependencies. Notwithstanding these challenges, Full Operating Capability is still expected within Main Gate Business Case (now known as Full Business Case) delivery approvals. The Training and Aircraft Support Provider contract is delivering well and, although challenges remain, is enabling fleet sustainment and growth. There have been many successes in terms of equipment delivery, infrastructure, work force uplifts, air-to-ground communications and Main Operating Base provision, all of which mean Poseidon is increasingly contributing to the nation's priorities and defence. | 2014-07-08 | 2023-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2024-04-01 to 2023-06-30. This is primarily due to the following factors. The Interim Capability Milestone was declared on 30 June 2022 (originally September 2021) based on delays to the training service provider contract and delivery of synthetic training devices. The Full Operating Capability milestone has been formally delayed to October 2024. All timelines remain within the Main Gate Business Case delivery approvals. The Programme seeks to graduate to a Force Headquarters-led capability on 1 April 2023, and the Programme Closure Date of 30 June 2023 refers to the removal of Poseidon Maritime Patrol Aircraft from the GMPP. | 124.98 | 119.27 | -5 | The budget variance is less than or equal to 5%. | 1981 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1933m. to 1981m. This is primarily due to the following factors. A slippage in the Full Operating Capability which has brought more of the Support Costs within the sphere of the Programme. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0106_1617-Q1
MARSHALL | MOD | Military Capability | Marshall enables military terminal air traffic management services in the UK and abroad. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Hub and Satellite operations commenced at the Lincolnshire Terminal Air Traffic Control Centre in April 2022, which enabled Waddington radar services to be delivered from Coningsby. Hub and Satellite operations from Terminal Air Traffic Control Centre (East) at Marham will start in April 2023 with the relocation of Wittering radar services, and the first Hub and Satellite operations from Terminal Air Traffic Control Centre (South) at Brize Norton are due to start in June 2023 with the transfer of Benson radar services. Work continues to address the known risks and issues with the Programme, including identifying mitigations to a potential delay to achieving the Full Operating Capability milestone. | 2006-04-03 | 2024-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-31. This is primarily due to the following factors. NA | 116.49 | 84.75 | -27 | The budget variance exceeds 5% This is primarily due to the following factors: Delays in new equipment roll-out against the schedule and re-alignment by Defence Equipment and Support of previously mis-aligned accruals. The In-Year Marshall underspend has been absorbed by Programme of Work bring-forward spend elsewhere across the wider Air Capability portfolio, with the commensurate Marshall costs re-profiled into Years 1 and 2. | 1573 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1564m. to 1573m. This is primarily due to the following factors. Reflects the inclusion of Private Sector Support costs over the Annual Budget Cycle period. The programme remains affordable, with cost increase contained within the Approved Budgetary Limit. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0033_1112-Q1
Martlet | MOD | Military Capability | Future Anti-Surface Guided Weapons is required to enable Wildcat helicopter to deliver kinetic effect against and defeat difficult targets in the complex littoral and maritime environments; that lie outside the capabilities of other anti-ship weapon systems. |  | Green | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber (IPA rating) to Green (SRO rating). This is primarily due to the following factors. The Future Anti-Surface Guided Weapon Light (Martlet) has achieved Initial Operating Capability with the next capability uplift on track for October 2023. The Full Operating Capabilty for Martlet is expected to deliver in 2025. Role Equipment delivery is continuing to improve and sustainability challenges are being addressed. | 2011-04-30 | 2045-03-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2045-03-01 to 2045-03-30. This is primarily due to the following factors. Minor date amendment. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0142_2122-Q1
Mechanised Infantry Programme | MOD | Military Capability | The Mechanised Infantry Programme will deliver modern wheeled Armoured Personnel Carriers that can perform a range of roles to support the Infantry, Combat Support, and Combat Service Support elements across new Brigade Combat Teams - a new concept emerging from the Integrated Review. The vehicles will be a significant contribution to enabling a highly deployable, networked force to operate differently from conventional industrial age combat forces, offering unique competitive advantage whether fighting, peacekeeping or delivering humanitarian aid. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. Global supply chain issues following Covid and the current war in Ukraine impacting at a key point of vehicle manufacture. The programme still forecasts to meet its approved Initial Operating Capability in October 2025 but increased risks require strong management action. The lead contractors have not yet stabilised or fully resolved their ongoing supply chain delays to vehicle production, which is also impacting other areas including training. Further remedial work is also required on Technical Documentation currently being drafted to enable acceptance and safety case work. Similar supply chain issues are also impacting the supply of communications equipment for Boxer also compounded by obsolescence and global supply chain impacts. | 2017-10-27 | 2033-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2033-03-31. This is primarily due to the following factors. NA | 281.43 | 86.37 | -69 | The budget variance exceeds 5%. This is primarily due to the following factors: Delays to equipment delivery and Bowman Government Furnished Equipment with the remainder a combination of reprofiling for risk, training aids, special tools and test equipment, and technical publications. | 6741 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 6575m. to 6741m. This is primarily due to the following factors. Re-profiling from in-year into future years. This was a direct consequence of equipment and Bowman delays and prudent risk-adjustment. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0115_1718-Q2
MENSA | MOD | Military Capability | Mensa is the replacement capability for assembly and disassembly of current and future nuclear warheads in support of HMG's strategic deterret. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The project has been challenged to maintain pace whilst managing a complex schedule and a testing supply chain environment. The project continues to make progress and is nearing finishing construction. | 2011-08-31 | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | The schedule narrative was exempt from publication in financial year 21/22-Q4. The project has been challenged to maintain pace whilst managing a complex schedule and a testing supply chain environment. The project continues to make progress and is nearing finishing construction. | 255.66 | 255.66 | 0 | The budget variance is less than or equal to 5%. | 2161 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 2161m. This is primarily due to the following factors. The programme remains affordable and is within its Approved Budgetary Limit of 2,544m. The programme continues delivering at pace, following work to ensure compliance with regulatory safety standards, and the impacts of COVID and other macro-economic pressures on the project's supply chain. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0132_2122-Q1
Meteor | MOD | Military Capability | To sustain a world beating Beyond Visual Range Air to Air Missile capability with our Meteor Partners (France; Germany; Spain; Italy and Sweden) to share cost and reap the benfits from competeing in the global Beyond Visual Range Air to Air Missile export market. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Successful acceptance and test of the first Meteor Spiral development SP1.1 has delivered significant increases in operational capability, and Spiral 2 is progressing well and is anticipated to deliver in late 2023. In the wake of the renewed Meteor In-Service Support contract, additional work has been completed to support front line delivery and develop a triage system regarding missile serviceability. | 2002-07-15 | 2048-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2048-12-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0143_2122-Q1
Mine Hunting Capability | MOD | Military Capability |  | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Resourcing challenges, predominantly with the infrastructure and logistics lines of development, and the impact of poor supplier performance on Block 1 in delivering Mission Systems for Operational Evaluation. | 2014-10-01 | 2034-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2034-03-31. This is primarily due to the following factors. NA | 102.45 | 102.44 | 0 | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0124_2021-Q4
MODnet Evolve | MOD | ICT | MODNet Evolve will sustain the essential base Information and Communications Technology infrastructure needed by the Ministry of Defence on exit from the current contracted service. | Red |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Red. This is primarily due to the following factors. The assessment of the deliverability of the MOD Official, End User Services and Future Secret Projects. However the recovery plan is in place and the programme is making positive progress and the Future Secret project is now being reset. Also linkages are being strengthened between the current MODnet Official network and its replacement End User Services project. | 2016-02-29 | Exempt under Section 26 of Freedom of Information Act 2000 (Defence). | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0110_1718-Q1
Naval Support Integrated Global Network (NSIGN) | MOD | Military Capability | The Naval Support Integrated Global Network is the re-provision of the services contracted through Future Maritime Support Programme. Whilst Naval Support Integrated Global Network will continue to develop the market facing transformation (a combination of single source and competition) it will also utilise Defence frameworks wherever possible, expand the scope for Ships to align the complex and non-complex, provide choice for how the Royal Navy will operate in the future, and look at scope boundaries/opportunities where Naval Support Integrated Global Network could deliver more effectively. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Early challenges with Programme initiation, resourcing and mobilisation. An Action Plan is in place which will ensure alignment of key stakeholders to the strategic narrative and industrial strategy. | 2021-12-01 | 2029-05-22 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2026-10-01 to 2029-05-22. This is primarily due to the following factors. The programme is in the pre-concept phase. Key Procurement and Commercial Strategy milestones and the Naval Support Integrated Global Network mobilisation plans will continue to mature as the Programme progresses through Strategic Outline Case, Outline Business Case before being aligned with Full Operating Capability within the Full Business Case. | [5 empty] | NA The Programme is yet to reach Outline Business Case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0136_2122-Q1
New Medium Helicopter | MOD | Military Capability | The New Medium Helicopter programme intends to rationalise five rotary wing requirements through the procurement of one new medium lift helicopter-type. This approach will maximise commonality allowing improvements in efficiency and operational flexibility. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The delay in securing the Outline Business Case approval. Significant work is ongoing to secure approval which will enable the main part of the New Medium Helicopter competition to proceed through the release of an Invitation-to-Negotiate which is expected later this year. | 2021-04-30 | 2031-09-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2028-07-07 to 2031-09-30. This is primarily due to the following factors. Since the initial report, further analysis on the programme schedule has been conducted and the financial profile was amended as part of the Ministry of Defence's Annual Budget Cycle 2022. This has led to a revision in the programme's projected end-date. | 3.9 | 3.29 | -16 | The budget variance exceeds 5%. This is primarily due to the following factors: The minor underspend results from activities moving into FY23/24 as a result of the programme not achieving the stretch target of Outline Business Case approval during FY22/23. | 1329 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1172m. to 1329m. This is primarily due to the following factors. The programme received an uplift to safeguard the capabilities that the New Medium Helicopter programme plans to deliver. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0125_2021-Q4
New Style of Information Technology (Base) | MOD | ICT | The New Style of IT Base programme was established to renegotiate the continuation of Defence IT systems. The intent is to transform the delivery of information and communication technology across the majority of Defence users in offices, headquarters and bases, providing a new IT system that exploits the power of cloud computing, along with Microsoft Office 365 software, new modern Win10 laptops, that securely deliver greater agility and mobility to service personnel wherever they may be. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. New Style of Information Technology (Base) has successfully delivered significant elements of its original scope; with MODNET (Official) and MODNET (Secret) now operational. The process to bring the programme to an orderly closure has begun with a formal closure report to be submitted in FY 23/24. Once approved; the outstanding scope and funding will be transferred to the MODNET Evolve programme for delivery. | 2015-04-01 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 282 | The project's departmental-agree monetised benefits at 22/23-Q4 is 282m. The projects departmental-agree Benefits at 22/23-Q4 is 281.550M. This is primarily due to the variable and fixed cost difference between the legacy DII service and the current MoDNET service. | MOD_0101_1516-Q1
New Style of Information Technology Deployed | MOD | Military Capability | The Programme aims to deliver an MOD-owned; highly secure; technologically advanced and evolutionary communications and information service that connects war-fighters and enables information advantage across the operational landscape. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Since the 2022 Q4 report the Programme has faced challenges with delivery in both the Land and Maritime environments, due to multiple factors and revised planning is in place and approval is being sought. | 2015-04-01 | 2028-03-31 | The project's end-date at 22/23-Q4 is 2028-03-31. This is primarily due to the following factors. NA | 117.25 | 105.79 | -10 | The budget variance exceeds 5%. This is primarily due to the following factors: Unspent risk inside costing, deferral's primarily due to supply chain issues, efficiencies mainly against material purchases. These reductions have been offset in part by the inclusion of an in year Capital Defence Expenditure Limit charge; net in year increase relates to an International Financial Reporting Standard 16 accounting payment that has been paid in year. | 835 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 835m. This is primarily due to the following factors. Whole Life Costs have reduced by 4.3M. The key factors are in year unspent risk inside costing, efficiencies mainly against material purchases, changed costing and further deferred costings. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0109_1617-Q2
Next Generation (fixed) Communication Network | MOD | ICT | The intent of the Next Generation (fixed) Communications Network Programme is to develop a secure; singular; modern enterprise network which connects sensors; effectors; and deciders across military and business domains. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Whilst the programme Delivery Confidence Assessment is the same as it was 12 months ago, the programme has been maturing the Outline Business Case, which is now in place, addressing the cost and schedule challenges. A key focus for the programme now is active risk management of programme resourcing in highly skilled areas that are in sector wide shortages. | 2021-04-28 | 2030-12-11 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2031-03-31 to 2030-12-11. This is primarily due to the following factors. The Programme schedule has recently been baselined following submission of the Outline Business Case. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0126_2021-Q4
PEGASUS | MOD | Military Capability | Pegasus is the replacement capability for uranium storage and component manufacture to support current and future nuclear warheads in support of HMG's strategic deterrent. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. a key focus for the programme now is active risk management of programme resourcing in a highly skilled area that has sector wide shortages. The programme also has continued challenges with supply chain and regulatory bodies. | 2003-07-01 | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | 71.83 | 71.83 | 0 | The budget variance exceeds 5%. This is primarily due to the following factors: A pull forward of funding from later years to reflect work already completed by Industry at risk. As a result the funding profile for future years has been adjusted accordingly. | 1753 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 1753m. This is primarily due to the following factors. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0133_2122-Q1
Project Bramley | MOD | ICT | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) | Exempt under Section 24 of the Freedom of Information Act 2000 (National security) |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4. | MOD_0128_2021-Q4
PROTECTOR | MOD | Military Capability | Protector will provide a certified remotely piloted air system with enhanced capabilities (to 2038) over those currently provided by the in-service Reaper air system. Protector will provide an armed, long range, persistent wide area surveillance with various sensors and be based at RAF Waddington in Lincolnshire. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Despite significant challenges, particularly relating to Equipment, Infrastructure and Information Defence Lines of Development, the Programme continues to manage risks and work through mitigations to progress towards the key milestones. However there are considerable increased costs for the planned Programme technical infrastructure at RAF Waddington. A contingency plan to deliver Initial Operating Capability utilising existing Infrastructure is underway and pending approval. Compounded with delays to critical software development, this has led to a delay in the Programme. In response, it is planned to re-baseline the Programme milestones and seek an increase to the Approved Budgetary Limit. | 2009-04-30 | 2038-03-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2038-03-30. This is primarily due to the following factors. NA | 235.34 | 241.84 | 3 | The budget variance is less than or equal to 5%. | 1345 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 1517m. to 1345m. This is primarily due to the following factors. Removal of the costs for the Enhance Maritime element which is now accounted for separately.The Review Note for Protector that will re-baseline the Programme will capture, and fairly attribute cost growth as appropriate, to programmatic and macro-economic factors that have affected the delivery and affordability of the programme. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0107_1617-Q1
Sea Venom | MOD | Military Capability | Future Anti-Surface Guided Weapon (FASGW) is required to enable Wildcat Helicopter to deliver kinetic effect against; and defeat difficult targets in the complex littoral and maritime environments; that lie outside the capabilities of other anti-ship weapon systems. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (IPA rating) to Amber (SRO rating). This is primarily due to the following factors. A Defence Science Expert Committee review resulted in an action plan which included integration and assurance activity and appropriate risk mitigations. Further assurance activity is planned to support the continued improvement of the Programme. | 2014-03-03 | 2047-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2047-12-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0138_2122-Q1
Skynet 6 (aka FBLOS) | MOD | ICT | SKYNET 6 programme the MOD will deliver and manage military Core Satellite Communications (SATCOM) services from September 22. This will include a new Service Delivery contract to take on existing core services and procurement of the next generation of space-based SATCOM capability. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The 6A satellite project remains on track to deliver in 2025 with 4-months schedule contingency. There remains, however, significant risk attached to a programme with this level of complexity and challenge. | 2011-01-01 | 2041-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2041-12-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0100_1516-Q1
Spearcap 3 | MOD | Military Capability | Spear Cap 3 will deliver the principal air-to-airground weapon for UK F-35 and is critical to the aircraft's Attack and Control of the Air capabilities in contested environments. |  | Red | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber (IPA rating) to Red (SRO rating). This is primarily due to the following factors. There are challenges with resourcing sufficient suitably qualified and experienced people across the programme and delivery teams, and within industry. A series of deep-dives, along with a monthly Programme Board with the new Senior Responsible Owner have been put in place to address these challenges. Programme Governance and the availability Management Information is also being refreshed alongside a plan to improve Programme performance. Opportunities are being identified to bring schedule back within the approved timeline. The programme is also exploring opportunities to spiral capability developments to ensure capability is delivered at the earliest opportunity. | 2020-09-30 | 2047-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2027-06-30 to 2047-12-31. This is primarily due to the following factors. Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0140_2122-Q1
Spearfish Upgrade Programme | MOD | Military Capability | To deliver in-service an upgraded submarine launched heavy-weight Torpedo that is safe, sustainable and capable of defeating modern Anti-Submarine Warfare and Anti-Surface Warfare threats in order to retain the UK's dominance of the Underwater Battlespace. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The continued challenges to the schedule imposed by both technical complexity and changes to fit opportunities to the submarine platforms. | 2008-04-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-03-31. This is primarily due to the following factors. Despite significant progress, the continued technical, industrial and supply chain challenges faced by the programme still threaten the feasibility of programme schedule. | 31.41 | 30.27 | -4 | The budget variance is less than or equal to 5%. | 405 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 406m. to 405m. This is primarily due to the following factors. A Foreign exchange variance and a double counted accrual which has been removed. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0047_1112-Q1
Submarine Dismantling Project | MOD | Military Capability | The Submarine Dismantling Project mandate covers preparation and execution to safely and securely dismantle the first defueled and decommissioned Royal Navy submarine in Rosyth by 2026. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The project is continuing to progress in line with its maturing schedule, however, this is a ground breaking programme and learning by doing encounters difficulty and challenge that cannot necessarily be planned for. | 2013-03-29 | 2026-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-12-31. This is primarily due to the following factors. Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 31/12/2026.The date is based on a maturing deterministic schedule and its achievability will become clearer over the next 12 months. | 33.39 | 33.18 | -1 | The budget variance is less than or equal to 5%. | 298 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 278m. to 298m. This is primarily due to the following factors. An increase in number of employees required to complete the work and the impact of inflation e.g. the rising cost of materials. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0135_2122-Q1
Submarine Waterfront Infrastructure Future | MOD | Infrastructure and Construction | The Submarine Waterfront Infrastructure Future project is investing in infrastructure at Devonport to support the maintenance of the Royal Navy's Astute Class nuclear-powered submarines. The facilities being provided include a new non-tidal maintenance berth, a refurbished dry dock and supporting buildings and services. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. As the project transitions into full construction, it remains exposed to a number of risks in the delivery environment outside the project's immediate control. | 2016-12-31 | 2027-10-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2028-12-15 to 2027-10-31. This is primarily due to the following factors. The previously reported end-date was for completion of the project assessment phase. The end-date reported now is the construction completion dateapproved at Full Business Case. | 182.95 | 191.7 | 5 | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0011_2122-Q2
Submersible Ship Nuclear AUKUS | MOD | Military Capability | In March 2021 the UK Government committed to funding of this next generation of submarines, with the programme becoming known as Ship Submersible Nuclear (Replacement). The programmes aim is to deliver the next generation of Royal Navy submarines. The intial design work will inform a future decision to define the replacement for the Astute Class submarines - the nuclear-powered fleet of submarines currently in service with the Royal Navy. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Significant challenges at this early stage of the programme, some outside the control of the programme. Progress has been made, but negotiations with the suppliers have been more protracted than anticipated. | 2014-04-01 | Early planning GMPP project (The project has not yet passed SOC, or its programme equivalent) | The project's end-date at 22/23-Q4 is currently undefined. This is primarily due to the programme being in its Programme Definition Phase until 31/03/2023. Therefore, the programme's strategic milestones, detailed programme schedule and end-date are not possible to define. | 188.87 | 179.81 | -5 | The budget variance is less than or equal to 5% | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0007_2122-Q2
TEUTATES | MOD | Military Capability | As part of the 2010 Lancaster House Agreements; a Treaty was established on a joint radiographic/hydrodynamics capability with France known as Teutates. The trials will be in a jointly operated facility but conducted on a national basis and are needed to underwrite the safety and performance of our nuclear weapon stockpile. Teutates covers the joint construction; funding; and operation of a new hydrodynamics facility in France; at Epure; near Dijon; and a technology development centre and interim firing point in the UK at the Atomic Weapons Establishment; at Aldermaston. The Teutates facilities will enable each country to undertake hydrodynamic experiments in a secure environment. The hydrodynamic facilities use radiography to measure the performance of materials at extremes of temperature and pressure. This enables us to model the performance and safety of the nuclear weapons in our current stockpile without undertaking nuclear explosive tests; and will make an important contribution to assuring the performance; safety and reliability of our next generation of nuclear weapons. | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | 2013-04-01 | 2064-03-31 | The project's end-date at 22/23-Q4 is 2064-03-31. This is primarily due to the following factors. Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) | Exempt under Section 27 of the Freedom of Information Act 2000 (International Relations) |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0134_2122-Q1
Type 26 Global Combat Ship Programme | MOD | Military Capability | Type 26 Global Combat Ship Programme will procure 8 x Anti Submarine Warfare ships and associated support. The ships will deliver an interoperable, survivable, available and adaptable capability that is operable globally within the maritime battle space to contribute to sea control for the Joint Force and contribute to maritime force projection and Joint Force command and control with the flexibility to operate across and within the range and scale of Contingent and non-Contingent operations. This 8 ship programme will deliver Anti-Submarine Warfare capability to protect strategic assets, sustain national shipbuilding capability and increase resilience of the Naval Service. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Delay caused by a combination of outstanding engineering design volume, supply chain performance and COVID related slowdown has resulted in a re-baseline to Initial Operating Capability, which was approved earlier in the year. Importantly, quality has not been compromised and T26 Frigates will be world class ships delivered in time to replace their T23 counterparts. | 2008-07-21 | 2035-05-01 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2035-05-01. This is primarily due to the following factors. NA | 816.77 | 814.78 | 0 | The budget variance is less than or equal to 5%. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0055_1112-Q1
Type 31e | MOD | Military Capability | The Type 31 general purpose frigate programme is designed to deliver a general-purpose frigate capability and act as the pathfinder programme for the National Shipbuilding Strategy. From the mid-2020s, Type 31 will be at the heart of the Royal Navy's surface fleet, deterring aggression and maintaining the security of the UK's interests. They will work alongside our Allies to deliver a credible UK warship presence across the globe. Flexible and adaptable by design, Type 31 frigates will undertake missions such as interception and disruption of those using the sea for unlawful purposes, collecting intelligence, conducting defence engagement and assisting those in need. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Successful delivery appears feasible but significant issues already exist requiring sustained management attention and mitigation, which are in place for these issues. Amber is considered appropriate given the COVID-19 pandemic impacts on the programme, supply chain issues as a result of the conflict in Ukraine, and the complex activities associated with delivering the full capability of a `new to service` combat system and its associated systems. In addition to this, inflation uncertainty, supply chain impacts as a result of Global events, and Royal Navy personnel challenges in areas of key engineering skills remain significant risks for the programme. | 2016-04-01 | 2029-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2029-03-31. This is primarily due to the following factors. NA | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This programme does not report cashable benefits. Its aim is to provision the armed forces with the equipment and / or infrastructure required. | MOD_0112_1718-Q1
10k Additional Prison Places - New Build | MOJ | Infrastructure and Construction | The New Build project supports our 20,000 additional prison places commitment; its scope is to build four new prisons. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment rating remained Amber.The Amber assessment is due to planning permission refusals atthree of the new prison sites which are subject to planning appeals.There has been positive progress building the third of our new prisons (Full Sutton).(The main works contract was executed on 21 July 2022 following which construction commenced in August 2022 and delivery is on track). | 2020-03-02 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 230.27 | 221 | -4 | Variance less than 5% so no narrative required | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. This programme's primary benefit relates to increasing capacity due to the projected rise in prison population as opposed to monetised benefits.The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0050_2021-Q1
10K Additional Prison Places Estate Expansion Category D | MOJ | Infrastructure and Construction | The Programme's scope is to deliver 1,320 places across the Category D estate. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is the first time data has been published for this programme, which has been added to GMPP over the last year.This programme was formerly reporting as part of the 10k Additional Prison Places Estates Expansion Programme.The Amber assessment is driven by inflation risks. | 2020-01-24 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 136.68 | 27.76 | -80 | Costs for the two phases have been re-profiled into future financial years, due to rescoping elements of the programme. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0111_2122-Q2
10k additional prison places Estate Expansion Houseblocks and Refurbishments | MOJ | Infrastructure and Construction | This programme will deliver around 1,785 additional prison places in the closed male category B and C estate. This includes modern, purpose-built houseblocks which will provide improved living space for prisoners and a safer working environment for staff. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is thefirst timedata has been published for this project, which has been added to GMPP over the last year.This programme was formerly reporting as part of the 10k Additional Prison Places Estates Expansion Programme.The Amber assessment is driven by inflation risk and recruitment challenges. The programme has successfully delivered one site. | 2019-08-15 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 194.21 | 65.38 | -66 | The underspend is due to the descoping of the Rye Hill project from the programme and delays to elements of the programme that have necessitatedcosts to be re-profiled into future financial years. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0113_2122-Q2
10K additional Prison places Women's Estate Expansions | MOJ | Infrastructure and Construction | The programme will deliver additional capacity to the women's prison estate. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is the first time data has been published for this project, which has been added to GMPP over the last year. This programme was formerly reporting as part of the 10k Additional Prison Places Estates Expansion Programme. The Amber assessment is due to inflation risks. | 2020-05-18 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 10.85 | 7.3 | -33 | The underspend is due to reduced activities in year requiring some costs to be re-profiled into the next financial year | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0112_2122-Q2
Accelerated Houseblocks | MOJ | Infrastructure and Construction | The Accelerated Houseblock Programme aims to deliver around 2,400 places as part of the wider Prison Capacity Portfolio Programme. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment rating remained Amber.The Amber assessment is driven by inflation risks and recruitment challenges. | 2020-09-28 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 357 | 61.5 | -83 | The underspend is due to changes in scope and wider budget reprofiling. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0053_2021-Q4
Approved Premises Expansion | MOJ | Government Transformation and Service Delivery | The Approved Premise Expansion Programme (APEX) has increased capacity within Approved Premises. Approved Premises are residential units in the community which house and monitor offenders following release from prison. They protect the public and rehabilitate offenders. The Programme has delivered 169 additional bed spaces for both men and women across 33 sites. |  | Green | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Green. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained Green. The Programme has successfully delivered 169 bed spaces for both men and women meeting the revised scope of the programme. | 2019-04-01 | 2023-07-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2024-03-31 to 2023-07-30. This is primarily due to the following factors. The project is now moving towards closure having successfully handed over169 bed spaces into operation in March 2023. | 13.73 | 13.77 | 0 | Variance less than 5%, so no narrative required | 80 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 65m. to 80m. This is primarily due to the following factors. The Whole Life Cost has increased from 65.15m to 79.69m. This is due to increased staffing and facilities management costs. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are related to the successful operation of the Approved Premises Service. | MOJ_0052_2021-Q3
Community Accommodation Service Tier 2 | MOJ | Government Transformation and Service Delivery | This is a critical service for HMPPS, providing suitable accommodation and support for low and medium risk offenders, primarily on Bail and Home Detention Curfew who would otherwise be held in custody, and thereby eases pressure on the prison population. The new contract commenced on 1st October 2022. |  | Green | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Green. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained Green.The project has successfully delivered the full scope of Community Accommodation spaces and all operations have been fully transitioned to business as usual. | 2020-07-15 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. The Mobilisation period ended on 31st March 2023 and all closure activity is in progress. | 5.21 | 6.08 | 17 | Increased in-year costs are due toan additional 200 beds being added to the project scope. | 63 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 63m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project currently reports no monetised benefits. The project's benefits are related to the successful operation of the Community Accommodation Service. | MOJ_0059_2122-Q1
Community Accommodation Services -Tier 3 | MOJ | Government Transformation and Service Delivery | Community Accommodation Services Tier 3 provides prison leavers, who would otherwise be homeless, up to 84 nights of transitional accommodation on release from prison, or when moving on from CAS1 (Approved Premises) and CAS2 (Home Detention Curfew or Bail Accommodation) provisions. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is the first time data has been published for this project, which has been added to GMPP over the last year.The Amber assessment is due to risk around the pace of mobilisation in England. Community Accommodation Services Tier 3 has successfully launched in Wales. | 2021-08-01 | 2023-12-19 | The project's end-date at 22/23-Q4 is 2023-12-19. This is primarily due to the following factors. The programme is on track against the current baseline plan. | 41.6 | 25.01 | -40 | The in-year underspend is due to a change in contract signature and mobilisation dates . All contracts have now been signed and mobilised. | 320 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 320m. This is primarily due to the following factors. The Whole Life Costs of the project include costs associated with delivery of new contracts,development of a digital service and ongoing staffing requirements. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project currently reports no monetised benefits. The project has seven defined benefits related to the successful operation of the Community Accommodation Service and will begin reporting on these 23/24. The project currently reports no monetised benefits as more data is required to complete this work | MOJ_0083_2122-Q4
Decommission and Legacy Risk Mitigation (DLRM) | MOJ | ICT | The Decommission and Legacy Risk Mitigation (DLRM) Programme has been established to mitigate the risks presented by HMCTS legacy technology. The DLRM Programme will retire aged and unused applications where possible and for those applications still required it will update the application and migrate it to supported hosting environments. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained Amber.The Amber assessment is due tocomplexity risks in the migration of live data. The programme has exceeded its Year 1 target. | 2021-07-01 | 2028-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2028-03-31. This is primarily due to the following factors. The project remains on track for completion in line with the current baseline schedule. | 51.53 | 27.15 | -47 | Underspend in 22-23 arises from the project not needing to call on contingency and optimism bias and reduction of costs more generally, with a small level of slippage into 2023-24. The programme remains on track and exceeded milestones set. The reduction in cost of the programme does not affect the delivery of the overall programme core milestones, which remain affordable. | 198 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 198m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project benefits focus on reducing the risk of legacy technology through decommission, transition and replacement. | MOJ_0061_2122-Q3
Drug Testing Services | MOJ | Government Transformation and Service Delivery | The project objective is to successfully procure and implement a service for the drug testing of offenders in prisons and under supervision in the community. It aims to procure services that are future-proof and support delivery of the drug testing strategy. Two contracts are to be procured 1) urine and oral fluid based laboratory analysis services, and (2) oral fluid point of care drug testing kits. |  | Amber | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Green to Amber. This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment rating remained Amber.The Amber assessment is due to the inherent risk that the quality of services required may be challenging to procure because of the highly specialised nature of the laboratory toxicology services being bought. | 2021-04-01 | 2024-07-12 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-05-01 to 2024-07-12. This is primarily due to the following factors. The project has been re-baselined following procurement challenges. | 1.1 | 1.1 | 0 | Variance is less than 5%, so no narrative required | 184 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 125m. to 184m. This is primarily due to the following factors. The increased costs reflect the updated Outline Business Case following procurement challenges. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are related to the successful onward operation of the Drug Testing service. | MOJ_0073_2122-Q4
Electronic Monitoring Expansion | MOJ | Government Transformation and Service Delivery | The Electronic Monitoring Expansion Programme seeks to expand the impact, use and efficiency of electronic monitoring as a tool for the management of offenders in the community, helping reduce re-offending and protecting the public. The programme's aims include - effectively retendering the current service, increasing the scope and reach of electronic monitoring, building a more comprehensive evidence base, and more closely embedding the electronic monitoring service within the Probation service | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (IPA rating). This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment rating remained Amber. The Amber assessment is due to timetable risks and recruitment challenges.A number of new initiatives to expand and enhance the current provision have been successfully delivered. | 2021-01-01 | 2024-12-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2024-12-31. This is primarily due to the following factors. The programme is on track against the current baseline plan. | 162.66 | 88.38 | -46 | The underspend is due to delays with operational recruitment andcaseload being below forecast. | 1214 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 1214m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits will be defined monetarily at a later stage and following the completion of the procurement of new service delivery contracts and current pilot projects. | MOJ_0058_2122-Q1
Evolve: End User Computer Service | MOJ | ICT | Ensure the continuation of critical End User Compute Services (EUCS) used by MoJ staff every day, and Implement an EUCS Future State model, which is crucial to achieving the strategic objective of a single technology ecosystem to all 110k MoJ users by 2025. In order to achieve the future state, there are 3 EUCS streams 1) The management of 3 re-procurements of EUCS suitable for the current and future needs of the Authority covering EUCS Platform & Legacy services, Hardware Sourcing and Hardware Support Services, 2) EUCS Insourcing to bring certain capabilities in-house, 3) Converge & Accelerate focuses on the migrating users on the legacy FITS services to the organisations service MoJ Official. |  | Green | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Green. This is primarily due to the following factors. This is the first time data has been published for this project, which has been added to GMPP over the last year.The project has been assessed as Green and is on track to deliver against baseline schedule and costs. | 2021-09-27 | 2025-04-30 | The project's end-date at 22/23-Q4 is 2025-04-30. This is primarily due to the following factors. The project is on track to deliver against the re-baselined schedule. | 33.33 | 10.46 | -69 | The underspend is due to reduced in-year activity requiring costs to be re-profiled into future years. | 340 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 340m. This is primarily due to the following factors. The Whole Life Costs in the Outline Business Case include projects costs for resources, 3rd party involvement and legal fees, costs to run the service once in place and costs for the purchase of new hardware |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project benefits focus on the continued quality of operation of end user compute services contracts. | MOJ_0062_2122-Q3
Evolve: Voice & Video | MOJ | ICT | Re-procurement of Voice and Video Services suitable for the current and future needs of the Authority, to replace the existing Future IT Services Voice and Video contracts. The project includes requirements gathering, ITT/Procurement preparation, competitive procurement and an increase in internal capability followed by the transition of services and exit of the existing contracts. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating increased from Amber to Green.The Green assessment is due the project being on track against the re-baselined schedule and costs. | 2021-09-27 | 2027-04-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2025-04-30 to 2027-04-30. This is primarily due to the following factors. The project has re-baselined in January 2023 due to changes to procurement timelines. | 5.3 | 7.03 | 33 | The overspend is due to increased resource costs, driven by the rebaselining activity. | 206 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 206m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project benefits focus on the continued quality of operation of voice and video services contracts. | MOJ_0049_2122-Q3
Evolve: WAN/LAN (Networks) | MOJ | ICT | Re-procurement of WAN and LAN Services suitable for the current and future needs of the Authority, to replace the existing Future IT Services WAN/ LAN. The project includes requirements gathering, ITT/Procurement preparation and competitive procurement followed by the transition of services and exit of the existing contracts. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained Amber. The Amber assessment is due to procurement timetable risks. | 2021-09-27 | 2026-08-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2026-08-30. This is primarily due to the following factors. The project rebaselined in the financial year to reflect revised timescales. | 28.2 | 7.6 | -73 | The underspend is driven by commercial activity being rescheduled which has required costs to be re-profiled to future years. | 253 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 253m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project benefits focus on the continued quality of operation of network services contracts. | MOJ_0050_2122-Q3
Glen Parva New Build Prison | MOJ | Infrastructure and Construction | The new prison at Glen Parva, HMP Fosse Way, is a resettlement prison, creating 1,715 Category C resettlement places. It will house prisoners nearing the end of their sentence or on short custodial sentences. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to21/22 Q4, the project's Delivery Confidence Assessment rating remained Amber.The Amber assessment is due to an extended construction phase and reduced transition period. The project is forecast to deliver within budget and lessons learned from the delivery of HMP Five Wells have been actively incorporated. | 2019-01-31 | 2023-11-05 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-11-05. This is primarily due to the following factors. The project is on track to deliver against the baseline schedule. | 92.1 | 88.95 | -3 | Variance less than 5%, so no narrative required | 6753 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 6765m. to 6753m. This is primarily due to the following factors. The Whole Life Cost has decreased due to a reduction in costs for fixtures, furnishings & equipment provided by the operator and construction risks not materialising. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. This project's primary benefit relates to increasing capacity due to the projected rise in prison population as opposed to monetised benefits.The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0043_1920-Q2
HMCTS Reform | MOJ | Government Transformation and Service Delivery | The HMCTS Reform Programme was launched in 2016 to modernise the justice system by reducing complexity and providing new ways for people to engage and access justice. The 1.3bn change programme is centred on the principle that the system should be designed around its users and be cheaper to run. Following the agreement of Ministers and the Senior Judiciary, timelines have been revised to extend the programme by 3 months to 31 March 2024 with an additional year to March 2025 for some elements of the Crime Programme. |  | Amber | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber (SRO rating). This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment rating remained Amber.The programme has recently revised and rebaselined its schedules in order to ensure delivery is completed with minimal impact on operational services. The Amber rating is due to the need to deliver a complex range of projects across a challenging delivery environment, with limited time contingency. This year the programme has delivered: A new digital service for Probate; A single case management system for the Royal Courts of Justice and Upper Tribunals; A new online service in Immigration and Asylum to providing improved customer experience, utilising technology and interactive with other government agencies. The Common Platform is live in 176 (59 Crown Courts and 117 Magistrates' Courts) totalling 78. The programme has opened the fifth Courts and Tribunals Service Centre; and A new tool for scheduling court and tribunal hearings is now live in civil and family courts. The programme has also completed the build of the new Strategic Data Platform. | 2016-12-01 | 2024-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-12-31 to 2024-03-31. This is primarily due to the following factors. Following ministerial agreement the programme timeline has been extended. The revised plan allows for a shift in the approach to implementation, recognising the lessons learnt in implementation to date. Some elements of the programme have been descoped to allow focus on successful delivery of the remaining higher-benefit projects. | 296.53 | 236.64 | -20 | The underspend is due to the programme not utilising the contingency and staff exit/redundancy funding allocated this year. | 2789 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 2789m. This is primarily due to the following factors. The whole life costs remained static, and the budget remains aligned to the current baseline business case. | 2899 | The project's departmental-agree monetised benefits at 22/23-Q4 is 2899m. The project currently reports monetised benefits of 2,898.76m.The benefits are focussed on ensuring the right outcomes and impacts for end-users, in terms of the ease of access and quality of services, and reduced steady-state running costs. | MOJ_0028_1314-Q2
PFI Prison Expiry and Transfer Tranche 1 | MOJ | Government Transformation and Service Delivery | The aim of this project is to carry out the exit and transfer of services at HMP Parc, Altcourse and Lowdham Grange in a safe, effective and efficient manner following the expiry of their PFI contracts between Q4 2022 and Q2 2023. HMPPS is undertaking essential work to ensure it is able to manage the expiry of the Project Agreements and transfer the service, while maintaining regime continuity and to ensure opportunities to modernise the sites and align service provision to future needs are fully considered. | Green |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. Compared to21/22 Q4, the project's Delivery Confidence Assessment rating remained Amber.The Amber assessment is due to risk of delays for remedial activities. The project has successfully mobilised and transitioned two of three sites to new operators and the final site is on track to delivery in line with the baseline schedule. | 2019-04-01 | 2024-01-20 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-09-30 to 2024-01-20. This is primarily due to the following factors. The programme schedule has been re-baselined and delivery is on now track. | 42.18 | 37.75 | -11 | The underspend is due to savings delivered through the new contracts. | 1638 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 1618m. to 1638m. This is primarily due to the following factors. The Whole Life Cost has been updated so that it now includes operating costs for Parc, Lowdham Grange and Altcourse prisons over the period of the new operator contracts. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project expects to realise efficiencies in future operating costs following the transfer of service to new operator contracts when compared to the PFI contracts. The project benefits also include the focus on the continued quality of service across the PFI contracts until expiry, and following the transfer of service, improvements in service quality in the new contract in line with the key priorities set out in the Prison Strategy White Paper. | MOJ_0051_2021-Q2
PFI Prison Expiry and Transfer Tranche 2 | MOJ | Government Transformation and Service Delivery | The aim of this project is to carry out the exit and transfer of services at HMP Ashfield, Forest Bank and Rye Hill in a safe, effective and efficient manner following the expiry of their PFI contracts between Q3 2023 and Q4 2025. HMPPS is undertaking essential work to ensure it is able to manage the expiry of the Project Agreements and transfer the service, while maintaining regime continuity and to ensure opportunities to modernise the sites and align service provision to future needs are fully considered |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is the first time data has been published for this project, which has been added to GMPP over the last year.The Amber assessment is due to inherent risk in the project's timelines. | 2022-01-22 | 2026-07-31 | The project's end-date at 22/23-Q4 is 2026-07-31. This is primarily due to the following factors. The project is on track against the baseline schedule. | 0 | 0.91 | Inf | Variance is less than 5%, so no narrative required | 1544 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 1544m. This is primarily due to the following factors. The Whole Life Costs includecosts of operating the three prisons andexpected capital costs. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project expects to realise efficiencies in future operating costs following the transfer of service to new operator contracts when compared to the PFI contracts. The project benefits also include the focus on the continued quality of service across the PFI contracts until expiry, and following the transfer of service, improvements in service quality in the new contract in line with the key priorities set out in the Prison Strategy White Paper. | MOJ_0060_2122-Q3
Print Recompete | MOJ | ICT | This project is renewing the department's print contract; establishing an open framework competition to ensure value for money and the delivery of a high-quality service. The new print contract will deliver an improved contract and new devices across the MoJ estate. |  | Red | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 decreased from Amber to Red. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating decreased form Amber to RedWhile the project has successfully moved into deployment of the service, the red assessment is due to delivery challenges which are impacting roll out. | 2019-02-01 | 2023-12-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-06-12 to 2023-12-30. This is primarily due to the following factors. The project has successfully moved into deployment, however is facing delivery challenges which are impacting progress and the project is evaluating options. | 14.5 | 1.67 | -88 | The variance in the in-year spend issue to delay in deployment which has required costs to be re-profiled into future years | 80 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 80m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. | 7 | The project's departmental-agree monetised benefits at 22/23-Q4 is 7m. The project reports monetised benefits of 6.66m.The projects benefits reflect a rationalised print fleet and new print and scan services that will reduced manual printing and handling across some MoJ business areas. | MOJ_0054_2021-Q4
Prison Retail | MOJ | Government Transformation and Service Delivery | Re-competition of the Prison Retail contract, which delivers a service to all public sector prisons and 4 private prisons in England and Wales. This service is a critical operational function within the prison estate, providing prisoners with the opportunity for choice and contributes to a more safe, decent and secure environment within prisons. The service also supports rehabilitation by providing prisoner employment positions; prisoners have an opportunity to learn vocational skills and gain real-world experience and prepare and secure employment on release. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 2017-04-03 | 2023-06-30 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2023-03-31 to 2023-06-30. This is primarily due to the following factors. The programme schedule has been re-baselined. | 81.13 | 81.13 | 0 | Variance less than 5%, so no narrative required | 660 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 660m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are related to the successful operation of the Prison Retail Service. | MOJ_0055_2021-Q4
Prison Technology Transformation Programme (PTTP) | MOJ | ICT | PTTP is delivering new end user technology for HM Prison Service (HMPS) and its Headquarters, to replace the existing Quantum IT system. This includes designing and delivering a new infrastructure build and service support solution, and providing staff with a modern working 'MoJ Official' device using Microsoft Office 365 operating on Windows 10 in the Cloud. The new platform and devices are being deployed to around 60,000 HMPS technology users spread across over 160 public and private prisons and HQ sites. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained Amber.The Amber assessment is due to work remaining to successfully exit contracts and complete transition of the service to business-as-usual operations. National deployment has completed, with over 71,185 users now live. | 2019-04-01 | 2023-09-25 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 decreased from 2023-12-31 to 2023-09-25. This is primarily due to the following factors. The programme has accelerated delivery against the baseline schedule. | 72.79 | 67.51 | -7 | The key variance represents movements in the budget allocations. | 234 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 234m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. | 70 | The project's departmental-agree monetised benefits at 22/23-Q4 is 70m. The project reports monetised benefits of 70.35m.The benefits are based on costs savings as a result of efficiencies driven by the new approach and contracts | MOJ_0044_1920-Q2
Prisoner Education Services | MOJ | Government Transformation and Service Delivery | The Prisoner Education Service is part of the Reducing Reoffending Portfolio within His Majesty's Prison and Probation Service. The programme has three main objectives: 1. Improve the numeracy and literacy of all prisoners who need it 2. Incentivise prisoners to improve their qualifications and skills to increase prospects of finding work/integrating back into society 3. Ensure Governors and their teams have the knowledge, tools and support they need to lead this work. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is thefirst timedata has been published for this project, which has been added to GMPP over the last year.The Amber assessment is driven by inflation risks. | 2021-04-01 | 2025-06-30 | The project's end-date at 22/23-Q4 is 2025-06-30. This is primarily due to the following factors. The programme is on track to deliver against the baseline schedule. | 3.5 | 3.5 | 0 | Variance is less than 5%, so no narrative required | 1884 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 1884m. This is primarily due to the following factors. The Whole life costs are based on the most recent business case and include optimism bias. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are related to the successful onward operation of the Prison Education service. | MOJ_0064_2122-Q3
Probation Workforce Reform | MOJ | Government Transformation and Service Delivery | The aim is to build a strengthened, innovative and professional Probation workforce which leads the criminal justice system, protects the public and reduces re-offending now and in the future. The Programme aims to create a modernised, diverse and open workforce culture that enables our people to be their best. This will ultimately reduce reoffending, protect the public and deliver change in a way which achieves value for money. |  | Amber | Compared to financial year 21/22-Q4, the Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained AmberThe Amber assessment is due to risks to recruitment and training of operational resources. | 2020-04-01 | 2025-03-25 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-25. This is primarily due to the following factors. The programme is on schedule to deliver within the agreed timelines. | 31.08 | 20.31 | -35 | The in-year underspend is due to scope/delivery changes, alongside resource recruitment and retention challenges. | 241 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 241m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are focussed on the improvement of the Probation Workforce and associated services. | MOJ_0060_2122-Q1
Rapid Deployment Cells Project | MOJ | Infrastructure and Construction | Rapid Deployment Cells offers a flexible capacity solution across the prison estate. The project is designed to provide a significant number of spaces at pre-determined sites. | Amber |  | Compared to financial year 21/22-Q4, the Delivery Confidence Assessment rating at 22/23-Q4 increased from Red (SRO rating) to Amber (IPA rating). This is primarily due to the following factors. Compared to21/22 Q4, theproject'sDelivery Confidence Assessment has improved from Red to Amber.TheAmber assessment is due to planning permission delays, changes tobuilding regulations and challenges in sourcing sufficient utilities to support sites.The project is managing the cost challenges that drove the Red rating last year and developed a business case that consolidates the two phases of the project into a single programme in two phases. One site has fully delivered. | 2020-08-17 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 104.06 | 99.06 | -5 | Variance is less than 5%, so no narrative required | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0057_2122-Q1
Small Secure Houseblocks | MOJ | Infrastructure and Construction | Small Secure Houseblock units will provide secure, permanent accommodation within the closed estate. The project provides a new style of accommodation for deployment in existing prison sites. Small Secure Houseblock units meet the technical needs and security standards required for Category C prisons. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. This is thefirst timedata has been published for this project, which has been added to GMPP over the last year.The Amber assessment is due to inherent risk in the project's timelines. . | 2021-11-15 | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | 13.3 | 6.69 | -50 | The underspend is due to procurement challenges | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. | Exempt under Section 43 of the Freedom of Information Act 2000 (Commercial Interests) - Commercial interests. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. Due to the projected increasing prisons population, this project focusses on increasing capacity and there are no monetised benefits to be claimed. The programme's other benefits are defined in the current baseline as: construction benefits and outcomes (capacity, modern methods of construction and sustainability); to enable an improvement in prisoner rehabilitation outcomes; and, during its construction, deliver local community benefits. | MOJ_0144_2223-Q2
YOI Education Services Retender | MOJ | Government Transformation and Service Delivery | There is a legal duty on HM Government to provide education to all children of school age; equally, access to education is every child's right and a key part of delivering both the statutory aims of Youth Justice and realising the strategic objectives of Youth Custody Service. These include to reduce re-offending, protecting the public from harm and ensuring that our prisons are decent, safe and productive places to live. The previous contracts for education services in public sector Young Offender Institutions (YOIs) in England ended between September and December 2022. A replacement education service has now been delivered by the YOI Education Services Retender project, which sought to transform the quality of learning in YOIs in order to support better outcomes for young people in our care including in terms of transition and resettlement, and to help promote positive identity shift. |  | Green | Compared to financial year 21/22-Q4, Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 increased from Amber to Green. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating improved from Amber to GreenThe project has now successfully delivered the service and transition to operational delivery has now been completed. | 2018-09-03 | 2023-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2023-03-31. This is primarily due to the following factors. The project successfully closed in line with the baselined schedule. | 13.4 | 12.8 | -4 | Variance less than 5%, so no narrative required | 133 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 remained at 133m. This is primarily due to the following factors. The Whole Life Cost has remained static, and the budget remains aligned to the current baseline business case. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project's benefits are related to the successful operation of the YOI Education Service. | MOJ_0056_2021-Q4
Youth Justice Reform Programme | MOJ | Government Transformation and Service Delivery | The Youth Justice Reform Programme has two aims: to make youth custody a place of safety both for children and those who work there, and to improve the life chances of children in custody. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Compared to 21/22 Q4, the project's Delivery Confidence Assessment rating remained AmberThe Amber assessment is due to the risks to operational recruitment, delays to the completion of the construction phase. | 2016-12-12 | 2024-08-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 increased from 2022-12-31 to 2024-08-31. This is primarily due to the following factors. The project re-baselined due to delays to the completion of the construction phase and remaining project activity is mobilisation and staffing of the Oasis Restore Secure School. | 41.89 | 40.6 | -3 | Variance less than 5%, so no narrative required. | 659 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 444m. to 659m. This is primarily due to the following factors. The Whole Life Cost has increased due to a change in the accounting calculation and for removal of income saving from future accounting years. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. This project currently reports no monetised benefits. The project benefits focus on improvements in education, safety in custody and reoffending for young people in the youth custody environment. Some of these benefits will be monetised but will not be realised until several years after the school opening. | MOJ_0040_1718-Q3
NCA Transformation Portfolio | NCA | Government Transformation and Service Delivery | The NCA's Transformation Portfolio will enable the NCA to become an intelligence led and digitally driven organisation. Our current capabilities and operating model limit our ability to relentlessly disrupt the changing threats, especially internet and digitally related threats. The NCA's Transformation Portfolio will deliver the culture, capability and capacity to enable the NCA to be a world-class law enforcement agency, leading the work to cut serious and organised crime. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Programme leadership, governance and assurance has been a key focus for the Agency following the 2022 IPA Gate 0 Review. A governance review included launching an Executive Committee which meets fortnightly, bringing the governance of Finance, Investment and Change closer together, appointing a new Transformation Director and strengthening our 2nd line assurance. In addition, there is a greater understanding of the workforce requirements and the skills required to deliver the agency ambition by reviewing our attraction strategies to encourage people to work for the agency and considering how we use our commercial contracts to ensure the best value for money. This year embedding benefit realisation into our performance framework is critical so that our governing boards focus on delivery that impacts on operational performance, and we will continue to develop our capability model to move away from a Command approach to define our future requirements. | 2014-04-01 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. There has been no deviation from schedule as the NCAs Transformation Programme remains aligned to the Agencys Strategy 23 28. The Transformation Programme (the portfolio) has been delivering since 2014, and continues to build capability and set the basis for transformation of our digital, data and technology and future estates. These activities builds on and provide firm direction for the Spending Review (SR) period and sets the foundations for future investments in subsequent SR rounds. The forward plan is divided into three tranches Tranche 1 (SR period 22-24), Tranche 2 (SR period 25-27) and Tranche 3 (SR Period 28-30). | 320.62 | 320.62 | 0 | The budget variance is inferior or equal to 5%. None | 2184 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 2189m. to 2184m. This is primarily due to the following factors. The decrease in whole life cost is as a result of aligning the WLC to the approved FY 22/23 Portfolio Business Case. There has been no change in forecast in future years at this stage. | 3086 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3086m. The project's departmental-agree monetised benefits at 22/23-Q4 is 3086m.The project's departmental-agree monetised benefits at 22/23-Q4 is 3086m.The project's departmental-agree monetised benefits at 22/23-Q4 is 3086m. The benefits figure is driven by the NCA Portfolio Business Case v1.2 and the contributing Programme level benefits. Benefit actuals are currently in the process of validation by the programme and the end of year benefit position will be available for reporting in Q1 of FY 23/24. | NCA_0001_1415-Q2
Census & Data Collection Transformation Programme | ONS | Government Transformation and Service Delivery | Delivering a successful 2021 Census, researching how to make it the last of its kind and transforming the work of ONS in how we collect, process and analyse data. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. The Programme has successfully processed the 2021 Census data and delivered outputs including: The 2021 Census First Release, Topic Summaries, multi-variate outputs and build your own dataset functionality in early 2023.Work has continued to Transform Population and Migration Statistics and the 2023 National Statisticians recommendation. Initial evidence was completed to time with the use of work rounds, however further evidence is needed which will impact associated consultation work.The transformation of Data Collection has continued with the Labour Market Survey now utilising "knock to nudge" in the field. Some challenges have been identified and following detailed options planning an extension is required to meet quality criteria.The Statistical Business Register has been outsourced. Delivery to date has been positive with an Alpha delivered to time and a Beta phase underway. 85% of Surveys have now been moved online. Delivery is progressing to timescale and is on track to complete. | 2015-01-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. There has been no change to the programme end date. Benefits are on track to be delivered and Census benefits are not expected to change. The programme has no funding after 31 March 2024 and project delivery will be working to that date. However, the programme does not fully close until 31 March 2025. This final milestone in 2025 is related to the assessment of the benefits of the 2021 Census. The delivery of which will facilitate the full and complete closure of the programme. | 38.82 | 47.5 | 22 | The budget variance exceeds 5%. The 2022/2023 annual position as at period 11 accounts, is a forecast of 47.5m against a budget of 38.8m, giving a forecast overspend of 8.7m. During the planning period and for the first half of the Financial Year, it was expected that a further 10m could be called upon during the Supplementary Estimates from HM Treasury (HMT). After discussions between the Office for National Statistics (ONS) and HMT, a decision was made not to call upon this additional 10m. The Programme focussed on its 5 core deliverables alongside all expenditure across ONS being reviewed, in order to try to mitigate this shortfall as best as possible. This has resulted in a 4.2m reduction in forecast since Quarter 1 from 51.7m to 47.5m. We will confirm the final post audit position at the Quarter 1 2023/2024 GMPP return. | 876 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 886m. to 876m. This is primarily due to the following factors. The budgeted Whole Life Costs have reduced from 886m to 876m. This is due to initially expecting to receive 10m of funding at the Supplementary Estimate in the first half of the Financial Year, which was then not called upon after discussions between ONS and HM Treasury. | 6418 | The project's departmental-agree monetised benefits at 22/23-Q4 is 6418m. The project's departmental-agree monetised benefits at 22/23-Q4 is 6418m. Compared to financial year 2021/2022 Quarter 4 Benefits at 2022/2023 Quarter 4 increased from 5,643.92m to 6,417.71m. This is due to the Benefit figures being inflated to 2022/2023 prices using the March 2022 Office for Budget Responsibility (OBR) forecast, specifically 1.7 Supplementary economy tables. The forecast lifetime benefits are 6,415.89m, 1.82m below the baseline of 6,417.71m. | ONS_0002_1112-Q1
Integrated Data Programme | ONS | Government Transformation and Service Delivery | The Integrated Data Programme is a radical and transformative proposal to bring together ready to use data and enable faster and wider collaborative analysis for the public good. The service delivers a secure and trusted Cloud hosted integrated data service enabling end to end collaborative analysis and dissemination of statistical and analytical outputs. The service will significantly simplify, increase and expedite access to data while balancing legal, security, data protection and ethics and enhances data ready for use after applying assured methodology and data management practices. The service will enable accredited analysts and researchers from government, wider public services and research organisations to produce faster and deeper analytical outputs of targeted public policy questions and more effective social, health, economic and environmental outcomes. Policy focused analysis conducted across government will demonstrate value of integrated data and the additional evidence and insight that is generated from it. | Amber |  | Compared to financial year 21/22-Q4, the Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 remained at Amber. This is primarily due to the following factors. Actions to address the previous Gateway 0 review are complete or partially complete. The recent IPA Gateway 4 review made 11 recommendations. The Programme team accept and are working up detailed responses to these recommendations. | 2020-01-01 | 2025-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2025-03-31. This is primarily due to the following factors. The programme consistently delivers against milestones, including DEA accreditation and Public Beta release in March 2023. There remains very limited contingency in the plan and hence progress is closely monitored through Governance and proactive risk management. The recent IPA Gateway 4 review assigned an Amber rating to the programme, acknowledging the achievements to date and the challenges ahead. | 66.6 | 65.62 | -1 | The budget variance is inferior or equal to 5%. | 525 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 increased from 481m. to 525m. This is primarily due to the following factors. | 1814 | The project's departmental-agree monetised benefits at 22/23-Q4 is 1814m. The project's departmental-agree monetised benefits at 22/23-Q4 is 1814m. Following on from the first round of ONS and external benefit consultations for IDS by November 2021, the programme plans to re-engage with Other Government Departments and Devolved Administrations, analytical areas to finalise forecasted outcomes, to capture their analytical efficiencies and statistical financial benefits for the public good, by June 2023. The outcomes and evidence of which will provide actual data for future remodelling for the FBCR in 2023. These consultations will be with Tier 1 and 2 (target audience of Heads of Profession, Heads of Analysis and CDIOs) and now tier 3 stakeholders/beneficiaries. This will follow the iterative public beta delivery, starting with March Public Beta and the delivery of Show and Tells for Other Government Departments and Devolved Administrations and other key stakeholders, on key topics such as data, analysis and access, dissemination and IDS technology. | ONS_0003_2021-Q4
VOA Non - Domestic Rating Reforms Programme | VOA | Government Transformation and Service Delivery | The Non - Domestic Rating (NDR) Reforms Programme is a multi-year programme to deliver key commitments from the Governments 2021 Review of Business Rates. These include changes to the non-domestic rating system to enable a sustainable move to three- yearly revaluations, measures to provide greater transparency to ratepayers, and the implementation of new reliefs. |  | Amber | The Senior Responsible Owner's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. The Infrastructure Projects Authority assesses the overall Departmental Commentary Actions for the Non-Domestic Rating Reforms Programme to be Amber.This reflects the current uncertainty over the impact of delays to a separate Valuation Office Agency programme to replace legacy technology.The Review Team assessed that the issue is resolvable but will require constant management attention by the Programme. The Programme is undertaking a significant amount of work to manage the dependency and consider alternative delivery options as a contingency. | 2022-04-01 | 2029-03-31 | The project's end-date at 22/23-Q4 is 2029-03-31. This is primarily due to the following factors. The Programme is currently on plan but will need to impact the delay to legislation on delivery timelines. | 4.2 | 4.2 | 0 | The GMPP project did not provide data | 110 | The project's departmental-agree Whole Life Cost at 22/23-Q4 is 110m. This is primarily due to the following factors. The programme is at an early stage having concluded its initial discovery stage. This informed the development of the Strategic Outline Business informed by order of magnitude IT costs, subsequently achieving His Majesty's Treasury Approval in January 2023. The next iteration of the Business Case (outline ) will be following the Alpha stage (testing prototypes and optimum customer journey assumptions) of the programme expected in Autumn 2023. This will produce refined Whole Life Cycle costs. |  | The project did not provide departmental-agree monetised benefits at 22/23-Q4. The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4.The project did not provide departmental-agree monetised benefits at 22/23-Q4. We are working to quantify the economic benefit of more frequent revaluations that the programme enables, and consider whether it is appropriate to include this at Outline Business Case stage. | HMRC_0143_2223-Q2